MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF GOVERNMENT

END-TERM REPORT – SELF-ASSESSMENT

OF PROGRESS ON THE OPEN GOVERNMENT PARTNERSHIP ACTION PLAN IMPLEMENTATION

IN THE REPUBLIC OF SERBIA FOR 2014 AND 2015

Belgrade, October 2016.

1. INTRODUCTION

The Open Government Partnership (hereinafter referred to as: OGP)  is an international multi-stakeholder initiative that aims to provide support to participating countries in creating open, transparent, efficient and accountable administration, citizen-oriented, through building public trust, cooperation with civil society organizations (hereinafter referred to as: CSOs), empowering civic participation in public affairs, fight against corruption, freedom of information, using modern technologies, in order to make public authorities more efficient and accountable. This initiative was formally launched on 20 September 2011, when the eight founding governments endorsed the Open Government Declaration. It gathers today 70 participating countries.

Participation in this initiative is recognized by the Republic of Serbia as an excellent way to implement the general objective of the Public Administration Reform, which includes the provision of high quality services to citizens and businesses, and development of public administration which will significantly contribute to economic stability and raising living standard.

The general OGP values are fully in line with the Government's commitment to build administration based on general principles of "good governance" and "open government", and to provide full implementation of generally accepted principles of the rule of law and legal certainty, transparency, accountability, cost-effectiveness and efficiency. Also, since the Open Government Partnership provides an international forum for dialogue and sharing experience among governments, civil society organizations and the private sector, constant cooperation with OGP participating countries provides a realistic assessment of the situation, and the need for further improvements.

In March 2012, at the proposal of the then Ministry of Culture, Media and Information Society, the Republic of Serbia submitted its Letter of Intent to the OGP Steering Committee announcing its intention to join the initiative, and by doing so it assumed the obligation to develop an action plan and endorse the open government principles laid out in the Open Government Declaration. Its first Action Plan for 2013 the Government adopted in April 2013, and appointed the then Ministry of Justice and Public Administration as the institution responsible to implement activities related to the Serbia accession to the OGP initiative. Due to the fact that when the 2013 Action Plan was adopted it was concluded that there was a need for improvement, this Action Plan was not officially presented to the OGP initiative. Instead, the authorities started to prepare a new and improved action plan.

Development of the Action Plan for implementation of the Open Government Initiative in the Republic of Serbia for 2014 and 2015 began in December 2013, and it was adopted on 25 December 2014 (hereinafter referred to as: Action Plan). Due to new organizational set up of the state administration authorities in line with the new Law on Ministries adopted in April 2014, the responsibility to implement activities related to the participation of the Republic of Serbia in the OGP initiative and develop an Action Plan was transferred to the Ministry of Public Administration and Local Self-Government.

The commitments set out in this Action Plan pertain to several “OGP grand challenges”, and special attention was paid to increasing public integrity (commitments pertaining to fight against corruption, public ethics, freedom of information, the freedom of media and civil society) and efficient management of public resources. During the selection of these challenges, attention was paid to the activities that were already covered by the 2013 Action Plan, as well as the need to harmonize the Action Plan activities with other strategic documents of the Republic of Serbia.

The undertaken commitments are grouped into several chapters: 1) Fiscal transparency, 2) Prevention – fight against corruption, 3) Access to information and 4) Public participation. The undertaken commitments, included in these chapters, reflect the determination of the Republic of Serbia to continuously promote the OGP values: transparency, accountability, public participation and the use of new technologies and innovations for openness and accountability. Promotion of these values is reflected in great efforts of the Republic of Serbia to develop all government levels in order to increase legal certainty, transparency, ethical standards and accountability of the public administration, improve the business environment and create favorable business climate, modernization, and hence the quality of services provided to citizens. The overall objective of the entire administration reform in the Republic of Serbia is to build reliable, accountable, transparent, efficient and economic government, available to users – citizens, business and other entities, which provides high quality services in line with the so-called “European principles of good public administration”. In keeping with that, cooperation with civil society is of great importance, which is one of the key prerequisites for the open government concept that has been constantly being improved in the Republic of Serbia. Dialogue between civil society and the administration is improved continuously, through various forms of cooperation, which will be discussed in more detail in the section on development and monitoring the implementation of the Action Plan.

2. ACTION PLAN DEVELOPMENT AND MONITORING OF ITS IMPLEMENTATION

Development of the Action Plan started in December 2013 with the establishment of a Project group, comprised of ten members (7 representatives of public authorities: the then Ministry of Justice and Public Administration, Ministry of Finance, Ministry of Culture and Information, Ministry of Regional Development and Local Self-Government, and Ministry of Foreign and Domestic Trade and Telecommunications; 2 representatives of special organizations: Public Procurement Office, Office for Cooperation with Civil Society; and one representative of an independent state authority: Anti-Corruption Agency).

Bearing in mind that one of the key prerequisites for the open government concept is the inclusion of civil sector and other stakeholders in the decision-making process, the then Ministry of Justice and Public Administration published a public call to all CSOs inviting them to participate in a consultative meeting that should define the manner of cooperation during Action Plan development. The public call was published on the websites of the Ministry and the Office for Cooperation with Civil Society (hereinafter referred to as: Office). Representatives of nine civil society organizations (Civic Initiatives, Transparency Serbia, BIRN, CRTA, Educational Center, CEP, Center for Development of Serbia, Mikro Art) took part in this meeting.

Considering the fact that at that moment there was no adequate mechanism for the selection of relevant representatives of civil society organizations within the civil sector, who would participate in the work of the Project group, it was agreed to publish proposed topics and working versions of the Action Plan on the websites of the then Ministry of Justice and the Office, with a comments template-form that would be used by civil society representatives to submit their comments, proposals, and suggestions to the proposed text of the Action Plan, which would be subsequently discussed at joint meetings.

During the preparation of the Action Plan, Project group held two meetings, in December 2013 and April 2014. In addition, the drafting of the Action Plan and communication between the Project group members was conducted electronically. Furthermore, the Ministry in charge of public administration held two more meetings with civil society representatives, on 24 April, where 18 representatives of civil society took part in the meeting, and on 4 July 2014, where over 30 representatives of civil society organizations were present. The last meeting with civil society organizations was also attended by several members of the Project group coming from institutions in charge of the implementation of the activities set out in the Action Plan, and the meeting was opened by State Secretary in the Ministry of Public Administration and Local Self-Government.

Public calls for each meeting, including relevant material, were published in advance, in order to provide civil society organizations with the opportunity to prepare and timely submit their suggestions and comments to the working versions of the Action Plan, to be latterly discussed at meetings. The Office also sent calls to all civil society organizations from its database, as well as posted relevant information on its Facebook profile.

According to the recommendations of the Open Government Partnership, the participating country should set up a mechanism for regular consultation with civil society on the implementation of the commitments and activities defined in the Action Plan. Due to the insufficient human resources and technical capabilities this mechanism was not established during the Action Plan implementation. On the other hand, the Republic of Serbia has already established the Office for Cooperation with Civil Society of the Government of the Republic of Serbia which was set up by the Regulation on the Office for Cooperation with Civil Society which serves as an institutional mechanism for support and promotion of the civil dialogue between government institutions and civil society organizations. On 26 August 2014 the RS Government adopted Guidelines for the Inclusion of Civil Society Organizations in the regulation adoption process, aiming to systematically regulate the cooperation between public authorities and civil society organizations. The recommendation issued by the Serbian Government specifying that, apart from public authorities, these Guidelines should also be observed by the authorities of the autonomous province and local self-governments, demonstrates the need that the issue of cooperation between the public and civil sector is resolved on all government levels. This is one of the key preconditions for further growth and development of the civil society in Serbia, but also for the overall improvement of the work performed by the Serbian institutions aimed at transparent decision making process and effective and efficient execution of decisions made.

In addition, Serbia’s commitment to the values underpinning the Open Government Partnership, and particularly to the cooperation with the civil sector, is also reflected in new initiatives for drafting, implementing and monitoring public policies. A good example is the preparation of the Action Plan implementing the RS Public Administration Reform Strategy for 2015-2017 and establishment of structures for coordination and monitoring of the public administration reform, where civil society representatives participate on an equal footing to civil servants and state secretaries. Their participation is ensured through the mechanism of Sector Civil Society Organization for public administration issues.  The Structure for reform coordination also includes the Standing Conference of Towns and Municipalities (SCTM), as a link to the local self-government. Due to the fact that this Action Plan sets out the adoption and implementation of the OGP Action Plan, and that it also contains the most significant activities from the OGP Action Plan, its monitoring can be used to a certain extent for the monitoring of the activities specified in the OGP Action Plan.

The MPALSG, with support of the Office for Cooperationwith Civil Society should organize consultative meeting with external stakeholders (not only civil society organizations, but also the private sector) to discuss the mechanisms for the  multistakeholder consultations and the drafting process of the next action plan.

The MPALSG should initiate the action plan consultation process in the presence of the representatives

identified from concerned state bodies, and it should be done prior

to developing a working draft to allow for external stakeholders to have a substantial impact in the stage of formulation.

In addition, the competent state administration authorities supported the research team of an Independent Reporting Mechanism (hereinafter referred to as: IRM) which is part of the OGP initiative that reviews development and implementation of the Action Plan. This support was provided both in the form of interviews that were conducted with the aim to gain the best possible overview of the status of defined activities, and during the organization of consultative meetings held between the Independent Reporting Mechanism researchers and civil sector representatives for the presentation of preliminary research results and collection of data and comments from the civil society with respect to the implementation of the OGP Action Plan.

It is worth mentioning that during the Action Plan implementation there was significant progress in terms of cooperation of the government with civil society. Namely, preliminary annual report prepared by the IRM contained, among other things, key recommendations for improving the activities in the next action plan which RS fully accepted and most of them implemented during the second Action Plan cycle.

IN THE SECOND CYCLE OF THE DRAFTING THE NAP, ТHE CIVIL SOCIETY WAS ACTIVELY INVOLVED FROM THE VERY BEGINNING, PRIOR TO DEVELOPING FIRST WORKING DRAFT, SO THE COMMITMENTS SPECIFIED IN THE SECOND NAP WERE ENTIRELY THE RESULT OF THE JOINT WORK OF THE COMPETENT AUTHORITIES AND CSOs, I.E. ALMOST ALL COMMITMENTS WERE INCLUDED AT THE PROPOSAL OF CSOs. http://www.mduls.gov.rs/partnerstvo-otv-upravu-2017.php и www.ogp.rs

IRM Recommendations

SIGNIFICANT ACIEVEMENTS

PUBLISHING THE RS CITIZEN BUDGET

STRENGTHEN THE SYSTEMIC FUNCTION OF CONTROL IN PA

Enhanced cooperation with civil society is reflected, firstly, in the fact that in the second Action Plan cycle, the civil society was actively involved from the very beginning, before the first working version of the Action Plan was drafted, so that the commitments specified in the second Action Plan entirely the result of the joint work of the competent authorities and CSOs, i.e. almost all commitments were included at the proposal of CSOs. Also, six representatives of CSOs, selected in a transparent procedure, were included in establishing a special Inter-Ministerial working group for drafting the second Action Plan for the period 2016-2017 and realization of Serbia’s participation in the Open Government Partnership initiative. In addition, to keep the consultative process as wide as possible, consultative meetings with civil society representatives were held outside the capital, namely in Novi Sad and Nis. Representatives of local self-governments and the autonomous province also took part at these meetings. The meetings, and the consultations, were also used to promote the OGP initiative and its underlying values.

STRENGTHENING CSO PARTICIPATION IN PAR MONITORING PAR

Regarding the mechanism for regular consultation, it is necessary to mention that a non-governmental organization, whose representatives are actively involved in the work of the Working group mandated to draft the second Action Plan, the Center for Research, Transparency and Accountability – CRTA, established the OGP website (http://www.ogp.rs) where detail information can be viewed about the implementation of this initiative in the Republic of Serbia, all relevant documents relating to Action Plan development, including the heading“get involved” through which the public may propose commitments which would be included in the Action Plan. The Ministry of Public Administration and Local Self-Government (hereinafter referred to as: MPALS) closely cooperates with CRTA on the content of this website and delivers all relevant documents that need to be published. Also, MPALS publishes on its website all information regarding the OGP activities:http://www.mduls.gov.rs/partnerstvo-za-otvorenu-upravu.php .

4. REVIEW OF COMMITMENTS AND ACTIVITIES

In keeping with the rules of the Open Government Partnership initiative, the Ministry of Public Administration and Local Self-Government, which was appointed by the Government to conduct activities related to the participation of the Republic of Serbia in this initiative, began the preparation of the Self-Assessment Report of Progress on the OGP Action Plan implementation. The process began with the submission of the reporting forms for each activity to the state administration authorities responsible for their implementation. This report is drawn up based on separate reports submitted by the competent authorities.

The Action Plan defines 13 commitments, comprising the total of 25 separate activities. For each activity, the Action Plan identifies the implementation steps with clearly defined end dates and leading agencies. Out of 25 planned activities, 11 activities were fully completed, 9 activities were substantially completed, 3 activities were partially completed, and 2 have not been started.

Graph1: Graph showing completion level of the activities set out in the OGP Action Plan

Out of the total of 25 activities, the Ministry of Public Administration and Local Self-Government, without the constituent bodies, is responsible for the implementation of 5 activities, the Ministry of Finance for 4 activities, the Directorate for eGovernment for 5 activities, as well as the Office for Cooperation with Civil Society, while the Ministry of Justice is responsible 3 activities, and the Public Procurement Office for 2 activities. Local self-government units are responsible for 2 activities, one of which is jointly implemented with the Ministry of Finance at the local level.

Graph 2: Graph showing the institutions responsible for implementation of the activities specified in the OGP Action Plan

Graph 3: Graph showing the completion level broken down by responsible institutions

It should be noted that the Action Plan is designed in such a way that certain activities which are under the responsibility of different state administration authorities are planned within the same commitments. That is why this report contains information for each activity that can be deemed a commitment, given that for every activity the relevant steps and end dates are defined.

COMMITMENT 1: IMPROVE TRANSPERENCY IN MONITORING BUDGET EXPENDITURES

| Activity 1.1. Publish the Annual Activity Report of Budget Inspection |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead implementing agency: |  | Ministry of Finance |  |  |  |
| Responsible person: |  | Zarko Savic |  |  |  |
| E-mail: |  | zarko.savic@mfin.gov.rs |  |  |  |
| Phone: |  | 0113642 975 |  |  |  |
| Other Actors Involved | Government |  |  |  |  |
|  | CSOs, private sector, working groups, multilaterals |  |  |  |  |
| Main objective |  | Improve transparency in budget expenditures |  |  |  |
| Brief description of activity: |  | Publication of the Annual Activity Report of Budget Inspection, which is delivered to the Government for consideration and adoption, on the website of the Ministry of Finance, to be available to all interested parties. |  |  |  |
| Relevance: (Briefly describe the way in which this commitment is relevant to further advancing OGP values –access to information, public accountability, civic participation, and technology and innovation for openness and accountability) |  | The function of Budget Inspection is to control the application of laws in the field of material-financial business operations, as well as purposeful and legal usage of funds by budget beneficiaries. Publication of the Annual Activity Report of Budget Inspection on the Ministry’s website will enable the citizens to obtain information about purposeful and legal usage of funds and to control the usage of funds, which will contribute to better transparency and stronger public confidence in the government, as well as the accountability of institutions. |  |  |  |
| Ambition: (Briefly describe the intended strategic results and how this commitment will either make government more openness or improve government through more openness) |  | It will enable the public to obtain more information about the work performed by institution, as well as the control over the public resources management and public funds spending. |  |  |  |
| Completion level: |  | Not started | Limited | Substantial | Completed |
|  |  |  |  |  | X |
| Description of the results: (Include specific activities within the reporting period (first or second year of the action plan) and, wherever possible, please indicate whether there has been evidence of members of the public using the commitment or whether the commitment has had an effect. |  | As stipulated in Article 86 of the Budget System Law, the function of Budget Inspection is to control the application of laws in the field of material-financial business operations, as well as purposeful and legal usage of funds by the abovementioned entities. In the reporting period, Budget Inspection conducted the control in line with its 2014 Work Plan and Programme developed by the Minister of Finance, as well as in keeping with special instructions issued by the Minister to conduct the control of certain entities that are not included in the Work Plan and Programme, as specified in Article 90 (2) of the Budget System Law and Article 4 (2) of the Regulation on the work, powers and features of the Budget Inspection. The annual report is published on the Ministry of Finance website: (http://www.mfin.gov.rs/UserFiles/File/dokumenti/2015/Izvestaj%20o% 20radu%20B%20I%20%20za%202014%20.pdf) |  |  |  |
| End date/Completion date: |  | May 2015 |  |  |  |
| Next steps: |  | Continue publishing the annual report on the Ministry of Finance’s website |  |  |  |
| Additional information (Description on what remains to be achieved and any risks or challenges to implementing the commitment) |  |  |  |  |  |

| Activity 1.2. Publish the Budget Execution Report |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead implementing agency: |  | Ministry of Finance LSUs |  |  |  |
| Responsible person: |  | Mirjana Cobjasic, Ministry of Finance |  |  |  |
| E-mail: |  | mirjana.cojbasic@mfin.gov.rs |  |  |  |
| Phone: |  | 011 3642 932 |  |  |  |
| Other Actors Involved | Government |  |  |  |  |
|  | CSOs, private sector, working groups, multilaterals |  |  |  |  |
| Main objective |  | Improve transparency in budget expenditures |  |  |  |
| Brief description of activity: |  | Budget Execution Reports that the Minister, or local self-government unit department responsible for finance, communicates at least twice a year to the Government, or to the competent authority of local self-government unit, for consideration and adoption, are published on the websites of state administration authorities and local self-government units and communicated to the National Assembly, or Assembly of the local self-government. |  |  |  |
| Relevance: (Briefly describe the way in which this commitment is relevant to further advancing OGP values –access to information, public accountability, civic participation, and technology and innovation for openness and accountability) |  | As is the case with the previous activity, the publication of Budget Execution Report contributes to better transparency and accountability of institutions and stronger public confidence. |  |  |  |
| Ambition: (Briefly describe the intended strategic results and how this commitment will either make government more openness or improve government through more openness) |  | Implementation of this activity will significantly improve the access to relevant information about the work of institutions and enable better control of public resources management and public funds spending. |  |  |  |
| Completion level: |  | Not started | Limited | Substantial | Completed |
|  |  |  |  | Х |  |
| Description of the results: (Include specific activities within the reporting period (first or second year of the action plan) and, wherever possible, please indicate whether there has been evidence of members of the public using the commitment or whether the commitment has had an effect. |  | The Ministry of Finance publishes on its website а monthly Bulletin Public Finances, and is therefore available to all interested parties, thus providing free access to information ( http://www.mfin.gov.rs/pages/issue.php?id=1568) LSUs are obligated to publish their budgets in the local office gazette. However, during the monitoring of the implementation of this activity, it has been discovered that there is neither mechanism nor the capacity to monitor the implementation of this activity on the local level. |  |  |  |
| End date/Completion date: |  | July 2015 |  |  |  |
| Next steps: |  | Continue publishing the Bulletin on the website of the Ministry of Finance |  |  |  |
| Additional information (Description on what remains to be achieved and any risks or challenges to implementing the commitment) |  |  |  |  |  |
| During the monitoring, it has been discovered that there is neither mechanism nor the capacity to monitor the implementation of this activity on the local level. Therefore, it is recommended that such mechanism is set up, in cooperation with civil society organizations and with their assistance. |  |  |  |  |  |

| Activity 1.3. Publish the RS Citizen Budget |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead implementing agency: |  | Ministry of Finance |  |  |  |
| Responsible person: |  | Mirjana Cojbasic |  |  |  |
| E-mail: |  | mirjana.cojbasic@mfin.gov.rs |  |  |  |
| Phone: |  | 011 3642 932 |  |  |  |
| Other Actors Involved | Government |  |  |  |  |
|  | CSOs, private sector, working groups, multilaterals |  |  |  |  |
| Main objective |  | Improve transparency in budget expenditures |  |  |  |
| Brief description of activity: |  | Publication of Civil Budget Document which in clear, simple, and understandable way and concisely summarizes the Budget of the Republic of Serbia to citizens. |  |  |  |
| Relevance: (Briefly describe the way in which this commitment is relevant to further advancing OGP values –access to information, public accountability, civic participation, and technology and innovation for openness and accountability) |  | Every government is funded from the budget which is comprised of the resources collected from citizens. Therefore, all citizens have the right to know how and for what purposes the budget funds are spent, which in turn calls for the budget that is clear and easy to understand. This contributes to better transparency, as well as public accountability and stronger public confidence. |  |  |  |
| Ambition: (Briefly describe the intended strategic results and how this commitment will either make government more openness or improve government through more openness) |  | Better public access to information regarding the work of institutions and control of public resources management and public funds spending. More information about the budget obtained by the public and budget prepared in a clear and understandable way will encourage citizens to take a more active role in the budget process. |  |  |  |
| Completion level: |  | Not started | Limited | Substantial | Completed |
|  |  |  |  |  | X |
| Description of the results: (Include specific activities within the reporting period (first or second year of the action plan) and, wherever possible, please indicate whether there has been evidence of members of the public using the commitment or whether the commitment has had an effect |  | Considering the importance of public dialogue for the public finance management, the Ministry of Finance developed and presented the first Citizens’ Guide to the Budget of the Republic of Serbia. Given that the majority of budget funds come from the tax collection, the citizens are given all available information about the collection and spending of the Serbian budget funds in a clear and understandable way. (http://www.mfin.gov.rs/UserFiles/File/dokumenti/2015/Gradjanski_ vodic_kroz_budzet.pdf). We are confident that the Citizens’ Guide to the Budget of the Republic of Serbia will bring about a better understanding of the budget process, as well as the decisions that guided us during the budget preparation, and that in turn it will result in a better management of public funds and its harmonization with the best international practice. Publication of the Civil Budget Document was highly commended by the public. Citizens communicated with the employees of the Budget Department (by telephone) and expressed their satisfaction that such a significant document is presented to them in a clear way, showing them how the budget funds are spent. This activity has also been praised by the Centre for Research, Transparency and Accountability. |  |  |  |
| End date/Completion date: |  | July 2015 |  |  |  |
| Next steps: |  | Continue publishing the Civil Budget Document. |  |  |  |
| Additional information (Description on what remains to be achieved and any risks or challenges to implementing the commitment) |  |  |  |  |  |

| Activity 1.4. Publish the Local Self-Government Civil Budget Document |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead implementing agency: |  | LSUs |  |  |  |
| Responsible person: |  |  |  |  |  |
| E-mail: |  |  |  |  |  |
| Phone: |  |  |  |  |  |
| Other Actors Involved | Government |  |  |  |  |
|  | CSOs, private sector, working groups, multilaterals | Center for Research, Transparency and Accountability - CRTA |  |  |  |
| Main objective |  | Improve transparency in budget expenditures |  |  |  |
| Brief description of activity: |  | Publication of Civil Budget Document which in clear, simple, and understandable way, and concisely summarizes the Budget of the local self-government. |  |  |  |
| Relevance: (Briefly describe the way in which this commitment is relevant to further advancing OGP values –access to information, public accountability, civic participation, and technology and innovation for openness and accountability) |  | The initiative is that the local budget, which consists of the funds collected from the citizens, is presented to the public. As is the case with the previous activity, this activity will significantly contribute to more active engagement of citizens in the budget process, and the responsible management of the local budget will also raise the public confidence in the local institutions. In a civil budget document, the authorities can explain which government level is responsible for which functions and activities, and as such it can be invaluable for the dialogue between the government and the public. |  |  |  |
| Ambition: (Briefly describe the intended strategic results and how this commitment will either make government more openness or improve government through more openness) |  | Implementation of this activity will significantly improve the access to relevant information about the work of local institutions and enable better control of public funds spending. |  |  |  |
| Ниво реализације: |  | Спровођење није започело | Спроведено у мањој мери | Спроведено у знатној мери | Спроведено у потпуности |
|  |  |  | Х |  |  |
| Description of the results: (Include specific activities within the reporting period (first or second year of the action plan) and, wherever possible, please indicate whether there has been evidence of members of the public using the commitment or whether the commitment has had an effect |  | LSUs are obligated to publish their budgets in the local office gazette. In relation to this, there is a proportionally small number of LSUs that published Civil Budget Document, mainly those that received the support from civil society organizations. According to data supplied by Center for Research, Transparency and Accountability – CRTA, the 2013 Civil Budget Document was prepared by 10 LSUs, for 2014 – 15 LSUs. In the previous period, the Civil Budget Documents have beeen prepared with the support of the civil society organizations. Due to the inability to establish adequate cooperation with local governments and considering the limited resources of civil society and the difficult access to quality information in connection with the budget, civil society organizations were not able to carry out planned activities within the period of the Action Plan implementation. Specifically, even in 2014, a large number of LSUs was not willing to cooperate, mainly for reasons of lack of interest, so that, in 2015, instead of 10 planned civil budgets, civil society organizations were not able to develop any. |  |  |  |
| End date/Completion date: |  |  |  |  |  |
| Next steps: |  | Civil Budget Documents of LSUs would be more easily formulated with the help of the civil sector dealing with this area, if data of consolidated reports of towns and municipalities was published on open, machine readable format, presenting the local government expenditures broken down by the type of expenditures and sources of funding, as well as local government revenues broken down by type and source of funding. Also necessary are data related to annual financial statements of local public enterprises. It is intended that this activity is included in the next action plan for 2016-2017. In addition, it is necessary to develop a methodology and appoint a responsible person for monitoring the quality and frequency of civil budget document publication at the local level. |  |  |  |
| Additional information (Description on what remains to be achieved and any risks or challenges to implementing the commitment) |  |  |  |  |  |
| During the monitoring, it has been discovered that there is neither identified methodology nor the capacity to monitor the implementation of this activity and to assess the quality of civil budget documents. Therefore, it is recommended that such methodology is developed, with the support of civil society organizations. |  |  |  |  |  |

COMMITMENT 2. ELIMINATE GAPS IN THE LEGAL FRAMEWORK AND PROCESS OF OVERSIGHT OF FINANCING POLITICAL ACTIVITIES AND ENTITIES

| Activity 2.1. Amend the Law on Financing Political Activities |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead implementing agency: |  | Ministry of Finance |  |  |  |
| Responsible person: |  | Vesna Jevtic |  |  |  |
| E-mail: |  | vesna.jevtic@mfin.gov.rs |  |  |  |
| Phone: |  | 011 3642 873 |  |  |  |
| Other Actors Involved | Government |  |  |  |  |
|  | CSOs, private sector, working groups, multilaterals |  |  |  |  |
| Main objective |  | Improve transparency in budget expenditures |  |  |  |
| Brief description of activity: |  | Although the legal framework on financing political activities has been improved, in practice, it turned out that some legal solutions have deficiencies. In order to overcome these issues, the Ministry of Finance worked on improving provisions of the Law on Financing Political Activities to clearly define and delineate the responsibilities of the Anti-Corruption Agency, the State Audit Institution, and other bodies involved in the oversight of political activities, and to precisely determine mechanisms for transparency in financing the political entities. - Communicate the Draft Law to the Government for consideration and formulation of the Bill |  |  |  |
| Relevance: (Briefly describe the way in which this commitment is relevant to further advancing OGP values –access to information, public accountability, civic participation, and technology and innovation for openness and accountability) |  | Amendments to the Law on Financing Political Activities enable better control over spending of the budget funds allocated for financing of the regular activities and election campaigns of political entities, as well as public accountability for public spending and publication of Report by the Anti-Corruption Agency. |  |  |  |
| Ambition: (Briefly describe the intended strategic results and how this commitment will either make government more openness or improve government through more openness) |  | Improved legal framework will significantly contribute to better public access to information regarding the work of the institution and to the control of public resources management and public funds spending. |  |  |  |
| Completion level: |  | Not started | Limited | Substantial | Completed |
|  |  |  |  |  | Х |
| Description of the results: (Include specific activities within the reporting period (first or second year of the action plan) and, wherever possible, please indicate whether there has been evidence of members of the public using the commitment or whether the commitment has had an effect |  | Following a public debate when all interested parties were invited to submit proposals, suggestions and comments related to the draft law, the text of the Draft Law Amending the Law on Financing Political Activities was communicated to the Government. On sessions held in January, the Committee on Legal System and the Committee on Economy and Finance adopted conclusions and communicated the Draft Law to the Government for consideration and formulation of the Bill. |  |  |  |
| End date/Completion date: |  | The final version of the Action Plan for Chapter 23, which is aligned with the latest recommendations and approved by the European Commission, sets the deadline for this activity –3 Quarter 2016. |  |  |  |
| Next steps: |  | Adoption of the Bill and its communication to the National Assembly |  |  |  |
| Additional information (Description on what remains to be achieved and any risks or challenges to implementing the commitment) |  |  |  |  |  |
| Regarding the completion level of this commitment, it is stated that this commitment is completed due to the fact the Draft Law has been communicated the Government for consideration and formulation of the Bill. As specified in the Action Plan for Chapter 23, the deadline is 3 Quarter 2016 and the Government will act accordingly. |  |  |  |  |  |

COMMITMENT 3. INCREASE TRANSPARENCY IN PUBLIC PROCUREMENT PROCEDURES

| Activity 3.1. Improve the Public Procurement Portal by introducing new features |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead implementing agency: |  | Public Procurement Office |  |  |  |
| Responsible person: |  | Director of Public Procurement Office |  |  |  |
| E-mail: |  | pjovanovic@ujn.gov.rs |  |  |  |
| Phone: |  | 011/2888-712 |  |  |  |
| Other Actors Involved | Government | Human Resource Management Office |  |  |  |
|  | CSOs, private sector, working groups, multilaterals | Civil society organizations |  |  |  |
| Main objective |  | Transparency and awareness in the area of public procurement |  |  |  |
| Brief description of activity: |  | Improve the Public Procurement Portal by introducing new features: possibility to publish contracting authorities’ procurement plans, publishing procurements carried out in keeping with international procedures, the English version of the Portal, improvement of searching Decisions made by the Republic Commission for the Protection of Rights in Public Procurement Procedures, setting up of the registry of public contracts, establishment of the reporting system to the Public Procurement Office. |  |  |  |
| Relevance: (Briefly describe the way in which this commitment is relevant to further advancing OGP values –access to information, public accountability, civic participation, and technology and innovation for openness and accountability) |  | All interested parties have the access to information about the manner and scope of public spending, as well as every public procurement procedure. This is enabled by publication of public procurement notices, tender dossiers, Q&A, and other relevant information (quarterly reports on conducted procurement procedures and concluded contracts, opinions issued by the Office regarding the justification of negotiated procedures, decisions of the Republic Commission for the Protection of Rights in Public Procurement Procedures, etc.) which enhances the transparency of activities performed by budget beneficiaries. The Portal represents a mechanism for monitoring public procurement procedures which increases public accountability and facilitates detection of irregularities in a timely manner. Access to the content posted on the Portal and its download is open and free of charge, which brings about significant saving of budget funds and enhances transparency and public awareness. |  |  |  |
| Ambition: (Briefly describe the intended strategic results and how this commitment will either make government more openness or improve government through more openness) |  | Publication of all relevant documents related to public procurement procedures at one place – Public Procurement Portal and their full availability to all interested parties enables the growth of economic activity, enhances efficiency of public spending, promotes the level of services rendered to citizens, reduced the level of corruption in this area and ensures permanent keeping of documentation on each transaction performed in this manner. |  |  |  |
| Completion level: |  | Not started | Limited | Substantial | Completed |
|  |  |  |  |  | X |
| Description of the results: (Include specific activities within the reporting period (first or second year of the action plan) and, wherever possible, please indicate whether there has been evidence of members of the public using the commitment or whether the commitment has had an effect |  | The link of the Public Procurement Portal is: http://portal.ujn.gov.rs/ The number of procurement procedures published on the Portal increased considerably since its launching, significantly contributing to the transparency of the public procurements performed in Serbia. In 2013, the number of procurement procedures published on the Portal stood at 39,417, while in 2014 this number reached 59,665, and in 2015 61 602 public procurement procedures were published. |  |  |  |
| End date/Completion date: |  | 30 October 2015 |  |  |  |
| Next steps: |  | Future activities will be aimed at: improving the call centre for providing expert support to users of the Public Procurement Portal, and training of the users of the Public Procurement Portal – two times a year. |  |  |  |
| Additional information (Description on what remains to be achieved and any risks or challenges to implementing the commitment) |  |  |  |  |  |
| There are no significant risks that can affect the implementation of the activity. |  |  |  |  |  |

| Activity 3.2. Improve the Electronic Public Procurement System |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead implementing agency: |  | Public Procurement Office |  |  |  |
| Responsible person: |  | Director of Public Procurement Office |  |  |  |
| E-Mail: |  | pjovanovic@ujn.gov.rs |  |  |  |
| Phone: |  | 011/2888-712 |  |  |  |
| Other Actors Involved | Government | Human Resource Management Office Ministry of Trade, Tourism and Telecommunications Administration for Joint Services of the Republic Bodies |  |  |  |
|  | CSOs, private sector, working groups, multilaterals | Civil society organizations |  |  |  |
| Main objective |  | Transparency and awareness in the area of public procurement |  |  |  |
| Brief description of activity: |  | - Analysis of the existing legislative and institutional frameworks for the implementation of e-procurement in the RS (e-tender submission, e-auction, e-dynamic purchase system, e-catalogues...) - Analysis of technical solutions and options that are in use or under development in the EU Member States in the field of e-procurement (e-tender submission, e-auction, e-dynamic purchase system, e-catalogues ...) |  |  |  |
| Relevance: (Briefly describe the way in which this commitment is relevant to further advancing OGP values –access to information, public accountability, civic participation, and technology and innovation for openness and accountability) |  | Greater number of electronic procurement procedures (Е-procurement), in addition to full availability of information about public spending for procurement of goods, services and works in the free market, significantly facilitates the timely detection of irregularities and increases the accountability level of contracting authorities. Recommendations arising from implemented activities (commitments) promote the usage of modern technologies and innovation in order to enable efficient dissemination of information, increase the involvement of market participants and encourage cooperation with all interested parties. |  |  |  |
| Ambition: (Briefly describe the intended strategic results and how this commitment will either make government more openness or improve government through more openness) |  | Ultimate goal is the establishment and functioning of a single, comprehensive platform for electronic public procurements that would include all the above-stated key functionalities (е-publication, e-communication, and e-tender submission, e-catalogue, e-auction and e-dynamic purchase system). E-procurement platform will enhance competition, reduce potential inappropriate spending of public funds and enable a more efficient public resources management. |  |  |  |
| Completion level: |  | Not started | Limited | Substantial | Completed |
|  |  |  |  |  | X |
| Description of the results: (Include specific activities within the reporting period (first or second year of the action plan) and, wherever possible, please indicate whether there has been evidence of members of the public using the commitment or whether the commitment has had an effect |  | The said activities represent the initial phase in the introduction of certain e-procurement techniques foreseen by EU directives which need to be presented to contracting authorities and tenderers, such as: е-tender submission, e-auctions, e-dynamic purchase system, and e-catalogues). Both analyses are prepared and adopted by the Public Procurement Office. Analyses are available at the following link: http://www.ujn.gov.rs/ci/strategija/realizacija-akcionog-plana/analize.html |  |  |  |
| End date/Completion date: |  | 28 August 2015 |  |  |  |
| Next steps: |  | Future activities will predominantly be focused on the development of system for electronic submission of tenders. |  |  |  |
| Additional information (Description on what remains to be achieved and any risks or challenges to implementing the commitment) |  |  |  |  |  |

COMMITMENT 4. IMPROVE THE PROCESS OF TRANSPARENT FINANCING OF CIVIL SOCIETY ORGANIZATIONS

| Activity 4.1. Prepare annual summary reports on the expenditure of funds provided and granted to associations and other civil society organizations from the public funds of the Republic of Serbia in 2013 and 2014 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead implementing agency: |  | Office for Cooperation with Civil Society and MPALS |  |  |  |
| Responsible person: |  | Milena Banovic, Head of Department for Planning and Creating the Enabling Environment for Civil Society Development, has been temporarily performing the duties of the Office Director according to a Government Conclusion of the Republic of Serbia 24, No. 119-9248/2015 as of 28 August 2015 |  |  |  |
| E-mail: |  | milena.banovic@civilnodrustvo.gov.rs |  |  |  |
| Phone: |  | 011/311 3895 |  |  |  |
| Other Actors Involved | Government |  |  |  |  |
|  | CSOs, private sector, working groups, multilaterals | Civil society organizations |  |  |  |
| Main objective |  | More effective and purposeful spending of budget funds for achievement of goals stipulated by strategic and national documents |  |  |  |
| Brief description of activity: |  | Preparation of annual summary reports on the expenditure of funds to support programs and projects activities, provided and granted to associations and other civil society organizations from the public funds of the Republic of Serbia in 2013, and 2014 - 2013 Annual summary expenditure report prepared; -2013 Annual summary expenditure report communicated to the Government for consideration and adoption; - 2013 Annual summary expenditure report adopted, presented to the public and public administration institutions, and published on the official website of the Office for Cooperation with Civil Society; ------ - 2014 Annual summary expenditure report prepared ; - 2014 Annual summary expenditure report communicated to the Government for consideration and adoption; - 2014 Annual summary expenditure report adopted, presented to the public and public administration institutions, and published on the official website of the Office for Cooperation with Civil Society |  |  |  |
| Relevance: (Briefly describe the way in which this commitment is relevant to further advancing OGP values –access to information, public accountability, civic participation, and technology and innovation for openness and accountability) |  | Annual summary report on the spending of funds to support programs and projects activities, provided and granted to associations and other civil society organizations from the public funds of the Republic of Serbia (hereinafter referred to as: Report) provides the public with the information about the funds planned and allocated for the CSOs activities as well as a detailed description of the procedures for the allocation of funds, manner of monitoring the results achieved by the supported programmes and projects, data about all supported programmes and projects, areas of activities receiving support, end beneficiaries, territorial distribution of the supported programmes and projects, and a list of associations and other CSOs that received the support. In this manner, citizens are given the information about the allocation of tax payers' funds, and the state administration authorities are provided with the necessary data for the future planning of support, improvement of allocation procedures, monitoring of results achieved by the supported projects, as well as the monitoring of the CSO participation in the implementation of public policies and achievement of set goals. |  |  |  |
| Ambition: (Briefly describe the intended strategic results and how this commitment will either make government more openness or improve government through more openness) |  | Introduction of the regular annual reporting on the allocation of funds to civil society organizations (CSOs), allocation procedures and monitoring of implementation of supported programmes and projects improves the fiscal transparency, raises the credibility of public institutions and promotes the public confidence in the work performed by institutions. Continuous reporting on the support provided to CSOs builds a system of regular reporting on the funds, procedures and results of the support granted to CSOs, and represents a credible source of information for state authorities and the public that will enable improvement of legislation, procedures and modalities of support to CSOs. Publication and promotion of the Report ensures a greater level of public confidence and strengthens the partnership between the public administration and civil society organizations, as well as the sustainability of the civil sector. |  |  |  |
| Completion level: |  | Not started | Limited | Substantial | Completed |
|  |  |  |  | Х |  |
| Description of the results: (Include specific activities within the reporting period (first or second year of the action plan) and, wherever possible, please indicate whether there has been evidence of members of the public using the commitment or whether the commitment has had an effect |  | Report contains the analysis of data collected from the authorities at the central government, autonomous province and local government level that provided financial and non-financial support to associations and other civil society organizations in 2013. The data was collected through an e-application/Questionnaire on the spending of budget funds allocated to associations and other civil society organizations. The received information about the central government level was processes separately from the information regarding the province and local government level. Report on the spending of funds to support programs and projects activities, provided and granted to associations and other civil society organizations from the RS budget in 2013, i.e. institutions on the national level, was adopted by the Government Conclusion 05 number 401-10677/2015. Considering the scope and content of the information contained in this Report, it represents a significant source of data for the monitoring of allocation of public funds to civil society organizations and relevant practices. Data provided in the Report served as a basis for the development of commitments and activities in the Draft National Strategy for Creating the Enabling Environment for Civil Society Development, particularly with respect to the CSO sustainability. In addition, information contained in the Report is also a valuable resource to civil society organizations for the monitoring of public policies, and especially the support granted to them. So far, the information presented in the Report was published by many media with the aim to inform the public about the amount of funds allocated to civil society organizations. |  |  |  |
| End date/Completion date: |  | The 2013 Expenditure report was prepared as planned, but it was adopted by the Government at the beginning of October 2015. Presentation of findings of the Annual summary report on the spending of funds to support programs and projects activities, provided and granted to associations and other civil society organizations from the RS budget in 2013 was organized at the beginning of November 2015. Preparation of the Annual summary report on the spending of funds to support programs and projects activities, provided and granted to associations and other civil society organizations from the RS budget in 2014 is underway and its adoption is planned to be in 4 Quarter 2016. |  |  |  |
| Next steps: |  | Report on the spending of funds to support programs and projects activities, provided and granted to associations and other civil society organizations from the RS budget in 2014 is currently in process of harmonization with the opinion of the Ministry of Finance. Its adoption is expected by the end of 2016. |  |  |  |
| Additional information (Description on what remains to be achieved and any risks or challenges to implementing the commitment) |  |  |  |  |  |
| Due to HR-related changes in the Office for Cooperation with Civil Society and the fact that there is no person authorised to sign on behalf of the Office, adoption of the 2013 Expenditure report was delayed. Acting director of the Office for Cooperation with Civil Society has been appointed by the RS Government Decision 24 number: 119-1521/2016 dated 12 February 2016. The Office will continue promoting the importance of reporting on the amounts and procedures regarding the allocation of public funds to civil society organizations, as well as legislation and good practices of transparent financing of civil society organization from the budget. |  |  |  |  |  |

| Activity 4.2. Introduce the obligation to publish public competition, evaluation and ranking lists of programs, decisions on the selection of programs, etc, on the e-Government Portal, as well as extension of the deadline for publication of ranking and evaluation lists to at least 5 days, in the process of allocation of budgetary resources for financing programs of public interest realized by associations. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead implementing agency: |  | Office for Cooperation with Civil Society and MPALS |  |  |  |
| Responsible person: |  | Milena Banovic, Head of Department for Planning and Creating the Enabling Environment for Civil Society Development, has been temporarily performing the duties of the Office Director according to a Government Conclusion of the Republic of Serbia 24, No. 119-9248/2015 as of 28 August 2015 |  |  |  |
| E-mail: |  | milena.banovic@civilnodrustvo.gov.rs |  |  |  |
| Phone: |  | 011/311 3895 |  |  |  |
| Other Actors Involved | Government |  |  |  |  |
|  | CSOs, private sector, working groups, multilaterals |  |  |  |  |
| Main objective |  | Improve transparency of public competition for the allocation of budget funds to associations and other civil society organizations. |  |  |  |
| Brief description of activity: |  | Introducing obligation to publish public competition, evaluation and ranking lists of programs, decisions on the selection of programs etc., on the e-Government Portal, as well as extension of the deadline for publication of ranking and evaluation lists to at least 5 days, in the process of allocation of budgetary funds for financing programs of public interest realized by associations. - Preparation of the Draft Regulation on Amendments to the Regulation on funds for stimulating programs or shortage of funds for financing programs of public interest realized by associations - Adopting the Regulation on Amendments to the Regulation on funds for stimulating programs or shortage of funds for financing programs of public interest realized by associations |  |  |  |
| Relevance: (Briefly describe the way in which this commitment is relevant to further advancing OGP values –access to information, public accountability, civic participation, and technology and innovation for openness and accountability) |  | Proposed amendments to the Regulation on funds for inciting programs or shortage of funds for financing programs of public interest realized by associations, should contribute to better transparency of public competition publication, decision-making and reporting on the allocation and usage of budgetary resources for inciting programs of public interest and better accountability of the state administration, the autonomous province and local self-government units, but also civil society organizations – budget beneficiaries. |  |  |  |
| Ambition: (Briefly describe the intended strategic results and how this commitment will either make government more openness or improve government through more openness) |  | The aim of the amendments to the Regulation on funds for inciting programs or shortage of funds for financing programs of public interest realized by associations is to introduce the obligation of publishing public competition, evaluation and ranking lists of programs submitted, decisions on the selection of programs both on the website of the competent authority and on the e-Government Portal. It is also envisaged to extend the deadline for civil society organization to submit complaints regarding the published ranking and evaluation lists to at least 5 days from their publication. Adoption of these amendments will enable a more transparent procedure of allocation of funds for inciting programs of public interest realized by civil society organizations. |  |  |  |
| Completion level: |  | Not started | Limited | Substantial | Completed |
|  |  |  |  |  | Х |
| Description of the results: (Include specific activities within the reporting period (first or second year of the action plan) and, wherever possible, please indicate whether there has been evidence of members of the public using the commitment or whether the commitment has had an effect |  | As the first step towards the implementation of this activity, “Preparation of the Draft Regulation on Amendments to the Regulation on funds for inciting programs or shortage of funds for financing programs of public interest realized by associations“, the Office for Cooperation with Civil Society launched the initiative for amendments in August 2015 as envisaged in the Action Plan. The Ministry of Public Administration and Local Self-Government prepared the Draft Regulation and delivered it to the competent authorities for opinion. |  |  |  |
| End date/Completion date: |  | The Serbian Government, at the initiative of the Office for Cooperation with Civil Society, and at the proposal from the Ministry of Public Administration and Local Self-Government, adopted the Regulation on 13 November 2015. |  |  |  |
| Next steps: |  | The following steps will be to monitor the implementation of the said amendments to the Regulation in practice and to develop Instructions on the manner of harmonization of internal bylaws on financing with the Regulation on funds for inciting programs or shortage of funds for financing programs of public interest realized by associations, in keeping with the activities specified in the Action Plan implementing the Strategy for creating the Enabling Environment for Civil Society Development in the republic of Serbia for the period 2016-2020. |  |  |  |
| Additional information (Description on what remains to be achieved and any risks or challenges to implementing the commitment) |  |  |  |  |  |
| The Office for Cooperation with Civil Society believes that there are no risks and challenges to implementing this activity. |  |  |  |  |  |

| Activity 4.3. Strengthen the capacities of state administration authorities in the areas of cooperation and transparent funding of civil society organizations from budget funds |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead implementing agency: |  | Office for Cooperation with Civil Society and MPALS |  |  |  |
| Responsible person: |  | Milena Banovic, Head of the Department for Planning and Creating Enabling Environment for Civil Society Development, has been temporarily performing the duties of the Office Director according to a Government Conclusion of the Republic of Serbia 24, No. 119-9248/2015 as of 28 August 2015 |  |  |  |
| E-mail: |  | milena.banovic@civilnodrustvo.gov.rs |  |  |  |
| Phone: |  | 011/311 3895 |  |  |  |
| Other Actors Involved | Government |  |  |  |  |
|  | CSOs, private sector, working groups, multilaterals |  |  |  |  |
| Main objective |  | Improve cooperation between state administration authorities and civil society organization, as well as more efficient conducting of public competition and other procedures for allocating funds and more purposeful spending of budget funds for achievement of goals stipulated by strategic and national documents |  |  |  |
| Brief description of activity: |  | - Conducting training courses for civil servants on the implementation of the Guidelines for the inclusion of civil society organizations in the regulation adoption process and transparent funding of civil society organizations from the budget funds. - Development of the Second Revised Edition of the Guide through transparent funding of civil society organizations from the budgets of local self-governments - preparation, design and printing, distributing Guide to all local self-government units |  |  |  |
| Relevance: (Briefly describe the way in which this commitment is relevant to further advancing OGP values –access to information, public accountability, civic participation, and technology and innovation for openness and accountability) |  | Strengthening of the public administration capacities in the area of cooperation with civil society organizations and ensuring transparent funding of CSOs from the budget funds sets the environment for the inclusion of CSOs in the process of policy making, adoption and implementation, as one of the core OGP values. |  |  |  |
| Ambition: (Briefly describe the intended strategic results and how this commitment will either make government more openness or improve government through more openness) |  | Strengthening of the public administration capacities and promoting the importance of cooperation with CSOs should lead to the establishment of clear mechanisms and standards for cooperation with the civil sector which, apart from its main function of civic participation in developing and implementing regulations and public policies, should also enable increased efficiency of authorities, cost reduction and optimisation of work in public institutions accompanied by general capacity building, and promotion of knowledge and skills of the public administration employees. |  |  |  |
| Completion level: |  | Not started | Limited | Substantial | Completed |
|  |  |  |  |  | Х |
| Description of the results: (Include specific activities within the reporting period (first or second year of the action plan) and, wherever possible, please indicate whether there has been evidence of members of the public using the commitment or whether the commitment has had an effect |  | 1. With respect to the implementation of the activity Strengthening the capacities of state administration authorities in the areas of cooperation and transparent funding of civil society organizations from the budget funds, the Office participated in the implementation of two training courses organized by the Human Resource Management Office during 2014 which dealt with the topic “Coordination and cooperation during in the law making process”. During the said training courses, the representative of the Office presented to the participants the scope of work of the Office and the document Guidelines for the inclusion of civil society organizations in the processes of adopting regulations whose aim is to promote the cooperation between the public institutions and CSOs, and involvement of CSOs in the process of preparation, adoption and implementation of regulations that govern the issues of public interest. The objective of this training was to inform the participants about the skills and techniques for conducting efficient and effective intra-ministerial and inter-ministerial consultative meetings and public debates, as models for involving interested public participants and civil society organizations. Following these training courses, the Office is recognised as a consultative body for implementing activities regarding the involvement and consultation with CSOs, and especially in regards to public competitions for allocation of funds to CSOs. Report on organised training courses is available on the Office website: http://civilnodrustvo.gov.rs/vest.37.html?newsId=651 2. Development of the Second Revised Edition of the Guide through transparent funding of civil society organizations from the budgets of local self-governments - preparation, design and printing, distributing Guide to all local self-government units Guide for transparent funding of associations and other civil society organizations from the local self-government budget was developed in 2013 by the Office for Cooperation with Civil Society and TASCO (Technical Assistance for Civil Society Organisations). It significantly contributed to the solving of practical issues regarding transparent funding of CSOs, and also served as the assistance for the improvement of CSO funding procedures and preparation of municipal Rulebooks on funding of associations and other CSOs, as well as other internal acts regulating the procedure of funding CSOs. Cooperation with local self-governments, as well as the evaluation of results of the civil servants training courses revealed that a great number of institutions believe that the cooperation with CSOs is enabled through funding of their activities. Given the importance of cooperation and funding of CSOs at the local level, because the local organisations most directly affect the quality of living for the local communities. The preparation of the second edition of the Guide for transparent funding of associations and other civil society organizations from the local self-government budget was not implemented due to the lack of funds for this activity implementation. |  |  |  |
| End date/Completion date: |  | Activity 1. : 2 and 4 Quarter 2016 Activity 2. : 1 Quarter 2016 |  |  |  |
| Next steps: |  | In keeping with the activities specified in the National Strategy for Creating the Enabling Environment for Civil Society Development in the Republic of Serbia for 2016-2020, it is envisaged to organise activities aimed at capacity building of public administration and civil society organizations for greater participation of interested public in the process of preparation of laws and other public policy instruments, as well as providing information about the manner and procedure for cooperation between state administration authorities and civil society organizations. Implementation of these activities will begin following the adoption of this strategic document. |  |  |  |
| Additional information (Description on what remains to be achieved and any risks or challenges to implementing the commitment) |  |  |  |  |  |
| In keeping with the activities specified in the National Strategy for Creating the Enabling Environment for Civil Society Development in the Republic of Serbia for 2016-2020, in 2017 the Office plans to continue with training courses for civil servants on the manner and procedure for cooperation and inclusion of civil society organization in the process of preparation, implementation and monitoring of regulations and policy documents, as well as on more transparent funding of civil society organizations from the budget funds. Also, Office activities regarding transparent funding of civil society organizations form the budget funds include development of the second revised edition of the Guide through transparent funding of civil society organizations from the budgets of local self-governments, which is equally informative for state administration authorities. Also, it is proposed to adopt a bylaw which would further regulate the monitoring of implementation and evaluation of supported programs and projects of associations and other civil society organizations. |  |  |  |  |  |

COMMITMENT 5. EXTEND AND CLARIFY RESPONSIBILITIES OF THE ANTI-CORRUPTION AGENCY

| Activity 5.1. Improve the provisions of the Law on Anti-Corruption Agency |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead implementing agency: |  | Ministry of Justice |  |  |  |
| Responsible person: |  | State Secretary Radomir Ilic |  |  |  |
| E-mail: |  | radomir.ilic@mpravde.gov.rs |  |  |  |
| Phone: |  | +381113622361 |  |  |  |
| Other Actors Involved | Government |  |  |  |  |
|  | CSOs, private sector, working groups, multilaterals |  |  |  |  |
| Main objective |  | More efficient fight against corruption |  |  |  |
| Brief description of activity: |  | Improve the provisions of the Law on the Anti-Corruption Agency so as to clearly distinguish and regulate concepts of accumulation of offices (to prevent exercising multiple public functions which are interconnected in a conflict of interest) and conflict of interest (to eliminate private interest in exercising public powers), and to expand the group of related persons for whom a public official is required to submit a declaration on assets and income, as well as to authorize the Agency by law, to carry out extraordinary control of assets, and to act upon anonymous notifications. |  |  |  |
| Relevance: (Briefly describe the way in which this commitment is relevant to further advancing OGP values –access to information, public accountability, civic participation, and technology and innovation for openness and accountability) |  | This activity is extremely important for the strengthening of preventive anti-corruption mechanisms. Adoption of the new Law on the Anti-Corruption Agency introducing more advanced solutions and increasing the powers of this independent state authority will directly contribute to the OGP values, and primarily to the public accountability. |  |  |  |
| Ambition: (Briefly describe the intended strategic results and how this commitment will either make government more openness or improve government through more openness) |  | Following the adoption of the new law, the Anti-Corruption Agency will have at its disposal adequate mechanisms necessary for the stronger prevention of corruption. The reform of the repression system, launched by the Ministry of Justice, cannot be properly performed without redefining the prevention sector. The aim is to impose on government officials, and perhaps to an extended group of persons, obligations to report and publish all relevant data, and not only with respect to revenues, accompanied by more severe sanctions, and with the ultimate objective to make all relevant information available to public in a transparent manner. |  |  |  |
| Completion level: |  | Not started | Limited | Substantial | Completed |
|  |  |  |  | Х |  |
| Description of the results: (Include specific activities within the reporting period (first or second year of the action plan) and, wherever possible, please indicate whether there has been evidence of members of the public using the commitment or whether the commitment has had an effect |  | Early 2015, the Minister of Justice signed a Decision to establish a Working group mandated to draft the Law on Anti-Corruption Agency, and the Decision is published on the website of the Ministry of Justice. During 2015 and 2016, the Working group intensively worked on the draft text of the Law on Anti-Corruption Agency, and its adoption is expected in the coming period. The public is regularly informed about progress on the draft law. |  |  |  |
| End date/Completion date: |  | 1 Quarter 2017 |  |  |  |
| Next steps: |  | The Working group will continue its activities. When the Working group finalizes its activities, the draft Law will be subject to public debate and communicated to the European Commission for opinion. |  |  |  |
| Additional information (Description on what remains to be achieved and any risks or challenges to implementing the commitment) |  |  |  |  |  |

COMMITMENT 6. ESTABLISH EFFICIENT AND EFFECTIVE WHISTLEBLOWER PROTECTION SYSTEM

| Activity 6.1. Conduct professional training on procedures and importance of whistleblower protection for prevention of corruption |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead implementing agency: |  | Ministry of Justice |  |  |  |
| Responsible person: |  | State Secretary Radomir Ilić |  |  |  |
| E-mail: |  | radomir.ilic@mpravde.gov.rs |  |  |  |
| Phone: |  | +381113622361 |  |  |  |
| Other Actors Involved | Government | Anti-corruption agency Human Resource Management Office |  |  |  |
|  | CSOs, private sector, working groups, multilaterals | Civil society organizations |  |  |  |
| Main objective |  | More efficient fight against corruption and whistleblower protection |  |  |  |
| Brief description of activity: |  | Conducting professional training of civil servants in the state administration authorities, and employees in local self-government units, on procedures and importance of protection of whistleblowers, as prevention of corruption - developing a professional training program for civil servants and local self-government units employees; - conducting the professional training of civil servants and local self-government units employees. |  |  |  |
| Relevance: (Briefly describe the way in which this commitment is relevant to further advancing OGP values –access to information, public accountability, civic participation, and technology and innovation for openness and accountability) |  | The necessity for legal regulation of the protection of persons reporting suspected acts of corruption stems from the rule of law as the fundamental principle of the Constitution which is, inter alia, achieved through constitutional assurance of human and minority rights and liberties. This implies that, in the country founded on the rule of law principle there is no room for corruptive actions and the most effective tool for combating any form of illegal activity is the protection of persons pointing out to such activities. Widely spread and, unfortunately, deeply rooted corruption in our transitional society fully justifies the need for a single legal solution that will ensure protection of whistleblowers and this protection will in turn encourage the public to disclose examples of corruptive and other illegal activity. All the above is relevant for the said OGP values and their progress. |  |  |  |
| Ambition: (Briefly describe the intended strategic results and how this commitment will either make government more openness or improve government through more openness) |  | The above described disclosure of corruptive behaviour will lead to reduction of corruption and serve as a clear preventive signal. |  |  |  |
| Completion level: |  | Not started | Limited | Substantial | Completed |
|  |  |  |  | Х |  |
| Description of the results: (Include specific activities within the reporting period (first or second year of the action plan) and, wherever possible, please indicate whether there has been evidence of members of the public using the commitment or whether the commitment has had an effect |  | Office for Human Resource Management started the training of civil servants on the implementation of the new Law on Whistleblower Protection. On the other hand, training courses were organized for labor inspectors, which were supported by the Council of Europe. In addition, NGO sector also organizes seminars and training courses on this topic for the local level (e.g. training courses held by the Centre for Democratic Activities). In the six-month period total of 853 judges were trained, Guidelines for the implementation of the Law on Whistleblower Protection are prepared, and a media campaign is launched with the aim to inform the public about the novelties introduced in the RS legal framework. Program of the Training course “Whistleblower protection” was developed during 2014 in cooperation with representative of the Belgrade Misdemeanor Court, who was a member of the working group mandated to develop the Law on Whistleblower Protection, and is part of the General Continuing Professional Development Program (program area Fight against Corruption), which was adopted on 31 March 2015. The Ministry of Public Administration and Local Self-Government adopted Rulebook on establishing General Professional Development Program for civil servants from state administration authorities and Government services for 2015, and in keeping with the adopted Program, conducted training titled “Whistleblower Protection” on the following three days: 25 August 2015, 13 November 2015 and 10 December 2015. Total number of participants who completed this training was 62, and the target group were all civil servants. In addition, at the training course held in January 2015, about 600 judges from Belgrade, Nis, Novi Sad and Kragujevac obtained a certificate and passed the training of the Judicial Academy. |  |  |  |
| End date/Completion date: |  | In progress |  |  |  |
| Next steps: |  | Continue the launched training courses. |  |  |  |
| Additional information (Description on what remains to be achieved and any risks or challenges to implementing the commitment) |  |  |  |  |  |

| Activity 6.2. Conduct campaign for raising awareness of citizens about rights and protection of whistleblowers; |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead implementing agency: |  | Ministry of Justice |  |  |  |
| Responsible person: |  | State Secretary Radomir Ilic |  |  |  |
| E-mail: |  | radomir.ilic@mpravde.gov.rs |  |  |  |
| Phone: |  | +381113622361 |  |  |  |
| Other Actors Involved | Government | Anti-corruption agency Human Resources Management Office |  |  |  |
|  | CSOs, private sector, working groups, multilaterals | Civil society organizations |  |  |  |
| Main objective |  | More efficient fight against corruption and whistleblower protection |  |  |  |
| Brief description of activity: |  | Conducting campaign for raising awareness of citizens about rights and protection of whistleblowers; - preparation of the campaign program; - adoption of the campaign program; - implementation of the campaign program. |  |  |  |
| Relevance: (Briefly describe the way in which this commitment is relevant to further advancing OGP values –access to information, public accountability, civic participation, and technology and innovation for openness and accountability) |  | Public campaign and providing information to citizens is the crucial activity that needs to be implemented. With the support of the Ministry of Justice, USAID is conducting a media campaign involving well-known characters from the popular show “Public service” (“Državni posao”). The commercial is broadcasted on all television stations with national coverage. |  |  |  |
| Ambition: (Briefly describe the intended strategic results and how this commitment will either make government more openness or improve government through more openness) |  | Law on Whistleblower Protection provides a new system of court protection to whistleblowers that are willing to report and disclose the cases of abusing the public office. Dissemination of information about this law among employers, employees and general public is an important step to bring the public and government closer in their joint fight against corruption and abuse of public office. |  |  |  |
| Completion level: |  | Not started | Limited | Substantial | Completed |
|  |  |  |  | Х |  |
| Description of the results: (Include specific activities within the reporting period (first or second year of the action plan) and, wherever possible, please indicate whether there has been evidence of members of the public using the commitment or whether the commitment has had an effect |  | The Law came in force on 5 June 2015. This date marked the beginning of the campaign titled “Whistleblowers are Stronger Now”. The Ministry of Justice, with the support of USAID Judicial Reform and Government Accountability Project (JRGA), led the media and awareness-raising campaign. According to JRGA, the campaign lasted for a month and resulted in a total of 120 news related reports and more than 300 promotional national-level television broadcasts on major media outlets, such as RTS, B92 and RTV1. A promotional microsite www.uzbunjivaci.rs was developed as part of the project. Promotional material was distributed on city buses in three regional centers of Serbia: Belgrade, Novi Sad and Nis. |  |  |  |
| End date/Completion date: |  | In progress |  |  |  |
| Next steps: |  | Continue the campaign. |  |  |  |
| Additional information (Description on what remains to be achieved and any risks or challenges to implementing the commitment) |  |  |  |  |  |

COMMITMENT 7. STRENGTHEN THE SYSTEMIC FUNCTION OF CONTROL IN PUBLIC ADMINISTRATION

| Активност 7.1. Унапређење законодавног оквира којим се уређује инспекцијски надзор |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead implementing agency: |  | Ministry of Public Administration and Local Self-Government |  |  |  |
| Responsible person: |  | Zeljko Ozegovic, State Secretary |  |  |  |
| E-mail: |  | drzavni.sekretar@mduls.gov.rs |  |  |  |
| Phone: |  | 011/3613-654 |  |  |  |
| Other Actors Involved | Government | Representatives of authorities performing inspection |  |  |  |
|  | CSOs, private sector, working groups, multilaterals | - USAID Business Enabling Project (USAID BEP) which supported the Ministry of Public Administration and Local Self-Government during the preparation of the Law. The same support is provided during the enforcement of the Law. - Transparency Serbia, a non-governmental organization that followed the Law preparation process |  |  |  |
| Main objective |  | More efficient fight against corruption, better transparency and accountability. |  |  |  |
| Brief description of activity: |  | Improving the legal framework regulating inspection oversight. - Communicating Draft Law to the Government for consideration and formulation of the Bill. |  |  |  |
| Relevance: (Briefly describe the way in which this commitment is relevant to further advancing OGP values –access to information, public accountability, civic participation, and technology and innovation for openness and accountability) |  | The Law was adopted with the aim to improve the framework regulating inspection oversight. It will regulate this area in a single and comprehensive manner. Stipulating clear rules for the oversight procedure, standardization of procedures, types and forms of inspection oversight and defining powers of inspectors, as well as rights and obligations of subjects of oversight will contribute to a more efficient combat against corruption and growing public confidence in the Government. In addition, the Law provides for the setting up of an IT system in order to ensure a more efficient exchange of information and electronic document, as well as risk assessment in the inspection oversight, which is a basic precondition for the improved transparency in this area. |  |  |  |
| Ambition: (Briefly describe the intended strategic results and how this commitment will either make government more openness or improve government through more openness) |  | A comprehensive reform of the inspection oversight that includes a better coordination and harmonisation of the oversight performed by different inspections, standardisation and unification of the inspection oversight procedure and practice, as well as providing support to sustainable business operation and economic development in accordance with legislation will contribute to the reduction of corruption and grey economy, and improvement of transparency and better public confidence. |  |  |  |
| Completion level: |  | Not started | Limited | Substantial | Completed |
|  |  |  |  |  | Х |
| Description of the results: (Include specific activities within the reporting period (first or second year of the action plan) and, wherever possible, please indicate whether there has been evidence of members of the public using the commitment or whether the commitment has had an effect) |  | The Law on Inspection Oversight came into force on 30 April 2015, and its application will begin on 30 April 2016, except for the provisions that regulate the actions of the inspection towards non-registered subjects whose implementation began on 30 July 2015. Implementation of these provisions is aimed at curbing grey economy. In this manner, legality and security of business operations is increased. In accordance with the Law, a Coordination Commission was set up in order to ensure a more comprehensive and effective oversight and to avoid overlapping and unnecessary oversight. A preliminary version of the Commission’s website has been launched and it will contain information about all authorities performing inspection oversight, and particularly the information about their scope of work, addresses, telephone numbers and e-mails, as well as their management. (http://www.inspektor.gov.rs/#/). The website contains video content with the held trainings, professional methodological rules for the enforcement of the law, a guide book for law enforcement, inspection checklists for risk assessment. The Coordination Commission held so far seven sessions, and within the Committee, the working groups and expert teams (7 wg and 2 et) were established, of mixed composition, both in terms of inspection, and in terms of other subjects, from industry and non-governmental sector. So far, 5 by-laws were adopted concerning the Law on Inspection Oversight, more precisely two Regulations adopted by the RS Government (Regulation on the form and manner of record keeping for the inspection oversight, and Regulation on common elements of risk assessment in the inspection oversight) and three Rulebooks passed by the Minister of Public Administration and Local Self-Government (Rulebook on the general form for the inspection oversight minutes, Rulebook on the program and manner of conducting exams for inspectors, and Rulebook on the features of the official identification of inspectors). There were trainings on the Law of the inspection and its implementation and reform of the inspection control, to improve the knowledge and skills of inspectors, for 300 inspectors at the central levele and around 1,200 inspectors at the local level. Transparency Serbia, a non-governmental organisation, monitored the entire process of the Law preparation and stated that its preparation provides good guidance for legislative process. |  |  |  |
| End date/Completion date: |  | The National Assembly passed the Law on Inspection Oversight on 15 April 2015 |  |  |  |
| Next steps: |  | Continue dissemination of information to economy, citizens, expert and general public about the Law, its implementation and reform of the inspection oversight, including continuous presentation of novelties introduced in the Law in sessions that will be organised in cooperation with regional chambers of commerce and administrative counties, as well as other professional and expert associations, and publication of the Guide for the application of the Law. Set up a single IT system for inspections (e-Inspector) which is performed in phases and is planned to be completed by 30 June 2018. The first activity in this respect is to analyse the business processes of all inspections at the central government level. It is also envisaged to provide technical and communication infrastructure, equipment and conditions for the work of certain inspections. Currently, the condition of equipment used by inspections is being assessed. Set up a training system, continuing improvement of knowledge and skills and professional advancement for inspectors, which also includes training of inspectors about the Law on Inspection Oversight and its implementation, as well as about the reform of the inspection oversight (Training of Trainers - ToT). The Ministry implements the said project in cooperation with USAID Business Enabling Project and Partners for Democratic Changes Serbia. Implementation will be launched in November 2015 and within a 10-month program total of 220 inspectors –future trainers will be trained about the new concepts in the Law on Inspection Oversight and the so called soft skills necessary for the job of the inspector. Following the training, the future trainers (instructors) will pass on their knowledge to colleagues and collaborators. |  |  |  |
| Additional information (Description on what remains to be achieved and any risks or challenges to implementing the commitment) |  |  |  |  |  |

COMMITMENT 8. IMPROVE E-GOVERNMENT PORTAL

| Activity 8.1. Raise awareness and knowledge regarding the operation and use of eGovernment portal |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead implementing agency: |  | Directorate for eGovernment |  |  |  |
| Responsible person: |  | Dusan Stojanovic |  |  |  |
| E-mail: |  | dusan.stojanovic@deu.gov.rs |  |  |  |
| Phone: |  | + 381 11 334 18 85 |  |  |  |
| Other Actors Involved | Government |  |  |  |  |
|  | CSOs, private sector, working groups, multilaterals |  |  |  |  |
| Main objective |  | A higher level of use of the Portal and provision of services, which will improve transparency and civic participation |  |  |  |
| Brief description of activity: |  | Raising awareness and knowledge regarding the operation and use of eGovernment portal: - Organizing training courses for all categories of Portal users (processors, persons which generate services, users from technical inspection, driving schools that use the system, appointed individuals from public authorities that set public hearings, etc ...). - Training of civil servants on e-government and e-Government portal. - Implementation of promotional activities and campaigns regarding the eGovernment Portal. |  |  |  |
| Relevance: (Briefly describe the way in which this commitment is relevant to further advancing OGP values –access to information, public accountability, civic participation, and technology and innovation for openness and accountability) |  | In relation to access to information, eGovernment Portal is recognised as a focal point for accessing electronic government services. Over 100 state administration authorities and local self-government units publicise their services on the Portal. Each service contains information about the method and place of service provision, most of them include submission forms, over 40% of services offer the possibility of electronic submission of completed forms and electronic payment of fees, if any, which is an electronic innovation. Public accountability is assured through decentralised method of publicising services given that each institution is responsible for its services in terms of accuracy of information regarding procedures, legal basis and fee amount. The Portal facilitates the participation of citizens and enables them to provide feedback concerning the quality of services, to file complaints or rank provided service using stars (1-5 stars) |  |  |  |
| Ambition: (Briefly describe the intended strategic results and how this commitment will either make government more openness or improve government through more openness) |  | E-Government Portal is continuously upgraded with the introduction of new services. The goal is to introduce payment with cards. It is also planned to continue promoting the sub-model for e-participation which contains draft laws and strategies that require stronger civic participation in public debate. The authorities have the responsibility to electronically publish all draft laws of public interest. |  |  |  |
| Completion level: |  | Not started | Limited | Substantial | Completed |
|  |  |  |  | Х |  |
| Description of the results: (Include specific activities within the reporting period (first or second year of the action plan) and, wherever possible, please indicate whether there has been evidence of members of the public using the commitment or whether the commitment has had an effect |  | The Directorate organises continuing training for all Portal users – civil servants responsible for publicising services and providing accurate relevant information. http://www.euprava.gov.rs/vesti/208/obuka zaposlenih u opstini zrenjanin za rad na portalu euprava.html. During the reporting period over 20 training courses were held and approximately 100 employees were trained, most of them coming from the City of Belgrade administration which published over 104 services on the Portal. Promotion of the Portal is currently performed through public appearance, issued notifications and news, as well as video material that contains instructions for working with certain Portal modules, as well as examples and good practice cases, such as the contract with Agency for Medicine. http://www.euprava.gov.rs/vesti/212/saradnja_Deu_Agencijezalekove.html Considering the fact that, apart from formal training courses planned in advance, the practice is to conduct training courses for all relevant users when a new service is implemented, the completion level can be assesses as substantial. |  |  |  |
| End date/completion date: |  | Continuing |  |  |  |
| Next steps: |  | It is planned to introduce new services for maternity care and social grants related to child and parent allowances within the Good Government project. Services publicised will be accompanied by additional information and promotion of responsible government, as well as the possibility for participation of citizens and all interested parties. New technological services are innovations that enable integration and data exchange between authorities, with improved and simpler solutions. |  |  |  |
| Additional information (Description on what remains to be achieved and any risks or challenges to implementing the commitment) |  |  |  |  |  |
| Portal users will be numerous institutions of the public administration such as hospitals, preschool institutions, etc. It is necessary to train all participants and provide them with constant technical support. Directorate has well-trained, although limited resources for such support. |  |  |  |  |  |

| Activity 8.2. Improve eGovernment Portal to enable the use by mobile phones |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead implementing agency: |  | Directorate for eGovernment |  |  |  |
| Responsible person: |  | Dusan Stojanovic |  |  |  |
| E-mail: |  | dusan.stojanovic@deu.gov.rs |  |  |  |
| Phone: |  | + 381 11 334 18 85 |  |  |  |
| Other Actors Involved | Government |  |  |  |  |
|  | CSOs, private sector, working groups, multilaterals |  |  |  |  |
| Main objective |  | A higher level of use of the Portal and provision of services, which will improve transparency and civic participation |  |  |  |
| Brief description of activity: |  | Improving eGovernment Portal to enable the use by mobile phones and other mobile devices: - Development of applications for mobile phones by which it will be possible to access and use the Portal through a mobile phone. |  |  |  |
| Relevance: (Briefly describe the way in which this commitment is relevant to further advancing OGP values –access to information, public accountability, civic participation, and technology and innovation for openness and accountability) |  | In relation to access to information, mobile application Portal e-Government increases availability of information due to the fact that mobile platforms are most accessible and used by the largest target group. Public accountability is assured by regular updating and publishing of relevant information on the Portal mobile application and through decentralised method of publicising services given that each institution is responsible for its services in terms of accuracy of information regarding procedures, legal basis and fee amount. Mobile application facilitates the participation of citizens and enables them to provide feedback concerning the quality of services, to file complaints or rank provided service using stars (1-5 stars). Mobile platform is a technological innovation introduced for the Portal. |  |  |  |
| Ambition: (Briefly describe the intended strategic results and how this commitment will either make government more openness or improve government through more openness) |  | It is expected that the level of using electronic services will grow as well as the participation of citizens who will provide more feedback using the mechanisms to be incorporated in the mobile application. These mechanisms will be used both for the services and for the section e-Participation. In addition, the section related to announcement of job competitions for public administration will contribute to better accessibility of information that is significant for users. |  |  |  |
| Completion level: |  | Not started | Limited | Substantial | Completed |
|  |  | Х |  |  |  |
| Description of the results: (Include specific activities within the reporting period (first or second year of the action plan) and, wherever possible, please indicate whether there has been evidence of members of the public using the commitment or whether the commitment has had an effect |  | The activity has not been launched due to the lack of budget funds. The impact of this commitment is expected to be substantial for both the promotion and the use of the Portal. |  |  |  |
| End date/Completion date: |  | Expected in 2016 |  |  |  |
| Next steps: |  | This activity is planned for the following period. |  |  |  |
| Additional information (Description on what remains to be achieved and any risks or challenges to implementing the commitment) |  |  |  |  |  |
| Risk to implementing this activity is the lack of budget funds. |  |  |  |  |  |

COMMITMENT 9. IMPROVE TRANSPARENCY IN THE WORK OF PUBLIC AUTHORITIES

| Activity 9.1. Harmonize websites of state administration authorities and local self-government units with Guidelines for website design. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead implementing agency: |  | Directorate for eGovernment |  |  |  |
| Responsible person: |  | Rade Dragovic |  |  |  |
| E-mail: |  | rade.dragovic@deu.gov.rs |  |  |  |
| Phone: |  | +381 11 32 39 730 |  |  |  |
| Other Actors Involved | Government |  |  |  |  |
|  | CSOs, private sector, working groups, multilaterals |  |  |  |  |
| Main objective |  | Improve transparency in public administration |  |  |  |
| Brief description of activity: |  | Harmonization of websites of state administration authorities and local self-government units with the Guidelines for website design: - Expand the scope of assessment of harmonization according to Guidelines to local self-government units - Annual report on website harmonization that should be adopted by the Government |  |  |  |
| Relevance: (Briefly describe the way in which this commitment is relevant to further advancing OGP values –access to information, public accountability, civic participation, and technology and innovation for openness and accountability) |  | Websites are the main source of information about the work performed by state administration authorities and local self-government units. Guidelines define the type of information and manner of providing information and services via internet presentations and the authorities are accountable for the provision of all legally required information. The method of disseminating information should conform to the needs of various user categories, with the focus on different groups with disabilities, and it should enable civic participation in the work of authorities, in terms of voicing opinion and providing relevant feedback. In view of this, technology and innovation are used for achieving greater openness and accessibility. To this end a methodology has been developed for assessing the level of conformity of websites with the Guidelines and an annual Report to the Government is prepared and published on the Directorate website. Assessments of websites at both central and local government level are provided. |  |  |  |
| Ambition: (Briefly describe the intended strategic results and how this commitment will either make government more openness or improve government through more openness) |  | Assessment report gives an accurate overview of each public authority regarding its fulfilment of the set criteria for publication of information and services, and serves as a basis for the upgrade of websites, which enables better awareness and public administration services, as well as higher civic participation. This also contributes to stronger accountability of authorities to harmonise their websites with specified standards. |  |  |  |
| Completion level: |  | Not started | Limited | Substantial | Completed |
|  |  |  |  |  | Х |
| Description of the results: (Include specific activities within the reporting period (first or second year of the action plan) and, wherever possible, please indicate whether there has been evidence of members of the public using the commitment or whether the commitment has had an effect |  | Assessment results indicate a significant increase in the number of authorities that regularly publish their Information booklets, in accordance with the Law on Free Access to Information of Public Importance. In addition, the number of electronic services publicised on the Portal and websites of authorities is on the rise. Expected results are particularly important for local self-government units as their websites have the most room for improvement. The impact of this commitment can be considered moderate to transformative. The impact of the website assessment to improved and standardized presence of information and services of local self-governments on the website will be able to be exactly estimated after at least one more annual assessment and results comparison. |  |  |  |
| End date/Completion date: |  | Government adopted Assessment Report in July 2015. |  |  |  |
| Next steps: |  | Methodology improvement is planned, particularly at the local government level. |  |  |  |
| Additional information (Description on what remains to be achieved and any risks or challenges to implementing the commitment) |  |  |  |  |  |

| Activity 9.2. Improve the provisions of the Law on Free Access to Information |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead implementing agency: |  | MPALSG |  |  |  |
| Responsible person: |  | Natalija Pavlovic Sinikovic |  |  |  |
| E-mail: |  | natalija.pavlovic@mduls.gov.rs |  |  |  |
| Phone: |  | + 381 11 2645-231 |  |  |  |
| Other Actors Involved | Government |  |  |  |  |
|  | CSOs, private sector, working groups, multilaterals |  |  |  |  |
| Main objective |  | Improve transparency in public administration |  |  |  |
| Brief description of activity: |  | Improve the provisions of the Law on Free Access to Information of Public Importance so to determine the obligation of public authorities to develop and maintain a website with all the information about the work of the authority in accordance with applicable regulations, to establish the obligation of public authorities to submit draft regulations to the Commissioner for opinion. - Preparation of Draft Law amending the Law on Free Access to Information of Public Importance; - Determination and publishing of Public Hearing Program; - Conducting public debate; - Communicating Draft Law to the Government for consideration and formulation of the Bill |  |  |  |
| Relevance: (Briefly describe the way in which this commitment is relevant to further advancing OGP values –access to information, public accountability, civic participation, and technology and innovation for openness and accountability) |  | Improvement of the legal framework in this area will contribute to better transparency of public authorities and public accountability for transparent operation and good management. Better realization of the right to access information, improved understanding of the role/powers of the Commissioner by the public authorities, as well as raising of public awareness regarding the importance of this right are preconditions for open government. |  |  |  |
| Ambition: (Briefly describe the intended strategic results and how this commitment will either make government more openness or improve government through more openness) |  | Enhance the legal framework with the aim to improve the transparency in public administration, reduce the number of complaints filed with the Commissioner for Information of Public Importance and Protection of Personal Data, continuous oversight |  |  |  |
| Completion level: |  | Not started | Limited | Substantial | Completed |
|  |  |  | Х |  |  |
| Description of the results: (Include specific activities within the reporting period (first or second year of the action plan) and, wherever possible, please indicate whether there has been evidence of members of the public using the commitment or whether the commitment has had an effect |  | A special working group mandated to prepare a Draft Law amending the Law on Free Access to Information of Public Importance was set up on 31 March 2015. In the period from the establishment to 25 November 2015, this special Working group held five meetings, which were also attended by representatives of civil society, the Administrative Court, persons authorized to act on requests for access to information of public importance. In December 2015, a one-day workshop on the application of the Law was organized by MPALS and the Office of the Commissioner for Information of Public Importance. During 2016, consultations were held with representatives of SIGMA in terms of improving legislative framework on access to information of public importance. Considering the fact that parliamentary elections in Serbia were held in 2016, as well as that in the period from March to August 2016 the Government was working in the technical mandate, preparation of Draft Law on amending the Law on Free Access to Information of Public Importance will continue in the coming period, and it is also included in the OGP Action Plan for 2016 and 2017. |  |  |  |
| End date/ Completion date: |  | 4 Quarter 2016 |  |  |  |
| Next steps: |  | Continue the implementation of this activity in 2016. This activity is also included in the next OGP Action Plan for 2016 and 2017. |  |  |  |
| Additional information (Description on what remains to be achieved and any risks or challenges to implementing the commitment) |  |  |  |  |  |
| End date of this activity is specified in the Action Plan for Charter 23. This activity will be monitored through the mentioned Action Plan. |  |  |  |  |  |

COMMITMENT 10. INTRODUCE NEW TECHNOLOGIES TO IMPROVE SERVICES PROVIDED TO CITIZENS

| Activity 10.1. Establish “Electronic Bulletin Board” in all police departments and stations, and the Ministry of Internal Affairs |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead implementing agency: |  | Directorate for e-Government |  |  |  |
| Responsible person: |  | Dusan Stojanovic |  |  |  |
| E-mail: |  | dusan.stojanovic@deu.gov.rs |  |  |  |
| Phone: |  | + 381 11 334 18 85 |  |  |  |
| Other Actors Involved | Government | Ministry of Internal Affairs |  |  |  |
|  | CSOs, private sector, working groups, multilaterals |  |  |  |  |
| Main objective |  | Facilitate access to information and obtaining documents electronically |  |  |  |
| Brief description of activity: |  | Establishing “Electronic Bulletin Board“ in all police departments and stations, and the Ministry of Internal Affairs - Setting up of kiosks in police stations where citizens can get the information on procedures for obtaining services, or submit the request for services from the Portal - Providing payment of administrative fees via credit cards, at kiosks |  |  |  |
| Relevance: (Briefly describe the way in which this commitment is relevant to further advancing OGP values –access to information, public accountability, civic participation, and technology and innovation for openness and accountability) |  | Establishing “Electronic Bulletin Board“ in all police departments and stations, and setting up of kiosks in police stations will provide citizens with access to information on procedures for obtaining services, as well as with the opportunity to submit the request for services that are also publicised on the e-Government Portal. This will ensure civic participation and access to services for those citizens that do not have technical possibilities or knowledge to perform these activities via computer or mobile telephones. In this way, technology and innovation are used for openness of public administration. Providing possibility for payment of administrative fees via credit cards at kiosks is an innovative technological solution aimed at offering users a complete service. |  |  |  |
| Ambition: (Briefly describe the intended strategic results and how this commitment will either make government more openness or improve government through more openness) |  | The project is planned in cooperation with the Ministry of Internal Affairs and the kiosks are to be placed in police stations, so that they are available to citizens who would be assisted by relevant personnel. The aim is to ensure a greater participation of citizens who do not have access to information communication technology (ICT) or do not possess adequate knowledge and skills to use electronic services or access electronic information. |  |  |  |
| Completion level: |  | Not started | Limited | Substantial | Completed |
|  |  | Х |  |  |  |
| Description of the results: (Include specific activities within the reporting period (first or second year of the action plan) and, wherever possible, please indicate whether there has been evidence of members of the public using the commitment or whether the commitment has had an effect |  | This commitment was stalled at testing, as it includes mainly ICT equipment, and to a lesser extent software and human resources, for which there were no funds. |  |  |  |
| End date/ Completion date: |  |  |  |  |  |
| Next steps: |  | It is planned to ensure funding for this project, and the lack of it has been the main obstacle for the project implementation. |  |  |  |
| Additional information (Description on what remains to be achieved and any risks or challenges to implementing the commitment) |  |  |  |  |  |

| Activity10.2. Realize electronic services for personal documents |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead implementing agency: |  | Directorate for eGovernment |  |  |  |
| Responsible person: |  | Dusan Stojanovic |  |  |  |
| E-mail: |  | dusan.stojanovic@deu.gov.rs |  |  |  |
| Phone: |  | + 381 11 334 18 85 |  |  |  |
| Other Actors Involved | Government | Ministry of Internal Affairs |  |  |  |
|  | CSOs, private sector, working groups, multilaterals |  |  |  |  |
| Main objective |  | Facilitate access to information and obtaining documents electronically |  |  |  |
| Brief description of activity: |  | The realization of electronic services related to issuance of personal documents to a level limited by the obligatory presence of citizens due to identification and biometric data - Procurement of equipment and installation - Commissioning of the mentioned services |  |  |  |
| Relevance: (Briefly describe the way in which this commitment is relevant to further advancing OGP values –access to information, public accountability, civic participation, and technology and innovation for openness and accountability) |  | The electronic services related to the issuance of personal documents to the level of submitting an electronic request via the e-Government Portal which contains precise information on the procedure. Such services cannot be completely provided without a civic presence. It should be ensured that the services require a civic presence only if biometric data need to be collected and when documents receipt requires identification. In this manner, the Ministry of Internal Affairs, as the service provider, is publicly accountable for ensuring the accuracy of biometric data and providing a service in a technologically up-to-date manner. |  |  |  |
| Ambition: (Briefly describe the intended strategic results and how this commitment will either make government more openness or improve government through more openness) |  | The service related to issuing personal documents will be maximally user-oriented in compliance with the operating principles of open government. The citizens will have transparent information on the procedures whereas the time necessary for obtaining documents will be shortened as much as possible, i.e. the intended deadline is within five working days. The civic presence during services provision will be reduced to minimum. OGP values to which this commitment pertains are technological innovations for transparency and accountability, and public accountability as well. |  |  |  |
| Completion level: |  | Not started | Limited | Substantial | Completed |
|  |  |  |  | Х |  |
| Description of the results: (Include specific activities within the reporting period (first or second year of the action plan) and, wherever possible, please indicate whether there has been evidence of members of the public using the commitment or whether the commitment has had an effect |  | Technological implementation of the e-Government Portal services has been completed, whereas the production services are expected to be implemented after necessary additional modifications of the MoI IS take place by the end of 2015. The equipment, biometric above all, is partly renewed (within the allocated budget) to a degree that allows for the provision of these services. The activity includes mainly improvements of the e-Government Portal, which was funded form the budget. The other part relates to improvements of the back office which is done in-house. The completion level of this activity can be assessed as substantial. |  |  |  |
| End date/Completion date: |  | December 2016 |  |  |  |
| Next steps: |  | An analysis of the outcomes and an estimate of user satisfaction are going to be conducted after the initial kick-off. All identified drawbacks related not only to the ICT solution but also to any changes in the operations management will be removed and upgrades and innovations will be implemented. |  |  |  |
| Additional information (Description on what remains to be achieved and any risks or challenges to implementing the commitment) |  |  |  |  |  |
| Other services that are related to the issuance of other personal documents in connection with the use of weapons, etc, as well as the issuance of qualified certificates by the MoI Certification Authority, are planned to be published on the e-Government Portal. These qualified certificates are issued by the ID section. |  |  |  |  |  |

COMMITMENT 11. IMPROVE COOPERATION WITH CIVIL SOCIETY ORGANIZATIONS IN PUBLIC POLICY MAKING

| Activity 11.1. Draft the National Strategy for Creating the Enabling Environment for Civil Society Development in the Republic of Serbia for the period 2014-2018 and its Action Plan |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead implementing agency: |  | Office for Cooperation with Civil Society and MPALS |  |  |  |
| Responsible person: |  | Milena Banovic, Head of Department for Creating the Enabling Environment for Civil Society Development, has been temporarily performing the duties of the Office Director according to a Government Conclusion of the Republic of Serbia 24, No. 119-9248/2015 as of 28 August 2015 |  |  |  |
| E-mail: |  | milena.banovic@civilnodrustvo.gov.rs |  |  |  |
| Phone: |  | + 381 11 311 3895 |  |  |  |
| Other Actors Involved | Government |  |  |  |  |
|  | CSOs, private sector, working groups, multilaterals |  |  |  |  |
| Main objective |  | Improve the cooperation between public administration and civil society organisations |  |  |  |
| Brief description of activity: |  | Drafting the Strategy for Creating the Enabling Environment for Civil Society Development for the period 2014-2018, and Action Plan for implementation of the Strategy, through a wide consultative process with all stakeholders throughout Serbia. -Preparation of draft text of the Strategy and Action Plan - Conducting 10 consultative meetings throughout Serbia with representatives of local and regional institutions, civil society organizations, and business sector -Determination and publishing of Public Hearing Program; -Conducting public debate; - Submitting Proposal Strategy and Proposal Action Plan to the Government for consideration and adoption |  |  |  |
| Relevance: (Briefly describe the way in which this commitment is relevant to further advancing OGP values –access to information, public accountability, civic participation, and technology and innovation for openness and accountability) |  | Adopting the Strategy for Creating the Enabling Environment for Civil Society Development will enable civil society organisations and stakeholders to participate more actively in making and implementing public policies, greater transparency and accountability of the state administration authorities. The implementation of this activity will contribute to enhancing the institutional and legal framework for the cooperation between the state administration authorities and civil society in the Republic of Serbia by introducing new and/or improving the existing, forms and mechanisms of cooperation between the state administration authorities and civil society at all participation levels. |  |  |  |
| Ambition: (Briefly describe the intended strategic results and how this commitment will either make government more openness or improve government through more openness) |  | The aim of adopting the National Strategy for Creating the Enabling Environment for Civil Society Development is establishing a framework for the development and sustainability of civil society, improving the cooperation between government institutions and civil society organisations as well as defining measures for more active participation of stakeholders in making and implementing public policies for the purpose of further developing and democratising our society, promoting and protecting human rights and freedom of association. |  |  |  |
| Completion level: |  | Not started | Limited | Substantial | Completed |
|  |  |  |  | Х |  |
| Description of the results: (Include specific activities within the reporting period (first or second year of the action plan) and, wherever possible, please indicate whether there has been evidence of members of the public using the commitment or whether the commitment has had an effect |  | As part of this activity and the first step - “Preparation of draft text of the National Strategy and Action Plan” – the Office for Cooperation with Civil Society drew up and posted a draft strategy on the website in III Quarter 2014. Along with the implementation of the second step of this activity, i.e. “Conducting ten consultative meetings throughout Serbia with the representatives of local and regional institutions, civil society organizations and business sector “, the stakeholders had an opportunity to leave their comments on the strategic document on: http://www.civilnodrustvo.gov.rs/. The third and the fourth step of the activity, i.e. “A set out and published public debate program” and “Conducting a public debate” were implemented during July and August in 2015. A public debate was held in Belgrade, Novi Sad and Niš from July 23 to 14 August 2015. The National Strategy Proposal and the Action Plan Proposal are expected to be submitted to the Government for consideration and adoption at the end of October 2016. |  |  |  |
| End date/Completion date: |  | 4 Quarter 2016 |  |  |  |
| Next steps: |  | The Strategy Proposal for Creating the Enabling Environment for Civil Society Development in the Republic of Serbia for the period 2016 and 2020, as well as the accompanying Action Plan and the Plan for the Strategy Implementation and Efficiency Evaluation (a monitoring and evaluation plan), in cooperation with the Ministry of Public Administration and Local Self-Government, has been submitted to the competent state administration authorities in October 2016. It is currently in the process of harmonization with the submitted opinions and the adoption by the Government is expected by the beginning of December 2016. |  |  |  |
| Additional information (Description on what remains to be achieved and any risks or challenges to implementing the commitment) |  |  |  |  |  |
| The fact that the Office for Cooperation with Civil Society did not have a director by 12 February 2016, when the acting director was appointed by a Government Decision, was one of the problems in implementing this commitment. Issues with regard to defining budgetary and donation funds in the Action Plan constitute risks and challenges to further implementing the activity. |  |  |  |  |  |

| Activity 11.2. Improve the provisions of the Law on Self-Government |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead implementing agency: |  | Ministry of Public Administration and Local Self-Government – Department for Local Self-Government System |  |  |  |
| Responsible person: |  | Minister and Assistant Minister for Local Self-Government |  |  |  |
| E-mail: |  | sasa.mogic@mduls.gov.rs |  |  |  |
| Phone: |  |  |  |  |  |
| Other Actors Involved | Government |  |  |  |  |
|  | CSOs, private sector, working groups, multilaterals |  |  |  |  |
| Main objective |  | Improve the cooperation between public administration and civil society organisations |  |  |  |
| Brief description of activity: |  | Amending the Law on Local Self-Government, so to specially consult the Standing Conference of Towns and Municipalities with the aim of cooperation between state administration authorities and local self-government units. - Communicating Draft Law to the Government for consideration and formulation of the Bill |  |  |  |
| Relevance: (Briefly describe the way in which this commitment is relevant to further advancing OGP values –access to information, public accountability, civic participation, and technology and innovation for openness and accountability) |  | Achieving better cooperation with the associations of the local self-government units allows for their active participation in finding appropriate legal solutions at local government level, which enables them to represent interests of their members. |  |  |  |
| Ambition: (Briefly describe the intended strategic results and how this commitment will either make government more openness or improve government through more openness) |  | Achieving greater transparency in the work of the local self-government authorities and participation of the general public in finding appropriate legal solutions at local government level, which in turn allows for the oversight of the said authorities |  |  |  |
| Completion level: |  | Not started | Limited | Substantial | Completed |
|  |  |  |  | X |  |
| Description of the results: (Include specific activities within the reporting period (first or second year of the action plan) and, wherever possible, please indicate whether there has been evidence of members of the public using the commitment or whether the commitment has had an effect |  | Even though the amending process of the Law on Local Self-Government, and given particular needs and interests of the LSUs, does not envisage seeking special consultancy from the Standing Conference of Towns and Municipalities, in practice such cooperation is regularly achieved with the association of towns and municipalities as well as with other associations. Their participation is particularly important in the process of adopting laws and other regulations, i.e. seeking consultancy from the associations of the local self-government units even during the regulations drafting phase, which directly affect the position and functions of the LSUs and enable them to be active participants in working groups mandated to draft those regulations. Cooperation with the SCTM is regularly demonstrated through participation in public debates, workshops and round tables during the procedure of drafting laws and other regulations concerning the scope of work of the ministry for local self-government. The best example is the participation in all activities undertaken with regard to drawing up a Draft Law amending the Law on Local Self-Government, a Draft Law on Employees in AP and LSUs, a Draft Law amending the Law on Municipal Police. Furthermore, the SCTM is also involved in the co-ordination structure of the public administration reform along with civil servants and state secretaries. |  |  |  |
| End date/Completion date: |  | 4 Quarter 2016 |  |  |  |
| Next steps: |  | Draw up and communicate the Draft Law to the National Assembly for adoption |  |  |  |
| Additional information (Description on what remains to be achieved and any risks or challenges to implementing the commitment) |  |  |  |  |  |
| Draft Law amending the Law on Local Self-Government was determined in October 2015 and communicated to the Government for consideration and Bill formulation. During the technical Government, the text was returned to the Ministry. As in April 2016 a new government was formed, it is necessary to repeat the whole procedure regarding the adoption of this law. The Minister of Public Administration and Local Self-Government established a Special working group mandated to draft this legal regulation, taking into account the so far prepared text of the Draft Law. . |  |  |  |  |  |

COMMITMENT 12. STRENGTHEN CIVIC PARTICIPATION IN LOCAL GOVERNMENT AFFAIRS

| Action 12.1. Sign the Additional Protocol to the European Charter of Local Self-Government |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead implementing agency: |  | Ministry of Public Administration and Local Self-Government – Department for Local Self-Government System |  |  |  |
| Responsible person: |  | Minister and Assistant Minister for Local Self-Government |  |  |  |
| E-mail: |  | sasa.mogic@mduls.gov.rs |  |  |  |
| Phone: |  |  |  |  |  |
| Other Actors Involved | Government |  |  |  |  |
|  | CSOs, private sector, working groups, multilaterals |  |  |  |  |
| Main objective |  | Improve the local self-government system |  |  |  |
| Brief description of activity: |  | Signing the Additional Protocol to the European Charter of Local Self-Government which guarantees the participation of citizens in the affairs of local authorities. - Preparation of the Draft Law on Ratification of the Additional Protocol to the European Charter of the Local Self-Government - Communicating the Draft Law to the Government for consideration and formulation of the Bill |  |  |  |
| Relevance: (Briefly describe the way in which this commitment is relevant to further advancing OGP values –access to information, public accountability, civic participation, and technology and innovation for openness and accountability) |  | The Additional Protocol provides a legal framework which guarantees the right to participate in the affairs of local authorities and define the content of the right, with limitations that in certain instances may affect the exercise of the right to participate in the affairs of local authorities. This document should reflect and observe the diversity of participation methods and procedures introduced into the national, regional and local legislation, including: the right to participate in public life at local level, the right to obtain information from the local authorities, as well as the obligation of the local authorities to ensure the exercise of those rights. Inclusion of the citizens in the process of creating democratic institutions is a necessity since they cannot last without citizen participation or without citizens having a key role by letting them take part in government. |  |  |  |
| Ambition: (Briefly describe the intended strategic results and how this commitment will either make government more openness or improve government through more openness) |  | The right to participate in the affairs of local authorities denotes the right to seek to determine or to influence the exercise of local authorities’ powers and responsibilities, and to facilitate the exercise of this right, and give effect to this right (Article 2 of the Additional Protocol). |  |  |  |
| Completion level: |  | Not started | Limited | Substantial | Completed |
|  |  |  | X |  |  |
| Description of the results: (Include specific activities within the reporting period (first or second year of the action plan) and, wherever possible, please indicate whether there has been evidence of members of the public using the commitment or whether the commitment has had an effect |  | On 4 June 2013 the Government defined a Basis for signing the Additional Protocol to the European Charter of the Local Self-Government and adopted the text of the Additional Protocol. Due to the fact that a law package regarding the scope of work of local self-government is a priority task, the implementation of this activity has been carried over to the following period. Factually, all requirements are fulfilled, but the formal and factual state of play would become equal after the signing. |  |  |  |
| End date/Completion date: |  | 4 Quarter 2016 |  |  |  |
| Next steps: |  | It is necessary to determine the most suitable time for signing (giving the authorisation for signing) the Additional Protocol. |  |  |  |
| Additional information (Description on what remains to be achieved and any risks or challenges to implementing the commitment) |  |  |  |  |  |

| Activity 12.2. Strengthen local governments capacities |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead implementing agency: |  | Office for Cooperation with Civil Society |  |  |  |
| Responsible person: |  | Milena Banovic, Head of the Department for Planning and Creating Enabling Environment for the Development of Civil Society, has been temporarily performing the duties of the Office Director according to a Government Conclusion of the Republic of Serbia 24, No. 119-9248/2015 as of 28 August 2015 |  |  |  |
| E-mail: |  | milena.banovic@civilnodrustvo.gov.rs |  |  |  |
| Phone: |  | + 381 11 311 3895 |  |  |  |
| Other Actors Involved | Government |  |  |  |  |
|  | CSOs, private sector, working groups, multilaterals |  |  |  |  |
| Main objective |  | Improve the cooperation between local self-governments and civil society organizations |  |  |  |
| Brief description of activity: |  | Strengthening the capacity of local self-governments in the areas of cooperation with civil society organizations and transparent funding of CSOs from the budgets of local governments - Organizing training for local self-government units employees, on the application of the Guidelines for the inclusion of civil society organizations in the process of adopting regulations and transparent funding of CSOs from the budget funds. |  |  |  |
| Relevance: (Briefly describe the way in which this commitment is relevant to further advancing OGP values –access to information, public accountability, civic participation, and technology and innovation for openness and accountability) |  | Strengthening public administration capacities for the cooperation with the civil society organisations and transparent funding of CSOs from the local government budgets will provide conditions for attaining the set standards for including CSOs in the process of making, adopting and implementing public policies as the main performance principle of open government. |  |  |  |
| Ambition: (Briefly describe the intended strategic results and how this commitment will either make government more openness or improve government through more openness) |  | Enhanced local government capacities for cooperation with CSOs and established sustainable mechanisms for cooperation between the public administration and CSOs in drafting and implementing regulations and other documents pertaining to public policies. |  |  |  |
| Completion level: |  | Not started | Limited | Substantial | Completed |
|  |  |  |  |  | Х |
| Description of the results: (Include specific activities within the reporting period (first or second year of the action plan) and, wherever possible, please indicate whether there has been evidence of members of the public using the commitment or whether the commitment has had an effect |  | From January to April 2015, the Office for Coordination with Civil Society, together with TACSO project, conducted ten two-day seminars for local government representatives on the coordination with CSOs and transparent funding of CSOs from the local government budgets. A total number of 211 employees from the local government authorities attended the training courses, i.e. 73% of the total number of municipalities in Serbia took part. The largest number of participants are decision makers, i.e. heads of organisational units in those institutions that are in charge of the cooperation with and/or funding of civil society organisations. Such information indicates that there is a necessity to advance the knowledge about the cooperation with civil society and its mechanisms, as well as a necessity to improve the relevant legislation and practice of the transparent funding of CSOs from the local government budgets. Seminar evaluation by participants showed great satisfaction with the scope and usability of the gained knowledge in 90% of cases. After conducting the seminars, the Office has been recognised as an advisory body for implementing the activities related to involving and consulting with CSOs, particularly with regard to holding open competitions for providing financial assistance to CSOs. A report on the conducted training courses is posted on the Office for Cooperation with Civil Society website: http://civilnodrustvo.gov.rs/vest.37.html?newsId=651 . |  |  |  |
| End date/Completion date: |  | 1 Quarter 2015 |  |  |  |
| Next steps: |  | In keeping with the activities set out in the Strategy for Creating the Enabling Environment for Civil Society Development in the Republic of Serbia for the period 2016-2020, the activities were proposed aiming at increasing capacities of local self-government units and civil society organizations for greater participation of interested public in drafting laws and other instruments of public policies, as well as transparent funding of CSOs from local government budgets. These activities will start to be implemented once this strategic document is adopted. |  |  |  |
| Additional information (Description on what remains to be achieved and any risks or challenges to implementing the commitment) |  |  |  |  |  |
| In keeping with the activities specified in the Draft Strategy for Creating the Enabling Environment for Civil Society Development in the Republic of Serbia for 2016-2020, in 2017 the Office plans to continue with training courses for civil servants on the manner and procedure for cooperation and inclusion of civil society organization in the process of preparation, implementation and monitoring of regulations and policy documents, as well as on more transparent funding of civil society organizations from the budget funds. Also, Office activities regarding transparent funding of civil society organizations form the budget funds include development of the second revised edition of the Guide through transparent funding of civil society organizations from the budgets of local self-governments, which is equally informative for state administration authorities. Also, it is planned to adopt a bylaw which would further regulate the monitoring of implementation and evaluation of supported programs and projects of associations and other civil society organizations. |  |  |  |  |  |

COMMITMENT 13. STRENGTHEN PARTICIPATION OF CIVIL SOCIETY ORGANIZATIONS IN MONITORING THE PUBLIC ADMINISTRATION REFORM IMPLEMENTATION

| Activity 13.1. Establish a coordination system for monitoring the Public Administration Reform Strategy |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead implementing agency: |  | Ministry of Public Administration and Local Self-Government |  |  |  |
| Responsible person: |  | Ljiljana Uzelac, Head of Division for the Implementation of Public Administration Reform and Professional Development |  |  |  |
| E-mail: |  | ljiljana.uzelac@mduls.gov.rs |  |  |  |
| Phone: |  | 011 2681-152 |  |  |  |
| Other Actors Involved | Government |  |  |  |  |
|  | CSOs, private sector, working groups, multilaterals |  |  |  |  |
| Main objective |  | Improve the monitoring and evaluation system of the public administration reform |  |  |  |
| Brief description of activity: |  | Establishing a coordination system for monitoring the Public Administration Reform Strategy - Establishing an Inter-ministerial project group consisting of civil servants (secretaries in ministries and civil servants from relevant special organization and Government services) and representatives of civil society organizations - Conducting training for members of Inter-ministerial project group - Holding regular meetings of the Inter-ministerial project group (at least 4 times a year) |  |  |  |
| Relevance: (Briefly describe the way in which this commitment is relevant to further advancing OGP values –access to information, public accountability, civic participation, and technology and innovation for openness and accountability) |  | Involving non-governmental organizations as equal members in decision-making, reporting, coordination and decision-making on directions of the public administration reform is in compliance with the core OGP values and contributes to building public confidence and greater government accountability. |  |  |  |
| Ambition: (Briefly describe the intended strategic results and how this commitment will either make government more openness or improve government through more openness) |  | Increase transparency in the process of reporting, coordination and decision-making on the directions of the public administration reform; then use capacities and knowledge owned by the non-governmental sector; build capacities of the non-governmental sector through direct participation in monitoring and decision-making, the interaction of the non-governmental and governmental sector to make the reform process closer to the citizens and responsive to actual demands coming from the civil sector. |  |  |  |
| Completion level: |  | Not started | Limited | Substantial | Completed |
|  |  |  |  |  | Х |
| Description of the results: (Include specific activities within the reporting period (first or second year of the action plan) and, wherever possible, please indicate whether there has been evidence of members of the public using the commitment or whether the commitment has had an effect |  | The Action Plan for implementing the PARS was developed as part of an extensive consultancy process during a few-month period, where the Working group mandated to draft the Action Plan consisted of, apart from all state administration bodies, civil society representatives (members of the Sectoral Civil Society Organisations - SECO consortium for public administration reform and a representative of Transparency Serbia, and representatives of the Standing Conference of Towns and Municipalities (SCTM). The Strategy and the Action Plan envisage, and in the previous period it was established a four level coordination structure to manage and monitor the public administration reform. In addition to the Ministry of Public Administration and Local Self-Government and organizational unit within the Ministry dealing with monitoring and being the first, administrative level, there are two political coordination levels at government level: the Council for Public Administration Reform including the Prime Minister, deputy prime ministers and line ministries and the College of State Secretaries with deputy ministries. The idea was to have another operational, administrative level which will equally include, in addition to civil servants, representatives of civil society, and this was achieved by establishing an Inter-ministerial project group (hereinafter referred to as: IPG). Pursuant to a Decision taken by the Minister of Public Administration and Local Self-Government on 23 February 2015, the Inter-ministerial project group was established as an expert coordination level for the implementation of the public administration reform, and it has held four meetings so far (29.06.2015, 07.10.2015, 15.12.2015, and 06.04.2016). Its members include secretaries from all ministries and representatives of the similar rank from special Government organisations and services, and equally involved are representatives of civil society organizations, through the member organisations of the SECO (Sectoral Civil Society Organizations) consortium mechanism related to the public administration reform, as well as the SCTM as a bond with the local government. The Group has 34 members and 33 deputy members, with six members and 6 deputy members coming from the non-governmental sector (European Movement Serbia, European Project Centre, European Policy Centre, Belgrade Open School, Belgrade Fund for Political Excellence, Standing Conference of Towns and Municipalities). The Inter-ministerial project group held a meeting on 29 June 2015, where current implementation of the PAR AP (regarding rationalization and wages) and reporting and monitoring procedure for PAR AP was discussed. At the second meeting on 7 October 2015, the IPG’s Rules of Procedure were adopted, as well as the six-month Report on the implemented activities of the PAR AP in the first half of 2015. Also, explanations of solutions provided for by recently adopted Law on Manner of Determining the Maximum Number of Public Sector Employees was discussed. At the third meeting, Information about World Bank’s loan Program-for-Results – modernization and optimization of public administration, and Information about realization of functional analysis within optimization support project were presented. At the fourth meeting, the Annual report on PAR AP implementation for 2015 was adopted, Report on activities in the rationalization process for 2015 was presented and existing issues in the payment of severance pays and cash benefits in the rationalization procedure, or implementation of the provisions of the Law on Manner of Determining the Maximum Number of Public Sector Employees relating to the procedure for exercising the right of employees to cash benefit or severance pay from the RS budget. In December 2014, a training course was conducted for the members of the Inter-ministerial project group on monitoring and evaluating public policies, implementation tools, practices and methods for including the civil society. |  |  |  |
| End date/Completion date: |  | February 2015 |  |  |  |
| Next steps: |  | Continue further training and regular meeting with the aim to monitor the AP implementation, assess the ratio of the number of members for more efficient functioning of the project group. |  |  |  |
| Additional information (Description on what remains to be achieved and any risks or challenges to implementing the commitment) |  |  |  |  |  |

Government Conclusion 05 number 05 345-03-1758/2012 dated 16 March 2012

Government Conclusion 05 number 337-3146/2013-001 dated 23 April 2013, “Official Gazette of RS”, number  38/2012

Government Conclusion 05 number 021-16514/2014, “Official Gazette of RS”, number 14/2014

“Official Gazette of RS” number: 26/10

Guidelines for the Inclusion of Civil Society Organizations in the regulation adoption process http://civilnodrustvo.gov.rs/enabling-environment/legal-framework/guidelines.246.html

“Official Gazette of RS”, number: 31/15