Self-Assessment Report Template

<<Liberia>>

Annual Self-Assessment Report

National Action Plan 2015-2017

- Introduction and Background

I.	Introduction

On 7 September 2011, the Liberian Government through Her Excellency President Ellen Johnson Sirleaf joined the Open Government Partnership (OGP). In her Letter of Intent, President Ellen Johnson Sirleaf stated: “…Despite this progress, there is still much to be done to make Liberia more open, transparent and free from corruption. Our involvement in the transparency activities like the OGP provides us the opportunity to demonstrate and strengthen commitments to open government, accountability and fighting corruption”.

The OGP-Liberia’ National Action Plan (NAP) is a shared plan, co-created and implemented by Government and Civil Society organizations focusing on enhancing Transparency, Citizens’ Participation, Accountability, and Technology & Innovation. It acts as a force that brings together  government and CSOs to  enhancing each other to easily take the government more closely to its citizens   through public information sharing using online and offline   tools, through co-creation of country National Action Plan, conduct public events and build a networks and campaigns across Liberia that ensure information   reach to every citizens of Liberia around issues of accountability, transparency, citizens’ participation, technology and innovation through regular meetings,  communications campaigns, network-building, and access to timely and credible information.

II. Background

The OGP, launched on September 20, 2011 in New York City, USA, is structured around four key pillars: Transparency, Citizens’ Participation, Accountability, and Technology & Innovation. A major requirement for full membership status in the OGP is that each participating country must develop and adopt a Country’s Action Plan consistent with the pillars of the OGP. On 7 September 2011, the Liberian Government through Her Excellency President Ellen Johnson Sirleaf joins the Open Government Partnership. A second National Action Plan was developed and endorsed in June 2014.  This report covers a mid-term self-assessment of the 2015-2017 National Action Plan.

- National Action Plan Process

The Annual Self-Assessment Report focuses on the four keys areas of OGP. They are: Transparency, Citizen Participation, Accountability and Integrity, and Technology and Innovation.

- Independent Reporting Mechanism (IRM) Recommendations

The IRM Recommendations from the implementation of the first NAP were used as a guide to improve the process of co-creating the second NAP and implementation by ensuring that the guidelines were adhered to, and also verified work that was done for accountability purpose.

- Implementation of National Action Plan commitments

| Commitment Completion Template |  |  |
| --- | --- | --- |
| Thematic Area 1: Transparency/ Commitment No. 1 |  |  |
| Lead implementing agency |  | Independent Information Commission |
| Name of responsible person from implementing agency |  | Cllr. Mark B. Freeman |
| Title, Department |  | Commissioner, Administration |
| Email |  | mbedorwla@yahoo.com |
| Phone |  | +231-886511170 |
| Other actors involved | Government | MICAT, FLY |
|  | CSOs, private sector, working groups, multilaterals | Carter Center, OSIWA, CEMESP, CENTAL |
| Main Objective |  | The main objective is the appointment Public Information Officers (PIOs) in government agencies and provision of training to fulfill their Terms of Reference. |
| Brief Description of Commitment (140 character limit) |  | The commitment seeks to ensure that additional 50 Public Information Officers (PIOs) were appointed in various governmental entities and trained by the Independent Information Commission. Furthermore, the Independent Information Commission would prepare and share quarterly reports and conduct capacity building training for its staffs. |
| Relevance Briefly describe the way in which this commitment is relevant to further advancing OGP values of access to information, public accountability, civic participation, and technology and innovation for openness and accountability. (A detailed description of these values is available in the OGP Values Guidance Note.) |  | The commitment is relevant to further advancing OGP values of access to information, public accountability, civic participation, and technology and innovation for openness and accountability thru the appointment of Public Information Officers. |
| Ambition Briefly describe the intended policy results of the commitment and how it will either make government more open or improve government through more openness. |  | The intended policy results of the commitment will make Liberia government more open because it allows the public to request for any information permissible by law from all government institutions without stating the use of said information. The appointed Public Information Officer is obligated by the FOI Law to give said information. |

| Completion Level | Not Started |  | Limited |  | Substantial | Completed |
| --- | --- | --- | --- | --- | --- | --- |
| Description of the results Include specific activities within the reporting period (first or second year of the action plan) and, wherever possible, please indicate whether there has been evidence of members of the public using the commitment or whether the commitment has had an effect. | The commitment has had substantial effect. Below are few instants: - 48 new Public Information Officers (PIOs) had been appointed and trained. - 5 Capacity building trainings were conducted. |  |  |  |  |  |
| End date | June 30, 2017 |  |  |  |  |  |
| Next steps | The next step is to complete the appointment and training of the outstanding 2 Public Information Officers (PIOs). |  |  |  |  |  |
| Additional information (The challenge to implementing the commitment was funding to underwrite the cost of training and equipment.) |  |  |  |  |  |  |
| Commitment Completion Template |  |  |  |  |  |  |
| Thematic Area 1: Transparency/ Commitment No. 2 |  |  |  |  |  |  |
| Lead implementing agency |  |  |  | iLab Liberia & Independent Information Commission |  |  |
| Name of responsible person from implementing agency |  |  |  | Mr. Carter Draper & Cllr. Mark B. Freeman |  |  |
| Title, Department |  |  |  | Program Director, Adm. Commissioner, Administration |  |  |
| Email |  |  |  | carter@ilabliberia.org mbedorwla@yahoo.com |  |  |
| Phone |  |  |  | +231-886403018 +231-886511170 |  |  |
| Other actors involved |  | Government |  | MICAT, MFDP |  |  |
|  |  | CSOs, private sector, working groups, multilaterals |  | Carter Center, CEMESP, CENTAL |  |  |
| Main Objective |  |  |  | The main objective is to popularize the Freedom of Information (FoI) Law and ensure access for more Liberians to the Law. |  |  |
| Brief Description of Commitment (140 character limit) |  |  |  | The commitment seeks to ensure that the Freedom of Information (FoI) Law is popularized by the use of both online and office line tools. Design and build an online FoI request platform that could be access quickly and easily by internet users; while the offline tool will be done by outreach and awareness for citizens across the country through town hall meetings and radio talk shows among others. |  |  |
| Relevance Briefly describe the way in which this commitment is relevant to further advancing OGP values of access to information, public accountability, civic participation, and technology and innovation for openness and accountability. (A detailed description of these values is available in the OGP Values Guidance Note.) |  |  |  | The commitment is relevant to further advancing OGP values of access to information, public accountability, civic participation, and technology and innovation for openness and accountability thru the popularization of the Freedom of Information (FoI) Law. |  |  |
| Ambition Briefly describe the intended policy results of the commitment and how it will either make government more open or improve government through more openness. |  |  |  | The intended policy results of the commitment will make Liberia government more open because it allows the public to understand the Freedom of Information (FoI) Law and to make request for any information from all government institutions without stating the use of said information. It also provides citizens with information on how they can request and access information under the Laws of Liberia. |  |  |

| Completion Level |  | Not Started | Limited |  | Substantial | Completed |
| --- | --- | --- | --- | --- | --- | --- |
| Description of the results Include specific activities within the reporting period (first or second year of the action plan) and, wherever possible, please indicate whether there has been evidence of members of the public using the commitment or whether the commitment has had an effect. |  | The commitment has had substantial effect. Below are few instants: - Platform was designed and built. The link to the platform is www.infolib.org.lr. - Outreach awareness activities were carried out in Bomi, Bong, Grand Bassa, Margibi, Grand Gedeh, Cape Mount, and Maryland Counties, respectively. Freedom of Information messages are planted at KLAY checkpoint, Bomi County, SKD-RIA Highway, Paynesville, and Freeport-Gardnersville road. |  |  |  |  |
| End date |  | June 30, 2017 |  |  |  |  |
| Next steps |  | The next step is to complete the awareness in the remaining nine (9) counties. |  |  |  |  |
| Additional information (The challenge to implementing the commitment is funding to facilitate additional awareness activities and the conduct of additional training.) |  |  |  |  |  |  |
| Commitment Completion Template |  |  |  |  |  |  |
| Thematic Area 1: Transparency/ Commitment No. 3 |  |  |  |  |  |  |
| Lead implementing agency |  |  |  | Ministry of Finance and Development Planning |  |  |
| Name of responsible person from implementing agency |  |  |  | Hon. Tanneh G. Brunson |  |  |
| Title, Department |  |  |  | Deputy Minister, Budget |  |  |
| Email |  |  |  | tbrunson@mfdp.gov.lr |  |  |
| Phone |  |  |  | +231-886236578 |  |  |
| Other actors involved | Government |  |  | MICAT, MIA |  |  |
|  | CSOs, private sector, working groups, multilaterals |  |  | CEMESP, CENTAL, LFIC, CUPPADL, LMC, All GSM companies |  |  |
| Main Objective |  |  |  | The main objective is to expand the Open Budget Initiative thus enhancing transparency in the budget preparatory and execution process. |  |  |
| Brief Description of Commitment (140 character limit) |  |  |  | The commitment seeks to ensure that Liberia’s budget is easily accessed to every Liberians and that the process is transparent. SMS platform should be developed to disseminate budget information through bulk SMS with instant SMS response and the Open Budget Initiative activities should be decentralized to the 15 counties of Liberia. |  |  |
| Relevance Briefly describe the way in which this commitment is relevant to further advancing OGP values of access to information, public accountability, civic participation, and technology and innovation for openness and accountability. (A detailed description of these values is available in the OGP Values Guidance Note.) |  |  |  | The commitment is relevant to further advancing OGP values of access to information, public accountability, civic participation, and technology and innovation for openness and accountability through decentralization and the platform creation of the Open Budget Initiative. It changes decades of secretive budget preparation process to the public in a significant way. |  |  |
| Ambition Briefly describe the intended policy results of the commitment and how it will either make government more open or improve government through more openness. |  |  |  | The intended policy results of the commitment will make Liberia government more open because it allows the public to access and understand Liberia budget. |  |  |

| Completion Level | Not Started | Limited | Substantial | Completed |
| --- | --- | --- | --- | --- |
| Description of the results Include specific activities within the reporting period (first or second year of the action plan) and, wherever possible, please indicate whether there has been evidence of members of the public using the commitment or whether the commitment has had an effect. | The commitment has had substantial effect. Below are few instants: - 10,000 copies of the Citizen’s Guide booklets produced, copies were distributed to 78 libraries of high schools, 6 universities and 6 community colleges across the 15 counties. - More than 3,000 citizens directly participated in a public forum and 11 focal group’s discussion. - There was awareness created through outreaches that were held in 11 counties for the FY2015/16 under the theme “National Open Budget”. |  |  |  |
| End date | June 30, 2017 |  |  |  |
| Next steps | The next step is to complete the SMS platform. |  |  |  |
| Additional information (The challenge to completing the implementation of this commitment is inadequate funding particularly to facilitate the setting up the SMS platform) |  |  |  |  |

| Commitment Completion Template |  |  |
| --- | --- | --- |
| Thematic Area 1: Transparency/ Commitment No. 4 |  |  |
| Lead implementing agency |  | LEITI |
| Name of responsible person from implementing agency |  | Hon. Myer W. Saye, Sr. |
| Title, Department |  | Deputy Head, Administration |
| Email |  | mwsaye@leiti.org.lr |
| Phone |  | +231-886551558 |
| Other actors involved | Government | Governance Commission, Land Commission, MIA, Law Reform Commission |
|  | CSOs, private sector, working groups, multilaterals | LMC, CENTAL, TGCI, concerned concession companies |
| Main Objective |  | The main objective is to make public information on proposed reforms in the Land and Natural Resources Sectors accessible to the public. |
| Brief Description of Commitment (140 character limit) |  | The commitment seeks to ensure that the public is informed on proposed reforms in the Land and Natural Resources sectors thru broad based stakeholders’ consultations in the counties to increase citizens’ understanding about issues of land and natural resources. |
| Relevance Briefly describe the way in which this commitment is relevant to further advancing OGP values of access to information, public accountability, civic participation, and technology and innovation for openness and accountability. (A detailed description of these values is available in the OGP Values Guidance Note.) |  | The commitment is relevant because it further advances OGP values of access to information, public accountability, , and technology and innovation for openness and accountability thru public knowledge on proposed reforms in the Land and Natural Resources sectors. It also promotes citizens’ participation in the natural resource sector. |
| Ambition Briefly describe the intended policy results of the commitment and how it will either make government more open or improve government through more openness. |  | The intended policy result of the commitment is that it will make the government more open by allowing the public to understand workings of the proposed reforms in the Land and Natural Resources sectors. |

| Completion Level | Not Started | Limited | Substantial | Completed |
| --- | --- | --- | --- | --- |
| Description of the results Include specific activities within the reporting period (first or second year of the action plan) and, wherever possible, please indicate whether there has been evidence of members of the public using the commitment or whether the commitment has had an effect. | The commitment has been completed. |  |  |  |
| End date | June 30, 2017 |  |  |  |
| Next steps | Towards next commitment |  |  |  |

| Commitment Completion Template |  |  |
| --- | --- | --- |
| Thematic Area 1: Transparency/ Commitment No. 5 |  |  |
| Lead implementing agency |  | National Bureau of Concession & LEITI |
| Name of responsible person from implementing agency |  | Atty. Ramses T. Kumbuyah & Hon. Myer W. Saye, Sr. |
| Title, Department |  | Deputy Director, Concession Deputy Head, Administration |
| Email |  | kumbuyahrt@gmail.com mwsaye@leiti.org.lr |
| Phone |  | +231-886848493 +231-886551558 |
| Other actors involved | Government | Forestry Development Authority, Ministry of Agriculture, National Investment Commission, Land Commission, MIA, Ministry of Justice, local tradition council |
|  | CSOs, private sector, working groups, multilaterals | LMC, CENTAL, CEMESP, concerned concession companies |
| Main Objective |  | The main objective is to ensure that material information on commercial land use rights is made publicly available. |
| Brief Description of Commitment (140 character limit) |  | The commitment seeks to ensure that the public is informed on proposed reforms in the Land and Natural Resources sectors thru broad stakeholders’ consultations in the counties to increase citizens’ understanding about issues of land and natural resources. |
| Relevance Briefly describe the way in which this commitment is relevant to further advancing OGP values of access to information, public accountability, civic participation, and technology and innovation for openness and accountability. (A detailed description of these values is available in the OGP Values Guidance Note.) |  | The commitment is relevant to further advancing OGP values of access to information, public accountability, civic participation, and technology and innovation for openness and accountability thru public knowledge on the proposed reforms in the Land and Natural Resources sectors. |
| Ambition Briefly describe the intended policy results of the commitment and how it will either make government more open or improve government through more openness. |  | The intended policy result of this commitment is to allow the public access to the process leading to the proposed reforms in the Land and Natural Resources sectors. This openness reduces negative perceptions about the process and emboldens public trust in the government’s reform efforts |

| Completion Level | Not Started | Limited | Substantial | Completed |
| --- | --- | --- | --- | --- |
| Description of the results Include specific activities within the reporting period (first or second year of the action plan) and, wherever possible, please indicate whether there has been evidence of members of the public using the commitment or whether the commitment has had an effect. | The commitment has been completed. |  |  |  |
| End date | June 30, 2017 |  |  |  |
| Next steps | Towards next commitment |  |  |  |

| Commitment Completion Template |  |  |
| --- | --- | --- |
| Thematic Area 1: Transparency/ Commitment No. 6 |  |  |
| Lead implementing agency |  | Ministry of Finance and Development Planning |
| Name of responsible person from implementing agency |  | Hon. Tanneh G. Brunson |
| Title, Department |  | Deputy Minister, Budget |
| Email |  | tbrunson@mfdp.gov.lr |
| Phone |  | +231-886236578 |
| Other actors involved | Government |  |
|  | CSOs, private sector, working groups, multilaterals | Development Gateway, Publish What You Fund, CEMESP |
| Main Objective |  | The main objective is to expand transparency of development assistance in Liberia through open data portal of aid activities and to encourage development partners to expand their own transparency by publishing timely, comprehensive, and disaggregated data on a quarterly basis in line with the International Aid Transparency Initiative (IATI) Standard. |
| Brief Description of Commitment (140 character limit) |  | The commitment seeks to ensure that Ministry of Finance and Development Planning work with development partners to make information accessible to users and develop programs for capacity building. Ensure public online access to Liberia’s Aid Management Platform and identify ways to improve accessibility, functionality and awareness of the platform. |
| Relevance Briefly describe the way in which this commitment is relevant to further advancing OGP values of access to information, public accountability, civic participation, and technology and innovation for openness and accountability. (A detailed description of these values is available in the OGP Values Guidance Note.) |  | The commitment is relevant to further advancing OGP values of access to information, public accountability, and technology and innovation for openness and accountability thru donors’ commitments to providing timely and comprehensive data on development assistance to the Government. |
| Ambition Briefly describe the intended policy results of the commitment and how it will either make government more open or improve government through more openness. |  | The intended policy result of the commitment is to enhance transparency in the performance of donors’ funding both on the government side and the donors’ side. |

| Completion Level | Not Started | Limited | Substantial | Completed |
| --- | --- | --- | --- | --- |
| Description of the results Include specific activities within the reporting period (first or second year of the action plan) and, wherever possible, please indicate whether there has been evidence of members of the public using the commitment or whether the commitment has had an effect. | The commitment has been completed. |  |  |  |
| End date | June 30, 2017 |  |  |  |
| Next steps | The next step is to roll out the Aid Management Platform to Development Partners, Ministries, Agencies and Commissions (MACs) and local government administrators. |  |  |  |
| Additional information - The system has been hacked and the data is being repopulated on the Aid Management Platform (AMP). |  |  |  |  |

| Commitment Completion Template |  |  |
| --- | --- | --- |
| Thematic Area 1: Transparency/ Commitment No. 7 |  |  |
| Lead implementing agency |  | Ministry of Finance and Development Planning |
| Name of responsible person from implementing agency |  | Hon. Tanneh G. Brunson |
| Title, Department |  | Deputy Minister, Budget |
| Email |  | tbrunson@mfdp.gov.lr |
| Phone |  | +231-886236578 |
| Other actors involved | Government |  |
|  | CSOs, private sector, working groups, multilaterals | CEMESP, CENTAL |
| Main Objective |  | The main objective is to strengthen development planning by identifying ways to link Liberia’s Financial Management System with the Aid Management Platform to monitor expenditures and plan more predictably over the medium-to long-term. |
| Brief Description of Commitment (140 character limit) |  | The commitment seeks to link the Aid Management Platform (AMP) and the Financial and Expenditure Management System. |
| Relevance Briefly describe the way in which this commitment is relevant to further advancing OGP values of access to information, public accountability, civic participation, and technology and innovation for openness and accountability. (A detailed description of these values is available in the OGP Values Guidance Note.) |  | The commitment is relevant to further advancing OGP values of access to information, public accountability, and technology and innovation for openness and accountability thru the tracking of information (eg. Budget Head Codes from the Chart of Account); alignment of Aid Management Platform and IFMIS data. |
| Ambition Briefly describe the intended policy results of the commitment and how it will either make government more open or improve government through more openness. |  | The intended policy result of the commitment is to improve government openness allowing donors and the public to monitor expenditures of the government to inform their discussions and feedbacks to their leaders on the budget. |

| Completion Level | Not Started | Limited | Substantial | Completed |
| --- | --- | --- | --- | --- |
| Description of the results Include specific activities within the reporting period (first or second year of the action plan) and, wherever possible, please indicate whether there has been evidence of members of the public using the commitment or whether the commitment has had an effect. | The commitment has had substantial effect. Liberia Aid Management Platform has been developed. |  |  |  |
| End date | June 30, 2017 |  |  |  |
| Next steps | The next step is to ensure public online access to Liberia’s Aid Management Platform. |  |  |  |
| Additional information (The AMP system has been hacked and currently the data is being repopulated.) |  |  |  |  |

| Commitment Completion Template |  |  |
| --- | --- | --- |
| Thematic Area 1: Transparency/ Commitment No. 8 |  |  |
| Lead implementing agency |  | Ministry of Health |
| Name of responsible person from implementing agency |  | Hon. Yah M. Zolia |
| Title, Department |  | Deputy Minister, Planning |
| Email |  | yzolia@yahoo.com |
| Phone |  | +231886516382 |
| Other actors involved | Government | LACC, Liberia Ebola Financial Tracking Group |
|  | CSOs, private sector, working groups, multilaterals | iLab Liberia, Accountability Lab |
| Main Objective |  | The main objective is to track EVD funds. |
| Brief Description of Commitment (140 character limit) |  | The commitment seeks to track financial resources spent and map financial resources committed or allocated from government and partners, including the private sector. Also to disseminate data and reports on Government websites, including the Open Data Portal. Management System. |
| Relevance Briefly describe the way in which this commitment is relevant to further advancing OGP values of access to information, public accountability, civic participation, and technology and innovation for openness and accountability. (A detailed description of these values is available in the OGP Values Guidance Note.) |  | The commitment is relevant to further advancing OGP values of access to information, public accountability, and technology and innovation for openness and accountability thru public awareness of EVD funds; including funding agency, project commitment and disbursement amounts. |
| Ambition Briefly describe the intended policy results of the commitment and how it will either make government more open or improve government through more openness. |  | The intended policy result of the commitment is to improve the government openness by allowing the public access to how EVD funding was expended. |

| Completion Level | Not Started |  | Limited |  | Substantial | Completed |
| --- | --- | --- | --- | --- | --- | --- |
| Description of the results Include specific activities within the reporting period (first or second year of the action plan) and, wherever possible, please indicate whether there has been evidence of members of the public using the commitment or whether the commitment has had an effect. | The commitment has been completed. |  |  |  |  |  |
| End date | June 30, 2017 |  |  |  |  |  |
| Next steps | Towards next commitment. |  |  |  |  |  |
| Additional information |  |  |  |  |  |  |
| Commitment Completion Template |  |  |  |  |  |  |
| Thematic Area 2: Citizen Participation/ Commitment No. 1 |  |  |  |  |  |  |
| Lead implementing agency |  |  |  | Judiciary |  |  |
| Name of responsible person from implementing agency |  |  |  | Cllr. George Katakpah |  |  |
| Title, Department |  |  |  | National Jury Manager, Central Office |  |  |
| Email |  |  |  | gkatakpah412@yahoo.com |  |  |
| Phone |  |  |  | +231-886512475 |  |  |
| Other actors involved |  | Government |  | MICAT, LACC, Governance Commission, MIA, MFDP |  |  |
|  |  | CSOs, private sector, working groups, multilaterals |  | UNMIL, PBF |  |  |
| Main Objective |  |  |  | The main objective is to implement the new jury law. |  |  |
| Brief Description of Commitment (140 character limit) |  |  |  | The commitment seeks to create awareness around the role of juries. Set up, recruit and train staff of the jury management central office and approved budget for the jury management office. |  |  |
| Relevance Briefly describe the way in which this commitment is relevant to further advancing OGP values of access to information, public accountability, civic participation, and technology and innovation for openness and accountability. (A detailed description of these values is available in the OGP Values Guidance Note.) |  |  |  | The commitment is relevant to further advancing OGP values of access to information, public accountability, and technology and innovation for openness and accountability thru public awareness about the roles of juries in the fifteen (15) political sub-divisions of Liberia. |  |  |
| Ambition Briefly describe the intended policy results of the commitment and how it will either make government more open or improve government through more openness. |  |  |  | The intended policy results of the commitment is to improve Liberia’s jury system by allowing the public to be abreast of the new jury law thus enhancing public engagement and feedback. |  |  |

| Completion Level | Not Started | Limited | Substantial | Completed |
| --- | --- | --- | --- | --- |
| Description of the results Include specific activities within the reporting period (first or second year of the action plan) and, wherever possible, please indicate whether there has been evidence of members of the public using the commitment or whether the commitment has had an effect. | The commitment has been completed. |  |  |  |
| End date | June 30, 2017 |  |  |  |
| Next steps | Towards next commitment. |  |  |  |
| Additional information |  |  |  |  |

| Commitment Completion Template |  |  |
| --- | --- | --- |
| Thematic Area 2: Citizen Participation/ Commitment No. 2 |  |  |
| Lead implementing agency |  | Judiciary |
| Name of responsible person from implementing agency |  | Cllr. George Katakpah |
| Title, Department |  | National Jury Manager, Central Office |
| Email |  | gkatakpah412@yahoo.com |
| Phone |  | +231-886512475 |
| Other actors involved | Government | MOJ |
|  | CSOs, private sector, working groups, multilaterals | UNMIL, JPC, CENTAL, CEMESP, LMC |
| Main Objective |  | The main objective is to allow citizen to monitor the workings of the justice system. |
| Brief Description of Commitment (140 character limit) |  | The commitment seeks to create awareness around the workings of judiciary by publishing the analysis of court returns. |
| Relevance Briefly describe the way in which this commitment is relevant to further advancing OGP values of access to information, public accountability, civic participation, and technology and innovation for openness and accountability. (A detailed description of these values is available in the OGP Values Guidance Note.) |  | The commitment is relevant to further advancing OGP values of access to information, public accountability, and technology and innovation for openness and accountability thru public awareness about the workings of the Judiciary in the fifteen (15) political sub-divisions of Liberia. |
| Ambition Briefly describe the intended policy results of the commitment and how it will either make government more open or improve government through more openness. |  | The intended policy results of the commitment is to enhance openness within the judiciary by allowing public access to court records particularly the quarterly of analysis of courts returns. |

| Completion Level | Not Started | Limited | Substantial | Completed |
| --- | --- | --- | --- | --- |
| Description of the results Include specific activities within the reporting period (first or second year of the action plan) and, wherever possible, please indicate whether there has been evidence of members of the public using the commitment or whether the commitment has had an effect. | The commitment has been completed. www.judiciary.gov.lr |  |  |  |
| End date | June 30, 2017 |  |  |  |
| Next steps | Towards next commitment |  |  |  |
| Additional information |  |  |  |  |

| Commitment Completion Template |  |  |
| --- | --- | --- |
| Thematic Area 2: Citizen Participation/ Commitment No. 3 |  |  |
| Lead implementing agency |  | Accountability Lab |
| Name of responsible person from implementing agency |  | Mr. Francis E. Lansana |
| Title, Department |  | Country Resident, Administration |
| Email |  | francis@accountabilitylab.org |
| Phone |  | +231-886156316 |
| Other actors involved | Government | MICAT, MIA, MOS, President’s office |
|  | CSOs, private sector, working groups, multilaterals | iLab |
| Main Objective |  | The main objective is to create civic education and citizen engagement around offline tools. |
| Brief Description of Commitment (140 character limit) |  | The commitment seeks to create tools for citizen outreach (interactive murals, citizen journalism, accountability film school, “conversation kekes”, “kick out corruption” programs and to gather annual perception survey of citizens on government accountability to strengthen the Civil Service Sectors. |
| Relevance Briefly describe the way in which this commitment is relevant to further advancing OGP values of access to information, public accountability, civic participation, and technology and innovation for openness and accountability. (A detailed description of these values is available in the OGP Values Guidance Note.) |  | The commitment is relevant to further advancing OGP values of access to information, public accountability, and technology and innovation for openness and accountability thru the civic education of citizen around offline tools. |
| Ambition Briefly describe the intended policy results of the commitment and how it will either make government more open or improve government through more openness. |  | The intended policy results of the commitment is that citizens’ participation in the fight against corruption will be further strengthened and public engagement will be deepened. |

| Completion Level | Not Started |  | Limited |  | Substantial | Completed |
| --- | --- | --- | --- | --- | --- | --- |
| Description of the results Include specific activities within the reporting period (first or second year of the action plan) and, wherever possible, please indicate whether there has been evidence of members of the public using the commitment or whether the commitment has had an effect. | The commitment has been completed. |  |  |  |  |  |
| End date | June 30, 2017 |  |  |  |  |  |
| Next steps | Towards next commitment. |  |  |  |  |  |
| Additional information |  |  |  |  |  |  |
| Commitment Completion Template |  |  |  |  |  |  |
| Thematic Area 2: Citizen Participation/ Commitment No. 4 |  |  |  |  |  |  |
| Lead implementing agency |  |  |  | Liberia National Police |  |  |
| Name of responsible person from implementing agency |  |  |  | Mr. Lewis Norman |  |  |
| Title, Department |  |  |  | Deputy Chief, Public Affairs |  |  |
| Email |  |  |  | normanlewis@gmail.com |  |  |
| Phone |  |  |  | +231-770800309 |  |  |
| Other actors involved |  | Government |  | MICAT, MIA, MOJ |  |  |
|  |  | CSOs, private sector, working groups, multilaterals |  | CENTAL, UNPOL, PUL, Community Watch Forum, TGCI |  |  |
| Main Objective |  |  |  | The main objective is to create public awareness under the theme “Know Your Rights” Policing Campaign/ Initiative |  |  |
| Brief Description of Commitment (140 character limit) |  |  |  | The commitment seeks to publish laws and protocols on enforcement powers, filing of complaints and whistle-blowing procedures and to promote citizens’ awareness of the existence, roles and actions of LNP Professional Standards Division as well as access to services of this division. |  |  |
| Relevance Briefly describe the way in which this commitment is relevant to further advancing OGP values of access to information, public accountability, civic participation, and technology and innovation for openness and accountability. (A detailed description of these values is available in the OGP Values Guidance Note.) |  |  |  | The commitment is relevant to further advancing OGP values of access to information, public accountability, and technology and innovation for openness and accountability thru the civic education of citizen around their rights as it relates to policing. |  |  |
| Ambition Briefly describe the intended policy results of the commitment and how it will either make government more open or improve government through more openness. |  |  |  | The intended policy results of the commitment is that improve public knowledge of relevant procedures by allowing the public to understand the roles and actions of the Liberia National Police, its laws and protocols. |  |  |

| Completion Level | Not Started | Limited | Substantial | Completed |
| --- | --- | --- | --- | --- |
| Description of the results Include specific activities within the reporting period (first or second year of the action plan) and, wherever possible, please indicate whether there has been evidence of members of the public using the commitment or whether the commitment has had an effect. | The commitment has been completed. www.lnp.gov.lr |  |  |  |
| End date | June 30, 2017 |  |  |  |
| Next steps | Towards next commitment. |  |  |  |
| Additional information |  |  |  |  |

| Commitment Completion Template |  |  |
| --- | --- | --- |
| Thematic Area 3: Accountability and Integrity/ Commitment No. 1 |  |  |
| Lead implementing agency |  | Governance Commission & Liberia Anti-Corruption Commission |
| Name of responsible person from implementing agency |  | Ms. Janet Johnson Mr. James Kingsley |
| Title, Department |  | Director, Communication Administrative Assistant, Administration |
| Email |  | jprudencej@yahoo.com jkingsley@lacc.gov.lr |
| Phone |  | +231-886553335 +231-886527326 |
| Other actors involved | Government | Law Reform Commission, National Integrity Forum, National Legislature, MICAT |
|  | CSOs, private sector, working groups, multilaterals | CENTAL, CUPPADL, CEMESP |
| Main Objective |  | The main objective is to ensure the passage of the Whistleblower Protection Act |
| Brief Description of Commitment (140 character limit) |  | The commitment seeks to ensure that the Whistleblower Protection Act is passed; in order to provide protection for whistleblowers across Liberia, and undertake awareness raising on citizens’ understanding of the act. |
| Relevance Briefly describe the way in which this commitment is relevant to further advancing OGP values of access to information, public accountability, civic participation, and technology and innovation for openness and accountability. (A detailed description of these values is available in the OGP Values Guidance Note.) |  | The commitment is relevant to further advancing OGP values of access to information, public accountability, and citizens’ participation thru the civic education of citizens around the Whistleblower Protection Act and their rights as it relates to reporting acts that are harmful towards the progress of Liberia. |
| Ambition Briefly describe the intended policy results of the commitment and how it will either make government more open or improve government through more openness. |  | The intended policy results of the commitment is to strengthen the fight against corruption by providing protection for those in the public who would like to report acts of corruption, misconducts, etc. |

| Completion Level | Not Started |  | Limited |  | Substantial | Completed |
| --- | --- | --- | --- | --- | --- | --- |
| Description of the results Include specific activities within the reporting period (first or second year of the action plan) and, wherever possible, please indicate whether there has been evidence of members of the public using the commitment or whether the commitment has had an effect. | The commitment has had limited effect. It is before the Legislature. |  |  |  |  |  |
| End date | June 30, 2017 |  |  |  |  |  |
| Next steps | The next step is to ensure the passage of the Whistleblower Protection Act. |  |  |  |  |  |
| Additional information (The challenge to implementing the commitment is limited ability to lobby for the passage of this bill coupled with lack of political will on the part of the legislature.) |  |  |  |  |  |  |
| Commitment Completion Template |  |  |  |  |  |  |
| Thematic Area 3: Accountability and Integrity/ Commitment No. 2 |  |  |  |  |  |  |
| Lead implementing agency |  |  |  | Accountability Lab |  |  |
| Name of responsible person from implementing agency |  |  |  | Mr. Francis E. Lansana |  |  |
| Title, Department |  |  |  | Country Resident, Administration |  |  |
| Email |  |  |  | francis@accountabilitylab.org |  |  |
| Phone |  |  |  | +231-886156316 |  |  |
| Other actors involved |  | Government |  | MICAT, Governance Commission, MIA, LACC |  |  |
|  |  | CSOs, private sector, working groups, multilaterals |  | CENTAL, OSIWA, Medica Mondiale, GAA |  |  |
| Main Objective |  |  |  | The main objective is to bring together accountability organizations. |  |  |
| Brief Description of Commitment (140 character limit) |  |  |  | The commitment seeks to build a community for accountability organizations through the creation of an OpenGov Hub in Monrovia, a co-working and community space for all accountability organizations in Liberia. |  |  |
| Relevance Briefly describe the way in which this commitment is relevant to further advancing OGP values of access to information, public accountability, civic participation, and technology and innovation for openness and accountability. (A detailed description of these values is available in the OGP Values Guidance Note.) |  |  |  | The commitment is relevant to further advancing OGP values of access to information, public accountability, and citizens’ participation thru the creation of the Open Government Hub for accountability organizations in Liberia. |  |  |
| Ambition Briefly describe the intended policy results of the commitment and how it will either make government more open or improve government through more openness. |  |  |  | The intended policy result of the commitment is to improve and strengthen coordination among accountability organizations. |  |  |

| Completion Level | Not Started | Limited | Substantial | Completed |
| --- | --- | --- | --- | --- |
| Description of the results Include specific activities within the reporting period (first or second year of the action plan) and, wherever possible, please indicate whether there has been evidence of members of the public using the commitment or whether the commitment has had an effect. | The commitment has been completed. |  |  |  |
| End date | June 30, 2017 |  |  |  |
| Next steps | Towards next commitment. |  |  |  |
| Additional information |  |  |  |  |

| Commitment Completion Template |  |  |
| --- | --- | --- |
| Thematic Area 3: Accountability and Integrity/ Commitment No. 3 |  |  |
| Lead implementing agency |  | Accountability Lab |
| Name of responsible person from implementing agency |  | Mr. Francis E. Lansana |
| Title, Department |  | Country Resident, Administration |
| Email |  | francis@accountabilitylab.org |
| Phone |  | +231-886156316 |
| Other actors involved | Government | MICAT, Governance Commission, LIPA, National Integrity Forum |
|  | CSOs, private sector, working groups, multilaterals |  |
| Main Objective |  | The main objective is to improve integrity within the government systems. |
| Brief Description of Commitment (140 character limit) |  | The commitment seeks to train at least 20 middle, junior and senior levels government officials on building a culture of integrity and promote a network of reformers within the government sectors. Creation of an innovation fund (US$2,500 - US$5,000) for small, creative ideas for integrity with the Government of Liberia. |
| Relevance Briefly describe the way in which this commitment is relevant to further advancing OGP values of access to information, public accountability, civic participation, and technology and innovation for openness and accountability. (A detailed description of these values is available in the OGP Values Guidance Note.) |  | The commitment is relevant to further advancing OGP values of access to information, and public accountability thru the demonstration of integrity and reforms of officials trained which would serve as guidance for those untrained. |
| Ambition Briefly describe the intended policy results of the commitment and how it will either make government more open or improve government through more openness. |  | The intended policy result of the commitment is to build a network of reformers within the government who will support each other thus enhancing integrity across government. |

| Completion Level | Not Started | Limited | Substantial | Completed |
| --- | --- | --- | --- | --- |
| Description of the results Include specific activities within the reporting period (first or second year of the action plan) and, wherever possible, please indicate whether there has been evidence of members of the public using the commitment or whether the commitment has had an effect. | The commitment has had substantial effect. Twenty (20) middle and junior levels government officials (PYPPs) were trained on issues of integrity. |  |  |  |
| End date | June 30, 2017 |  |  |  |
| Next steps | The next step is to create a network that would ensure that those trained build and promote a culture of integrity within the various government sectors that they work. By extension, the giving of the innovation funds is also a next step. |  |  |  |
| Additional information (The challenge to implementing the commitment is funding to among other things cover the Innovative Funds.) |  |  |  |  |

| Commitment Completion Template |  |  |
| --- | --- | --- |
| Thematic Area 4: Technology and Innovation/ Commitment No. 1 |  |  |
| Lead implementing agency |  | iLab Liberia |
| Name of responsible person from implementing agency |  | Mr. Carter Draper |
| Title, Department |  | Program Director, Adm. |
| Email |  | carter@ilabliberia.org |
| Phone |  | +231-770003983 |
| Other actors involved | Government | MICAT, MFDP, LISGIS, MOPT, MIA |
|  | CSOs, private sector, working groups, multilaterals | CENTAL, GSM companies, All local/community radio stations |
| Main Objective |  | The main objective is to gather citizens’ feedback on national development outcomes. |
| Brief Description of Commitment (140 character limit) |  | The commitment seeks to build an online/SMS platform for receiving and gathering the public feedback on any national issues. |
| Relevance Briefly describe the way in which this commitment is relevant to further advancing OGP values of access to information, public accountability, civic participation, and technology and innovation for openness and accountability. (A detailed description of these values is available in the OGP Values Guidance Note.) |  | The commitment is relevant to further advancing OGP values of access to information, public accountability, citizen participation, and technology and innovation thru the creation of the online platform. |
| Ambition Briefly describe the intended policy results of the commitment and how it will either make government more open or improve government through more openness. |  | The intended policy result of the commitment is to enhance openness by strengthening citizens’ participation in the governance process through the creation of citizens’ feedback. |

| Completion Level | Not Started | Limited | Substantial | Completed |
| --- | --- | --- | --- | --- |
| Description of the results Include specific activities within the reporting period (first or second year of the action plan) and, wherever possible, please indicate whether there has been evidence of members of the public using the commitment or whether the commitment has had an effect. | This commitment has not been completed due to financial constraint. |  |  |  |
| End date | June 30, 2017 |  |  |  |
| Next steps | The next step is to source funding to set up the SMS platform and carry out awareness rising about the platform and ensure that it is fully and conveniently utilized. |  |  |  |
| Additional information (This commitment currently lacks funding for implementation) |  |  |  |  |

| Commitment Completion Template |  |  |
| --- | --- | --- |
| Thematic Area 4: Technology and Innovation/ Commitment No. 2 |  |  |
| Lead implementing agency |  | MOPT, Accountability Lab, & iLab Liberia |
| Name of responsible person from implementing agency |  | Dr. Darren Wilkins Mr. Francis E. Lansana Mr. Carter Draper |
| Title, Department |  | Project Manager, Adm. Country Resident, Adm. Program Director, Adm. |
| Email |  | dwilkins@wilkinssystems.com francis@accountabilitylab.org carter@ilabliberia.org |
| Phone |  | +231-886703789 +231-886156316 +231-770003983 |
| Other actors involved | Government | MICAT, LTA |
|  | CSOs, private sector, working groups, multilaterals | Liberia Media Center, IBM |
| Main Objective |  | The main objective is to improve GoL’s online provision of information. |
| Brief Description of Commitment (140 character limit) |  | The commitment seeks to standardize government websites with “gov.lr standards and policies”, train requisite staff for updates and maintenance. Develop “Knowmore LIB” open data and citizen navigation system. |
| Relevance Briefly describe the way in which this commitment is relevant to further advancing OGP values of access to information, public accountability, civic participation, and technology and innovation for openness and accountability. (A detailed description of these values is available in the OGP Values Guidance Note.) |  | The commitment is relevant to further advancing OGP values of access to information, public accountability, citizen participation, and technology and innovation thru the standardization of government website and the “Knowmore LIB” open data development. |
| Ambition Briefly describe the intended policy results of the commitment and how it will either make government more open or improve government through more openness. |  | The intended policy results of the commitment is to standardize government’s websites thus providing unconfused access to the public. This would also improve access to information. |

| Completion Level | Not Started | Limited | Substantial | Completed |
| --- | --- | --- | --- | --- |
| Description of the results Include specific activities within the reporting period (first or second year of the action plan) and, wherever possible, please indicate whether there has been evidence of members of the public using the commitment or whether the commitment has had an effect. | The commitment has had a limited effect. 45 government ministries, agencies and commissions have the “gov.lr standards. |  |  |  |
| End date | June 30, 2017 |  |  |  |
| Next steps | The next step is to develop Knowmore LIB open data and citizen navigation system and to ensure all remaining government websites have the “gov.lr standards”. |  |  |  |
| Additional information (The challenge to implementing the commitment is funding.) |  |  |  |  |

| Commitment Completion Template |  |  |
| --- | --- | --- |
| Thematic Area 4: Technology and Innovation/ Commitment No. 3 |  |  |
| Lead implementing agency |  | Ministry of Finance and Development Planning |
| Name of responsible person from implementing agency |  | Hon. Tanneh G. Brunson |
| Title, Department |  | Deputy Minister, Budget |
| Email |  | tbrunson@mfdp.gov.lr |
| Phone |  | +231-886236578 |
| Other actors involved | Government |  |
|  | CSOs, private sector, working groups, multilaterals | Liberia Media Center, CEMESP, CUPPADL, CENTAL |
| Main Objective |  | The main objective is to expand the Integration of Financial Management Systems (IFMIS) to make the provision of public financial information easier. |
| Brief Description of Commitment (140 character limit) |  | The commitment seeks to extend coverage of IFMIS to additional 17 Ministries and Agencies and provide functional or technical support (hardware and software to 19 MACs), share publicly financial data and create awareness on the IFMIS program. |
| Relevance Briefly describe the way in which this commitment is relevant to further advancing OGP values of access to information, public accountability, civic participation, and technology and innovation for openness and accountability. (A detailed description of these values is available in the OGP Values Guidance Note.) |  | The commitment is relevant to further advancing OGP values of access to information, public accountability, citizen participation, and technology and innovation thru the publication of financial data so that those data can be shared for public consumption. |
| Ambition Briefly describe the intended policy results of the commitment and how it will either make government more open or improve government through more openness. |  | The intended policy result of the commitment is to promote openness in the government’s financial management system by allowing public access to financial data. |

| Completion Level | Not Started | Limited | Substantial | Completed |
| --- | --- | --- | --- | --- |
| Description of the results Include specific activities within the reporting period (first or second year of the action plan) and, wherever possible, please indicate whether there has been evidence of members of the public using the commitment or whether the commitment has had an effect. | The commitment has been completed. |  |  |  |
| End date | June 30, 2017 |  |  |  |
| Next steps | Towards next commitment. |  |  |  |
| Additional information (32 additional MACs have been integrated on the IFMIS and four counties have been integrated to use the system; namely Nimba, Margibi, Grand Bassa and Bomi.) |  |  |  |  |

| Commitment Completion Template |  |  |
| --- | --- | --- |
| Thematic Area 4: Technology and Innovation/ Commitment No. 4 |  |  |
| Lead implementing agency |  | Liberia National Police |
| Name of responsible person from implementing agency |  | Mr. Lewis Norman |
| Title, Department |  | Deputy Chief, Public Affairs |
| Email |  | normanlewis@gmail.com |
| Phone |  | +231-770800309 |
| Other actors involved | Government | MICAT, MOPT, LISGIS |
|  | CSOs, private sector, working groups, multilaterals | CENTAL, iLab Liberia, UNPOL |
| Main Objective |  | The main objective is to digitize community policing. |
| Brief Description of Commitment (140 character limit) |  | The commitment seeks to create online crime/policing maps with visualization options and interactivity. Link the platform up with the Liberia National Police official website when constructed; and put current police nationwide data to this platform. |
| Relevance Briefly describe the way in which this commitment is relevant to further advancing OGP values of access to information, public accountability, civic participation, and technology and innovation for openness and accountability. (A detailed description of these values is available in the OGP Values Guidance Note.) |  | The commitment is relevant to further advancing OGP values of access to information, public accountability, citizen participation, and technology and innovation thru the creation of the crime/policing maps for public consumption. |
| Ambition Briefly describe the intended policy results of the commitment and how it will either make government more open or improve government through more openness. |  | The intended policy result of the commitment is to enhance citizens’ access to nationwide crime statistics. |

| Completion Level | Not Started | Limited | Substantial | Completed |
| --- | --- | --- | --- | --- |
| Description of the results Include specific activities within the reporting period (first or second year of the action plan) and, wherever possible, please indicate whether there has been evidence of members of the public using the commitment or whether the commitment has had an effect. | The commitment has had limited effect. Hard copies of crime/policing maps and information about community policing are available at the Liberia National Police Headquarters. |  |  |  |
| End date | June 30, 2017 |  |  |  |
| Next steps | The next step is to publish these statistics and maps when the open data platform established and launched. |  |  |  |
| Additional information (N/A) |  |  |  |  |

| Commitment Completion Template |  |  |
| --- | --- | --- |
| Thematic Area 4: Technology and Innovation/ Commitment No. 5 |  |  |
| Lead implementing agency |  | iLab Liberia, & MOPT |
| Name of responsible person from implementing agency |  | Mr. Carter Draper Dr. Darren Wilkins |
| Title, Department |  | Program Director, Adm. Project Director, Adm. |
| Email |  | carter@ilabliberia.org dwilkins@wilkinssystems.com |
| Phone |  | +231-770003983 +231-886703789 |
| Other actors involved | Government | MICAT, MFDP, MOS |
|  | CSOs, private sector, working groups, multilaterals | CENTAL, Accountability Lab, IBM |
| Main Objective |  | The main objective is to establish and launch an Open Data portal. |
| Brief Description of Commitment (140 character limit) |  | The commitment seeks to create a portal which will provides public access to all relevant information on Liberia. |
| Relevance Briefly describe the way in which this commitment is relevant to further advancing OGP values of access to information, public accountability, civic participation, and technology and innovation for openness and accountability. (A detailed description of these values is available in the OGP Values Guidance Note.) |  | The commitment is relevant to further advancing OGP values of access to information, public accountability, citizen participation, and technology and innovation thru the creation of the Open Data portal that would be used by the public to access all relevant information on Liberia. |
| Ambition Briefly describe the intended policy results of the commitment and how it will either make government more open or improve government through more openness. |  | The intended policy result of this commitment is to increase access to information through the proactive disclosure of information to the public by using an open data platform. |

| Completion Level | Not Started | Limited | Substantial | Completed |
| --- | --- | --- | --- | --- |
| Description of the results Include specific activities within the reporting period (first or second year of the action plan) and, wherever possible, please indicate whether there has been evidence of members of the public using the commitment or whether the commitment has had an effect. | The commitment has had limited effect. Liberia Open Data portal prototype had been created. |  |  |  |
| End date | June 30, 2017 |  |  |  |
| Next steps | The next step is to fully complete the establishment of the Open Data portal. |  |  |  |
| Additional information (N/A) |  |  |  |  |

- Progress on Eligibility Criteria (optional)

Liberia has voluntarily taken steps to improve her performance on the OGP criteria as part of the NAP. Those actions are:

- Formulation of the first year action plan. Lesson learnt was lack of consultation which was used during the formulation of the second year action plan. 20 commitments  was outlined in the second action plan of which 10 commitments were completed with results, while out of the remaining 10 commitments, 5 were substantially completed, 4 were limited in terms of results and 1 was not started due to funding constraints.

- Creation of transparency institutions such as: the Liberia Anti-Corruption Commission, Public Procurement and Concession Commission, and the Internal Audit Secretariat now Internal Audit Agency (IAA). The outcome of formulating these institutions is that, they have increased transparency and accountability in the public sectors.

- Therefore, the National Action Plan achievements would be measure up to75% of the total commitments.

- Peer Exchange and Learning (if applicable)

During the period, one of the major challenges has been the lacked of funding which has impeded the peer exchange and learning.

- Conclusion, other initiatives and Next Steps

- Lessons learned:

Developing a National Action Plan entails lots of energy as the process of consultation with many sectors involves lots of processes ranging from government ministries, agencies & commissions, civil society organizations, community leaders, business sector and other ordinary citizens. It also involved harmonizing of multiple ideas across all sectors.

The following were the lessons learned;

- Alignments of responsible and strategic partners – pairing of CSOs and government to deliver on a mile stone as set in the NAP required more strategic planning and coordination;

- Monitoring and coordination - making sure those responsible parties are following up with their commitments entails more time, efforts and resources.

- Maintaining CSOs energy level - accomplishing those commitments in the NAP requires time, effort and courage especially when CSOs are not getting direct funding from OGP to support any initiatives.

- Cabinet full support - getting public officials full cooperation for the implementation of the commitments within NAP required more efforts and continuous follow up than previously thought.

- Institutionalization of OGP - establishing an OGP implementation support unit to coordinate and support implementation of commitments is taking longer than previously anticipated.

- Other initiatives (optional)

Other initiatives or reform undertaken by Liberia to advance the Open Government Partnership values that were not included in the National Action Plan are as follows:

- Public Procurement Concession Commission (PPCC), publication of all procurement processes on line which was never previously done.  It is a huge transparency bonus that OGP should take credit for.

- The empowerment of 15 Public Information Officers with 15 internet gadgets to timely respond to citizens concern.

- Next steps

Achieving all of the milestones set in the NAP required total commitments from all parties, hence, the steering committee has plan to do the following;

- Conduct more awareness in the cabinet;

- Collect milestones report and verify same;

- Encourage CSOs to get more pro-active and adapt some milestone into their daily activities;

- Get the government to give more support and institutionalize OGP

- (establish the OGP support unit).

- Identify funding support for CSOs to enhance their capacities to adequately accomplish the milestones;

- Re-enforce the implementation of next commitments in the 2017-2019 NAP;

- Conclusion

Through the positive intervention of these commitments, the government has been able to create the space to enhance transparency, citizen participation, accountability, technology and innovation in Liberia.