INTERIM ANNUAL REPORT – SELF-ASSESSMENT OF THE IMPLEMENTATION OF THE ACTION PLAN ON

IMPLEMENTATION OF THE OPEN GOVERNMENT PARTNERSHIP INITIATIVE IN THE REPUBLIC OF SERBIA IN 2016 AND 2017

Belgrade, October 2017

1. INTRODUCTION

The Republic of Serbia has been a member of the Open Government Partnership – OGP since 2012, when it submitted a letter of intent to join this initiative, and obliged itself to develop an action plan and compliance with the open government principle contained in the OGP Declaration. This initiative started in 2011 and is aimed at supporting the participating countries in building open, transparent and accountable administration, oriented towards citizens, and its basic values are: access to information, civic participation, public accountability and technology and innovation for openness and accountability. The Open Government Partnership has 75 member states.

As a participant in the Open Government Partnership, the Republic of Serbia considers that this is a good way to implement the overall goal of the public administration reform in the Republic of Serbia which implies providing high-quality services to citizens and corporate entities and creating a public administration which will considerably contribute to the economic stability and increase the standard of living. The principles on which this initiative is based are fully in line with Government’s determination to build government based on the general principles of “good governance“ and “open government“, that is, to ensure the full implementation of generally accepted principles of the rule of law and legal security, publicity, accountability, and efficiency.

The development and implementation of the action plan is the most important element of country’s participation in the Open Government Partnership, considering that the country expresses its commitment to the core values of the Partnership through this, taking on ambitious and specific commitments that significantly improve the existing situation within these values.

Since it became a member, Serbia prepared and adopted 3 action plans for 2013, 2014 and 2016, while for the action plan adopted in 2013 was stated that it needs to be improved, hence, it was not officially presented to the OGP initiative. Accordingly, drafting of the Action Plan for Implementation of the Open Government Partnership in the Republic of Serbia in 2016 and 2017 (hereinafter referred to as the “Action Plan“) is considered to be second cycle.

The Government adopted the Action Plan on November 17, 2016 by Conclusion No. 021-10793/2016 (“Official Gazette of the RS“ No. 93/16 of 18 November 2016). The Ministry of Public Administration and Local Self-Government (hereinafter: MPALSG) is authorised by the Government to undertake activities within the framework of RS participation in the OGP initiative.

Commitments undertaken with the adoption of the Action Plan involve specific activities that will contribute to the improvement of the situation in the following existing areas: Civic Participation, Access to Information, Open Data, Government Integrity, Fiscal Transparency and Public Services.

2. ACTION PLAN PREPARATION PROCESS

2a. Participation and collaboration throughout the OGP cycle

In this second cycle of the Action Plan preparation, the Republic of Serbia has made a significant progress in all the stages of its preparation. The overall implementation of the Open Government Partnership Initiative was raised to a higher level, the level of awareness of state authorities related to this initiative was also raised, and cooperation with civil society significantly improved, which is one of the main principles of open government. Inter alia, the experience gained during the preparation of the first action plan contributed to this, as well as implementation of recommendation of the Independent Reporting Mechanism (hereinafter: IRM), established at the level of this international initiative, from the IRM Progress Report relating to the first action plan. These recommendations mostly referred to the improvement of the action plan preparation process, involvement of all stakeholders and improvement of the consultative process.

The MPALSG published on its website all information, documents and public calls for OGP implementation, whereas the Centre for Research, Transparency and Accountability – CRTA created website OGP.rs where all relevant information may also be found, as well as OGP accounts on social networks like Facebook and Twitter which are suited for the promotion of this initiative. For the purpose of website updating, the MPALSG regularly submits to the CRTA all relevant information. The information about the institution responsible for the OGP implementation and about the focal point is publicly available. The Office for Cooperation with Civil Society (hereinafter referred to as: OCCS) publishes on its website all public calls to stakeholders and all supporting documents, and sends direct invitations to civil society organisations (hereinafter referred to as: CSO) on its mailing list. The public is, this way, able to follow all the activities conducted in the OGP cycle, from the beginning of participation of the Republic of Serbia in the OGP initiative. All relevant information is published for stakeholders in advance to ensure a period of preparation for participation in all the stages of implementation of the OGP initiative.

The second cycle of the Action Plan preparation included establishment of the Special Interdepartmental Working Group for the preparation of the second Action Plan from 2016 to 2017, and for participation of the Republic of Serbia in the OGP initiative (hereinafter referred to as: the Working Group), with a task to implement all the activities related to the entire OGP cycle. In addition to the representatives of state bodies, members of the Working Group are also representatives of the CSO, special organisations, government services, independent state bodies, the National Assembly and the Serbian Chamber of Commerce. The Working Group met regularly during the preparation of the Action Plan (5 meetings, and 4 additional consultative meetings – roundtables with a wider civil sector and 1 roundtable related to the monitoring of the implementation of the Action Plan, whereas additional communication was done via e-mail.

As part of the promotion of the OGP initiative and public consultations, members of the Working Group, representatives of state bodies and CSO attended meetings – roundtables in several self-government units (hereinafter referred to as: SGU) outside of Belgrade, where, in addition to informing the public about this initiative, the Draft Action Plan was considered as well as the possibilities of participation of SGUs and CSOs located outside the capital city. For more information on all activities, see 2b of this section.

During the period in which the Action Plan was prepared, Serbia hosted a regional meeting of Western Balkans OGP Focal Points, which was held from 26-27 May 2016, in Belgrade. The participants presented draft action plans of the countries from the region and, inter alia, discussed individual commitments, possibilities for their improvement, possible solutions to identified issues, and the form of action plans; tools and models of civil society engagement; examples of “commitments marked with an asterisk” which were presented by the representatives of the OGP Support Unit; and the concept of open data, which was presented by a representative of the Web Foundation. In addition to better understanding of the situation in the region with regards to the implementation of the OGP initiative, the regional exchange of experiences also allowed the participants to compare the action plans in terms of openness of administration and ambition of envisaged commitments and to improve the quality of their respective action plans. The participants also noted it would be opportune to consider a possible modification of the schedule of activities under the OGP initiative, since the current time schedule requires countries to adopt their action plan every two years in June, whereas the countries of the region would consider it more acceptable if the timeframe were moved forward to January, so the implementation of the commitments matches the adoption of national budgets.

At the OGP Global Summit held in December 2016 in Paris, Serbia presented one of its commitments from the Action Plan, as part of the short presentations session. This commitment 6 from the Action Plan refers to the access to information, i.e. to the reformatting of the Information Booklet, and its implementation shall, inter alia, significantly contribute to the better provision of information to citizens through timely publication of information in an open format, and improve the availability of data, which will make the work of the public administration more transparent and accountable, and promote participation of citizens and their impact on the work of the public administration. Successful presentation of this commitment was achieved in close cooperation and with a significant help of civil society organisations CRTA and BOS which, with the support of the United Nations Development Program (hereinafter referred to as: UNDP) made two visual presentations – video clips, for the purpose of successful presentation, which significantly contributed to the understanding of the problem being solved with the implementation of this commitment, and envisaged solution: What is the Information booklet, Open Information Booklets for an Open Society, Transparency Builds Trust.

In order to inform the general public about commitments undertaken in the implementation of the OGP initiative, CRTA made several visual presentations of the commitments from the Action Plan, along with clear and understandable explanations of problems and envisaged solutions.

In order to further raise awareness of civil servants on the principles and values of the OGP initiative, OGP training was introduced in the Republic of Serbia as part of the General Program of Continuous Professional Development of Civil Servants in 2017.

2b. Participation and collaboration during the preparation of the Action Plan

The Action Plan preparation process officially began in January 2016 with the formation of the Working Group. Representatives of CSOs were appointed members of the Working Group in a transparent procedure: in OCCS, in cooperation with the MPALSG, published a public call for participation in the work of the Working Group, in November 2015, and also sent it to all CSOs on its mailing list. In addition to all information relevant for prospective applicants, the public call also stated the criteria for the selection of a CSO and for the appointment of CSO representatives as members and deputy members of the Working Group. These criteria reflected an intention to involve in the work of the Working Group and preparation of the Action Plan CSOs active in various fields promoted by OGP values, including: access to data, access to information of public importance, media and information, fiscal transparency, public advocacy and policies, strengthening the rule of law and raising civic awareness, combating corruption, development of new technologies and innovation in order to exchange information, improve public services and involve citizens in decision-making, open data, and Open Government Partnership, another requirement was that COSs must have demonstrated their interest in a specific field in the past three years. In accordance with IRM recommendations, the public call was sent to CSOs active across the Republic of Serbia, to ensure that CSOs which operate outside of the capital city are also represented.

Once the final date for application has passed, the selection procedure had been completed and the period of raising complaints had expired, a Committee consisting of representatives of the OCCS and MPALSG made a final decision on the appointment of COS members and deputy members to the Working Group. The public call, all relevant documents, ranking lists and Commission’s final decision are available on the OCCS’s website.

All the representative of CSOs that met conditions and criteria from the Public Call were invited as members of the Working Group, or their deputies, to participate in its work (Belgrade Open School – BOS, Centre for Research, Transparency and Accountability  – CRTA, Civic Initiatives, Union of ICT Societies of Serbia– JISA, Local Democracy Centre, Association of Business Women in Serbia).

In addition to CSO representatives, members of the Working Group included representatives of the MPALSG, the e-Government Directorate, the Ministry of Finance, the Ministry of Justice, the Ministry of Foreign Affairs, the Ministry of Internal Affairs, the Ministry of Education, Science and Technological Development, the Ministry of Trade, Tourism and Telecommunication, the Anti-Corruption Agency, the Serbian European Integration Office, the Republic Secretariat for Public Policies, OCCS, the Public Procurement Office, the Government’s General Secretariat, the National Assembly of the Republic of Serbia and the Serbian Chamber of Commerce – in order to include the private sector, in accordance with IRM recommendations.

In addition to the members of the Working Group, work of the Working Group and preparation of the Action Plan also involved active participation of representatives of the UNDP and the Standing Conference of Towns and Municipalities (hereinafter: SCTM) as a direct connection with the local self-government.

The Working Group held its first meeting on 8 February 2015, in which all the members were familiarised with basic OGP values and principles, agreed on modes of cooperation, structure and steps for the preparation of the AP, as well as on the schedule of activities. In the period from February to September 2016, the Working Group held a total of five meetings during which proposals for commitments submitted by CSO representatives were considered.

In compliance with IRM recommendations, to involve the public in the entire process of preparation of the Action Plan and deciding on Action Plan priorities and content, members of the Working Group held a consultative meeting/roundtable with all interested COSs before compiling a working draft of the Action Plan. In addition to setting priorities, the objective of this meeting was to collect ideas, suggestions and specific proposals for commitments that will be included in the Action Plan. This manner enabled the public to get involved in the Action Plan preparation from the very beginning and, thus, influence its content as much as possible.

For purpose of ensuring a wider consultation process and as part of the preparation for this meeting, the MPALSG sent a public call, together with the OCCS, to the CSOs from the entire territory of Serbia, which was posted on the websites of the MPALSG, and the OCCS, and was also distributed to all recipients on the OCCS’s CSO mailing list. In addition to the public call, the Guidelines on OGP values, Instruction for the preparation of the Action Plan, IRM recommendations, Work Program, commitment forms, and forms for the submission of CSO written proposals were also published next to the public call.

The meeting was attended by 40 representatives of CSOs. After providing comprehensive information to all the participants about the OGP initiative, schedule and manner of preparation and structure of action plans, it was agreed that the participants break into working groups which will define commitment proposals related to the following topics: Civic Participation, Access to Information, Open Data, Government Integrity, Fiscal Transparency and Public Services. A total of twenty-two commitments proposals were collected as a result of collaboration of members of the Working Group and CSO representatives.

After the meeting, the Report and conclusions from the consultative meeting containing all the proposals presented on the meeting were published on the same websites.

All proposals made by CSOs were reviewed at Working Group’s meetings. Certain commitment proposals were also reviewed at individual meetings with competent state authorities, which also were attended by CSO representatives. Most of the proposals were included in the Action Plan, while some were found to be unfeasible within the framework of this action plan, and an explanation was provided. All proposals, relevant information, conclusions and explanations, in case of the omitting of certain proposals from the Action Plan, were published in the Minutes of all meetings of the Working Group, on MPALSG’s website and at www.ogp.rs to allow all stakeholders to follow up on the Group’s work. The minutes also include all written proposals received from CSOs within the specified timeframe, with relevant explanations in case of those proposals that have not been incorporated in the Action Plan.

The commitments set out in this Action Plan are borne fully out of collaboration between competent authorities and COSs.

In accordance with the rules of the OGP initiative, a working draft of the Action Plan was made publicly available on 15 July 2016, two weeks before the commencement of public consultations. A public call for the participation of CSOs from the entire territory of Serbia was posted on the websites of the MPALSG and OCCS, on the ePortal, and at www.ogp.rs. The OCCS also sent notifications to all CSOs on its mailing list. Public consultations were held from 1 to 22 August 2016.

In accordance with IRM recommendations, public consultations on the wording of the Draft Action Plan included three consultative meetings with CSOs held on 5 August 2016 in Belgrade, on 9 August 2016 in Novi Sad, and on 19 August 2016 in Niš. The Public Call for CSOs was repeated before each meeting and information on the agenda of each meeting was provided on the websites mentioned above. The meetings were attended by more than 150 participants, including representatives of CSOs, state administration, local self-governments, and Autonomous Province, they also included members of the Working Group on Preparation of the Draft Action Plan. In addition to collecting suggestions and proposals for improving the wording of the Action Plan, these meeting were mostly dedicated to the promotion of the OGP initiative, for connecting better with CSOs outside the capital city and representatives of local self-government units with OGP values and possibilities to engage. Meetings in Novi Sad and Niš were organised through full collaboration between the MPALSG and TASCO Resource Centre of Civic Initiatives, while the meeting in Belgrade was organised in collaboration between the MPALSG and OCCS. By contributing their comments and suggestions, the participants helped improve the working draft of the Action Plan. The Report on conducted public consultations is available on the websites of the MPALSG and OCCS and at www.ogp.rs.

2c. Participation and collaboration in the implementation and monitoring of the Action Plan

In terms of monitoring the implementation of the Action Plan, improvement was made in the second cycle, if compared to the previous cycle. After four months of implementation of the Action Plan, an interim operating report was created in April 2017 on the progress in the implementation of commitment from the Action Plan to which contribution was made by all the relevant authorities competent for the execution of commitments. The report was submitted to all members of the Working Group to inspect the situation related to the execution of these commitments.

The Report on the implementation of the Action Plan for first 6 months of 2017 was made in June 2017, and published on MPALSG and OCCS websites, as well as at www.ogp.rs. The Report contains information on the progress and reasons of delay, and next steps. In order to increase participation of interested civil society organisations in the process of monitoring the implementation of the Action Plan, the MPALSG published the Public Call to CSOs on the same websites, in cooperation with the OCCS and Civic Initiatives, to participate in a consultative meeting held on 27 June 2017, where this report was presented. In addition to the members of the Working Group, the meeting was attended by about 10 representatives of CSOs. Members of the Working Group, representatives of Civic Initiatives, OCCS, the Public Policy Secretariat, General Secretariat of the Government, and e-Government Directorate, MPALSG and Ministry of Trade, Tourism and Telecommunications, presented the situation related to the implementation of the commitments stated in the Action Plan for which they are competent. In accordance with OGP rules, the Report and Public Call for the meeting were published two weeks in advance, for timely preparation of all the participants.

In addition to creating the report, several activities were held in the period of implementation of the Action Plan, aimed at promoting the OGP initiative, apart from reporting on conducted activities from the Action Plan, with a focus on the local level. The MPALSG established great cooperation during these activities with civil society organisations through organising joint events aimed at informing local communities and improving the open government mechanism at the local level.

One of such events is Conferenced Open Government Partnership in Serbia at the local level held on 15 December 2016 in Aranđelovac, organised by the CRTA, with the support of the OSCE Mission in Serbia. The conference was used for presenting the adopted Action Plan, achieved results and review of good practice and importance of cooperation between institutions and civil society. Special part of the conference was dedicated to the discussion about various experiences and examples of good practice related to open government at the local level. One of conclusions was that the openness of local self-governments will contribute to the better quality of services and more efficient work of municipalities and institutions. The event was attended by the representatives of local self-government of the city of Kragujevac, municipalities of Aranđelovac, Lučani, Batočina, Knić, Lapovo, Rača and Topola, as well as head of Šumadija and Moravica districts.

TACSO Resource Centre of Civic Initiatives organised a meeting with the representatives of local self-government units and civil society organisations in Subotica, in March 2017, with the aim to present the adopted Action Plan and achieved results, and to consider the possibility of creating informal coalitions within the OGP at the local level, which could, in the future, monitor the implementation of the Action Plan and compliance with the OGP principle. The meeting was attended by the representatives of local self-government and civil society organisations from Subotica, Sombor, Apatin, Senta, Kikinda, Kanjiža, Bačka Topola and Novi Kneževac.

The second meeting of such nature was held in May 2017, also hosted by the TACSO Resource Centre of Civic Initiatives, which was attended by the representatives of local self-government and civil society organisations from the Zaječar district.

In addition, having in mind that public administration is the closest to the citizens at the local level, CRTA started an initiative, with the support of the OSCE Mission in Serbia, to promote the OGP initiative at the local level, and initiate a dialogue between civil society and public administration in order to encourage activities that represent an answer to the real needs of the citizens, which is one of the main goals of the OGP. Also, the goal is to create a basis for local contribution and engagement of local self-governments in creating action plans together with civil society. The initiative involves over 25 local self-governments though five regional workshops, as well as relevant civil society organisations at the local level. One of the results of the initiative was the Model of Local Action Plan of the OGP, and the plan was to develop and customise action plans in four selected local self-government units. The model of the local action plan of the OGP shall enable to local self-governments to better plan the implementation of the OGP principles and their adaptation to the needs of the local community, thus improving the framework for public participation in decision-making, transparency of local institutions and the quality of public services. The workshops were held on 29 June 2017 in Vranje, on 7 July 2017 in Užice, on 20 September 2017 in Zrenjanin, on 5 October 2017 in Šabac, and on 12 October 2017 in Kragujevac. All the activities related to the promotion of the OGP in Serbia were conducted by the CRTA, in close cooperation with and support of the MPALSG.

In terms of the implementation of commitment 6 from the Action Plan – Improving Proactive Transparency – Information Booklet, which refers to the amendment of the method of data entry and publication of the Information Booklet of public authorities, the MPALSG initiated a process of support, in partnership and with the support of the UNDP, for several local self-government units (Novi Sad, Niš, Leskovac, Vranje, Novi Pazar, Zrenjanin, Pančevo, Bečej, Šabac, Užice,  Loznica) through which these LSGUs would obtain support of the consultants in the field of information technologies, as well as advisory assistance for the application of new electronic application for the entry of the Information Booklet, including preparation and processing of data. At the same time, interested CSOs from the selected LSGUs attended the training for work with open data and for the development of specific applications based on LSGU data, which would contribute to the quality of life of their fellow citizens, more efficient services and easier communication with the citizens. An interactive workshop was held as part of this process on 5 July 2017, in Belgrade, which was attended by the representatives of selected LSGUs which had a chance to get familiar with the OGP initiative, Action Plan and new application for the entry of the Information Booklet, as well as with great benefits of open data for local development. A workshop for CSO representatives was held in the period from 16 to 18 June 2017, in Belgrade.

3. RECOMMENDATIONS OF THE INDEPENDENT REPORTING MECHANISM- IRM

The IRM was established at the level of the global OGP initiative with the aim to monitor and report on all stages of the development and implementation of national action plans and the fulfilment of the OGP principle. In all progress reports, the IRM makes recommendations for improving processes and activities within the state’s participation in the OGP initiative.

The Republic of Serbia received IRM recommendations as part of the Progress Report relating to the first action plan for 2014 and 2015. The recommendations mainly referred to the improvement of the action plan preparation process, engagement of all stakeholders, and improvement of the consultative process.

In accordance with these recommendations and owing to the gained experience from the first cycle of the OGP, the overall implementation of the OGP initiative was raised to a higher level in the second cycle. The previous sections provide a detailed overview of activities of preparation and monitoring of the Action Plan, which were conducted in accordance with the IRM recommendations. Inter alia, the most significant improvement was achieved in the area of cooperation with civil society, the consultative process was significantly improved, and efforts were made to raise awareness about the values of the OGP and participation of the Republic of Serbia in this initiative, both at the national and local level. Close cooperation with CSOs was also achieved, which were actively engaged throughout the OGP cycle and provided significant and specific support in the implementation and monitoring of the implementation of assumed commitments.

3. OVERVIEW OF COMMITMENTS

The Action Plan defined 14 commitments, which envisage steps for their implementation, with clearly defined deadlines and competent institutions. The report was prepared on the basis of individual reports of state authorities responsible for the implementation of certain commitments. The report covers the implementation period from November 2016 to 30 August 2017, and shows the current situation in the implementation of the assumed commitments.

Chart 1: Overview of the implementation level of the activities envisaged by the OGP Action Plan

Until the completion of this report, out of a total of 14 commitments, only one commitment was completed, seven of them were significantly implemented, and six commitments were partially implemented.

Chart 2: Overview of the relationship of institutions responsible for the implementation of activities defined in the OGP Action Plan

Chart 3: Overview of the implementation level of activities of the competent institutions

А. CIVIC PARTICIPATION

| COMMITMENT 1: Develop a model of job description or part of job description of an officer responsible for cooperation with civil society in local administration |
| --- |
| Period – Commitment Start and End Date Q4 2016 – Q4 2017 (October 2016 – December 2017) |
| Lead implementing agency | Ministry of Public Administration and Local Self-Government, Department of Local Self-Government (MPALSG) |
| Description of Commitment |
| Problem addressed by the commitment | As part of development of the Strategy for an Enabling Environment for Civil Society Development in the Republic of Serbia for the Period 2016-2020, a survey of cooperation between LSGUs and CSOs in the process of enactment of regulations was conducted in 122 municipalities in 2015. The results of this survey showed that, out of the total number of enactments adopted in 2014 (11,000 enactments, including budgets, strategic development plans, decisions, zoning plans, statutes etc.), only 3% had been subject to public hearings. Furthermore, those municipalities that did hold such public hearings, tended to involve CSOs in those hearings usually in the drafting stage, rather than in the follow-up on implementation and application. According to the available figures, the existence of a CSO liaison unit has positive effects both in terms of the number of public hearings held and in terms of involvement of CSOs in those public hearings. The average number of received comments, comments taken into consideration and accepted comments was higher in those municipalities that had designated a CSO liaison officer/body; those municipalities were also more likely to directly inform CSOs of public hearings they had held compared with the LSGUs which lack such officer/body. The results of this survey show there is a clear need for a post if this type in the job classification documents of LSGUs, i.e. a post whose duties would, inter alia, include liaison with CSOs, based on a previously developed job description model for such a post. |
| Main objective | Prepare and submit a model job description, or part of a job description for a post in charge of civil society liaison for all LSGUs in the Republic of Serbia. The model job description should include a description of duties and a designation of job complexity and responsibility, with recommended civil service title, required level and type of education, qualifications and skills. To increase the number of LSGUs with a civil society liaison post in their job classification rules to improve cooperation between public administration bodies and the civil society and improve and develop mechanisms of cooperation between public administration and CSOs. |
| How will this commitment contribute to problem solving? | An open and democratic society is based on a constant dialogue between citizens, various social groups and sectors. While public administration bodies and a wide range of civil society organisations often have different roles, their common goal – improving the quality of life for citizens – can be achieved only on the basis of trust and mutual respect. In this context, it is necessary to develop methods and mechanisms of cooperation at all levels of their engagement, to the extent necessary for achieving their common goal. Development of the said model job description for civil sector liaison officers at LSGU level and its acceptance by or adaptation to the needs of each local -self-government and subsequent inclusion of this position in the staff of local self-governments should contribute to more active cooperation between LSGUs and civil society organisations, build mutual trust and foster greater openness and accountability of public administration bodies. |
| The way in which this commitment is relevant to further advancing OGP values | The Public Administration Reform Strategy in the Republic of Serbia (Official Gazette of RS Nos. 9/14 and 42/14) highlights a need to improve the principles, standards and measures of cooperation between national and other authorities and organisations with CSOs in the making of decisions which pertain to issues of common interest and stands on matters of common interest. The core principles underlying the involvement of CSOs in the drafting, passing and follow-up of regulations are set out in the Guidelines on Inclusion of Civil Society Organisations in the Process of Passing Regulations (Official Gazette of RS No. 90/14) are in line with the core OGP principles: openness and accountability of public administration and active engagement with citizens in all stages of the legislative process. The Guidelines contain recommendations for compliance with these principles by LSGUs and advise public administration bodies to appoint civil society liaison officers with the knowledge and skills required for these duties. In this context, this commitment, in particular adoption of the proposed model job by LSGUs, will contribute to improved cooperation and greater engagement with citizens in the formulation and implementation of public policies. Defining of a job description for civil society liaison officers will contribute to implementation of the core OGP principles by those LSGUs that opt for this model. |
| Additional information (optional) |  |
| Implementation level | Not started | Partially implemented | Significantly implemented | Completed |
|  |  |  | X |  |
| Description of results | At the beginning of November 2016, SCTM prepared and published to Models of Rules of Procedure on internal organisation and job classification in the government(s), professional services and special organisations in towns and municipalities in cooperation with the MPALSG, in order to provide normative support to LSGUs in the implementation of the new Law on Employees in AP and LSGU. The models of the Rules of Procedure covers internal organisation of administration, professional services and special organisations with job descriptions and employment conditions in them, recommended vocations and all other elements that are necessary in accordance with the Law on Employees in AP and LSGU. When preparing these Models, special attention was paid to the development of job description for a post that involves cooperation with civil society. When preparing job description for this post, and during its finalisation, in addition to local experts (mostly heads of administrations) who were involved in the drafting of the Model of the Rules of Procedure, the Office for Cooperation with Civil Society was also consulted, whose comments and proposals were incorporated in the final wording of the Rules of Procedure. The Model of the Rules of Procedure was published on OCCS’s website and sent electronically to the addresses of all heads of administrations in Serbia. Unfortunately, currently there are no data that would serve as a a starting point in terms of the number of LSGU that had a dedicated post for cooperation with CSOs. By the end of 2017, the SCTM will collect data on the number of LSGU that envisaged the post for cooperation with civil society, as well as the number of LSGU that took up the proposed job description, on a sample of 80 LSGU (including city municipalities). This will facilitate future monitoring of the increase in these posts. |
| Next steps | Establish systems and procedures for the follow up on the increase in the number of public administration bodies with a dedicated post for cooperation with CSOs, i.e. they classified these jobs as part of one or more posts Establish a system of keeping records on the number of public administration bodies with a dedicated post for cooperation with CSOs, i.e. they classified these jobs as part of one or more posts. |
| Activity Status | Start Date: | End Date: | Completion Rate |
| 1. Development of a model job description | (October 2016) | Q4 2016 | Fully completed (100%) |
| 2. Presentation of the model job description to all LSGUs | Q1 2017 (January 2017) | Q1 2017 (February 2017) | Fully completed (100%) |
| 3. Follow up on the increase in the number of public administration bodies with a dedicated post for cooperation with CSOs | Q2 2017 (April 2017) | Q4 2017 (December 2017) | In progress |
| Contact |
| Lead implementing agency | Ministry of Public Administration and Local Self-Government, Department of Local Self-Government (MPALSG) SCTM |
| Name of a responsible person in the implementing agency | Saša Mogić, MPALSG Marko Tomašević, SCTM |
| Title, Department | Assistant Minister, Department of Local Self-Government, MPALSG Head of Unit for the Political System of Local Self-Governments at the SCTM Secretariat |
| Email and phone number | sasa.mogic@mduls.gov.rs marko.tomasevic@skgo.org 011 3060-113 011 3223 446 |
| Other actors involved | Administration | Office for Cooperation with the Civil Society LSGU |
|  | Civil sector organisations, private sector, working groups | Civic Initiatives |
| Additional Information |

| COMMITMENT 2: Organise trainings for public administration officers in connection with the application of the Guidelines on Inclusion of Civil Society Organisations in the Process of Passing Regulations |
| --- |
| Period – Start Date and End Date Q4 2016 – Q4 2017 (December 2016 – December 2017) |
| Lead implementing agency | Office for Cooperation with the Civil Society |
| Description of Commitment |
| Problem addressed by the commitment | In 2015 we conducted the “Initial Survey for the Purpose of Drafting the First Strategy for an Enabling Environment for Civil Society Development in the Republic of Serbia for the Period 2015–2019”. The data collected cover the period from 1 January to 31 December 2014. The first part included data relating to cooperation between state administration and CSOs, based solely on information obtained from state administration bodies. Based on the survey results, out of the 32 public administration bodies which participated in the survey, although invitations had been sent to 42 state administration bodies, only 11 state administration bodies reported they had held public hearings in 2014 in the process of passing regulations. According to the available data, out of the total number of regulations passed in 2014 (351), only one in ten were subject to a public hearing (37 regulations in total, or 10.5%). Furthermore, a minority of the surveyed state administration bodies formed working groups tasked with drafting regulations in the course of last year. Generally, the only CSOs that are invited to participate in this form of cooperation are those that are recognised by the authorities as relevant for various reasons. Furthermore, public calls for CSOs to apply for membership in working groups are relatively rare (such calls were made only in respect of eight working groups of the 38 formed in 2014). The second part of the survey includes data on cooperation between LSGUs and CSOs, which included 122 LSGUs, or 75% of all LSGUs in the Republic of Serbia. The results of this survey have shown that, out of the total number of instruments passed in 2014 (11,000 instruments - budgets, strategic development plans, decisions, zoning plans. Statutes etc.), only 3% had undergone any kind of public hearing. In addition, those LSGUs that did hold public hearings usually involved CSOs in the public hearings during the drafting stage, but not during the follow-up and implementation stages. In 2015, the Office for Cooperation with the Civil Society collaborated with the TACSO project in Serbia to organise 10 two-day training events for representatives of LSGUs on the issues of transparent financing of civil society organisations and importance of cooperation with CSOs. The recommendations set out in the reports from these trainings are indicative of a need for additional training of public administration officers about improved cooperation and possible cooperation mechanisms and models, especially with regard to involvement in the process of planning and allocation of funding. |
| Main objective | Plans have been made for up to 5 training events for representatives of public administration bodies that would address the importance and potential modalities of cooperation with CSOs in the process of developing, adopting and monitoring of the application of regulations. The trainings will be organised in collaboration with the Human Resource Management Service and other relevant partners. The minimum planned number of participants is 20, including officers in charge of drafting regulations, as well as officers in charge of financing and cooperation with CSOs. The main objective is to improve capacities of public administration bodies to establish sustainable models and mechanisms of cooperation with CSOs when developing and implementing public policies. Improvement of practice in the implementation of already established mechanisms and levels of cooperation between the public and civil sector by the public administration should contribute to the involvement of the citizens in the preparation and implementation of regulation, and ensure increased efficiency of work of public administration bodies, reduction of costs, and optimisation of the work of agencies, i.e. a total increase in capacities, knowledge and skills of employees in public administration bodies. |
| How will this commitment contribute to problem solving? | Conducting the training for public administration officers regarding cooperation with CSOs will raise the level of their knowledge, first of all, of possible modalities and models of cooperation with CSOs, and of the importance of this cooperation, expertise and experience with which CSOs may contribute in the process of the preparation, adoption and monitoring of the implementation of regulations. Getting familiar with legal regulations, internationally established principles and models of cooperation, as well as with the examples of good practice will set good foundation for the greater involvement of CSOs and citizens, and generally greater public participation in the legislative process. Creating an adequate Training Program (activity No. 1) which defines key elements (objectives, topics and program of work of the target group, training schedule, agenda, etc.) represent an important starting point for conducting further activities within the commitment. The main activity (activity No. 2), i.e. organising trainings and their execution, will directly target problems that the commitment deals with. Specifically, through one-day training, the employees in state administration bodies and local self-government units will obtain necessary information relevant for the improvement of cooperation with CSOs, and they will do practical exercises in which they will be able to apply the knowledge obtained in the theoretical part of the training. Upon completion of training, the participants will have a clearer idea on the importance, possibilities and benefits of greater public involvement in the process of preparation, adoption and monitoring of the implementation of regulations. Reports on completed trainings (activity No. 3) will contain data on the number of training participants, covered topics, key observations and achievements. The report will also contain recommendations for further activities related to the building of capacities of public administration bodies with civil society organisations. |
| Why is the commitment relevant compared to OGP values | By increasing the capacities of public administration bodies for the application of the Guidelines on Inclusion of Civil Society Organisations in the Process of Passing Regulations, we will contribute to better understanding of the role and importance of CSOs and improved cooperation between public administration bodies and CSOs. Better understanding of cooperation and building CSO capacities will contribute to their larger involvement in the work of the public administration and preparation of good-quality regulations, on one hand, and greater transparency and accountability in the work of the authorities, on the other hand. The commitment is relevant in terms of participation of citizens in the preparation, adoption and monitoring of the application of regulations, considering that the building of capacities of public administration bodies for understanding the role, potential and possible models of cooperation with CSOs will increase their readiness and openness for cooperation with the civil sector and citizens in general. |
| Additional information (optional) | The commitment of organising trainings for public administration officers regarding the topic of involvement of CSOs in the process of passing regulations is related to the activities within the scope of measure 5.1. of the Action Plan for the Implementation of the Public Administration Reform Strategy of the Republic of Serbia for the period 2015-2017, which aims to ensure that CSOs and citizens are involved in the process of preparation, implementation and monitoring of public policies at the national and local level. The commitment is also recognised in the action plan that is an integral part of the Proposal for the strategy for creating an enabling environment for civil society development in the RS for period 2017-2020. Since the activities requiring execution of the commitment fall into regular activities of the Office for Cooperation with Civil Society that is responsible for the commitment, no special funds in the RS budget were earmarked for its implementation. |
| Implementation level | Not started | Partially implemented | Significantly implemented | Completed |
|  |  |  | X |  |
| Description of results | In the observed reporting period, the commitment was executed in accordance with set deadlines determined in the Action Plan. The drafting of the Training Program was followed by the realisation of trainings. The Training Program envisages 3 (three) trainings for the employees in public administration bodies, i.e. 2 (two) for the employees in local self-government units, and 1 (one) for the employees in public administration bodies. At the moment of submission of this report, two trainings were conducted for the employees in local self-government units, which were planned with the Training Program. Trainings were held in Niš and Novi Sad, and attended by 39 employers out of a total of 24 local self-government units and city municipalities. First indicators in the form of evaluation forms and created report on completed trainings show a high level of satisfaction of participants, and also a progress in understanding the importance of involvement of CSOs and the public in regulation preparation. The report was published on the website of the Office for Cooperation with Civil Society of the Government of the RS at https://goo.gl/qSn76t and will be an integral part of the final Report on completed trainings, which is envisaged as activity No. 3 within this commitment. The training designed for the employees in public administration bodies, which will be conducted in cooperation with the Human Resource Management Service of the Government of the RS, will be conducted by the end of the current year. |
| Next steps | The next step in the execution of the commitment is training of the employees in public administration bodies that should be conducted by the end of 2017, in accordance with the Program for general continuous professional development of civil servants for the current year of the Human Resource Management Service of the Government of the RS, which is a partner in the execution of the commitment. |
| Activity Status | Start Date: | End Date: | Completion Rate |
| 1. Preparation of the Training Program | Q1 2017 (March 2017) | Q2 2017 (April 2017) | Completed |
| 2. Organisation of training events | Q2 2017 (April 2017) |  | In progress |
| 3. Compiling a Report on Completed Trainings with recommendations for further improvement of the collaboration process | Q3 2017 (August 2017) |  | In progress |
| Contact |
| Lead implementing agency | Office for Cooperation with the Civil Society |
| Name of a responsible person in the implementing agency | Milena Banović |
| Title, Department | Head of Division for Planning and Creating an Enabling Environment for Civil Society Development |
| Email and phone number | milena.banovic@civilnodrustvo.gov.rs , 011/311-38-95 |
| Other actors involved | Administration | Human Resource Management Service |
|  | Civil sector organisations, private sector, working groups | Civil society organisations |
| Additional information |

| COMMITMENT 3: Organise trainings for CSO in connection with application of the Guidelines on Inclusion of Civil Society Organisations in the Process of Passing Regulations |
| --- |
| Period – Commitment Start and End Date Q4 2016 – Q4 2017 (December 2016 – December 2017) |
| Lead implementing agency | Office for Cooperation with the Civil Society |
| Description of Commitment |
| Problem addressed by this commitment | The consultative process which preceded the drafting of the Strategy for an Enabling Environment for Civil Society Development included 10 consultative meetings that were held in 10 cities across Serbia and were attended by 433 participants, who gave their suggestions and proposals in connection with the proposed measures and activities included in the Strategy. According to the Report on the Consultative Process, CSO representatives were very actively involved in the discussion and highlighted the issue of insufficient knowledge of applicable legislation, including, in particular, secondary legislation which sets out the powers and functioning arrangements of state administration bodies. The overall conclusion was therefore that provisions should be made for activities that would inform and educate CSOs, with a view to increasing their capacities in connection with the institutional and legal framework for cooperation between public authorities and the civil society. As part of the project “Creating an Enabling Environment for Civil Society Development” implemented by the Office with USAID support, an assessment was made of the capacities and needs of CSOs for the purpose of developing a long-term training plan to increase CSO capacities, which is implemented by the Office within its remit. The findings presented in the Office’s Strategic Framework for Increasing the Capacities of CSOs in the Period 2016-2018 point to a need for improved dialogue between civil and public sectors. In this context, we have recognised a need to improve the capacities of public and private sector actors and, to that end, a need for trainings that would increase the capacity of CSOs for cooperation with public administration institutions and involvement in the legislative process. |
| Main objective | The plan is to collaborate with Civic Initiatives to make a public call for interested CSOs and hold 4 training events for CSO representatives in connection with the application of the Guidelines on Inclusion of Civil Society Organisations in the Process of Passing Regulations in several cities in the Republic of Serbia. Minimum 30 representatives of CSOs are expected to undergo this training. General objective of trainings is improved capacities of CSOs for cooperation with public administration institutions and involvement in the process of preparation, adoption and monitoring of regulations. Improved capacity of CSOs to cooperate with public administration bodies will lead to more effective use of the already established cooperation mechanisms and thus contribute to greater and sounder civic participation in the drafting and implementation of regulations and public policies, which in turn will increase the quality of newly-passed regulations and contribute to their effective implementation. |
| How will this commitment contribute to problem solving? | Implementation of trainings for CSOs regarding cooperation with public administration bodies will be raised to the level of their understanding of possibilities to get involved in the process of preparation, adoption and monitoring of the implementation of regulations. Familiarisation with legal regulations, internationally established principles and models of cooperation, as well as with the examples of good practice through the execution of trainings will set good foundations for the greater involvement of CSOs and citizens, and generally greater public participation in the legislative process. This is particularly important due to the low level of familiarity with legal regulations, especially by-laws referring to the competencies and functioning of public administration bodies (which is presented in the description of the problem which the commitment deals with) and it is particularly visible at the local level. Creating an adequate Training Program (activity No. 1) which defines key elements (objectives, target groups, training schedule, agenda, etc.) represents an important starting point for conducting further activities within the commitment. The main activity (activity No. 2), i.e. organising trainings and their execution, will directly treat the problem that the commitment deals with. Specifically, through one-day training, CSO representatives will obtain necessary information relevant for the improvement of cooperation with public administration bodies and will do practical exercises in which they will be able to apply the knowledge acquired in the theoretical part of the training. Upon completion of the training, the participants will have a clearer idea on the importance, possibilities and benefits of their involvement in the process of preparation, adoption and monitoring of the implementation of regulations, as a manner of influence on the decision-making process. Reports on conducted trainings (activity No. 3) will show CSOs interests in the topic and, consequently, in cooperation with public administration bodies, and through the evaluation forms and “knowledge quizzes“, which will show first effects of the trainings. |
| The way in which this commitment is relevant to further advancing OGP values | The commitment is relevant in relation to citizens’ participation in the preparation, adoption and monitoring of the implementation of regulations as a value promoted and encouraged by the Open Government Partnership. By building CSOs capacities as citizens’ association for the implementation of the Guidelines for the involvement of civil society organisations in the process of passing regulations, which is the ultimate goal of this commitment, CSOs and, through them, citizens, will be able to thoroughly inform themselves about models and principles of their participation in the decision-making process. Better understanding of legal and other possibilities for cooperation with public administration bodies will contribute to a greater interest and involvement of CSOs in their work and preparation of good-quality regulations, on one hand, i.e. greater transparency and responsibility in the work of public administration bodies, on the other hand. |
| Additional information (optional) | The commitment of organising trainings for CSPs regarding the topic of their involvement in the process of passing regulations is connected with the activities within measure 5.1. of the Action Plan for the Implementation of the Public Administration Reform Strategy of the Republic of Serbia for period 2015-2017, which aims to ensure that CSOs and citizens are involved in the process of preparation, implementation and monitoring of public policies at the national and local level. Also, the obligation is also recognised in the action plan that is an integral part of the Proposal of the strategy for creating an enabling environment for civil society development in the RS for period 2017-2020. Since the activities requiring the execution of the commitment fall into regular activities of the Office for Cooperation with Civil Society that is responsible for the commitment, no special funds in the RS budget were earmarked for its implementation. |
| Implementation level | Not started | Partially implemented | Significantly implemented | Completed |
|  |  | X |  |  |
| Description of results | In the observed reporting period, the commitment was executed in accordance with set deadlines determined by the Action Plan. A partnership agreement was reached with the TASCO Resource Centre of Civic Initiatives which are envisaged by the Action Plan as partners with the Office in the implementation of activities within the commitment. The 4 (four) planned trainings will be held in Šabac, Kruševac, Subotica and Belgrade by the end of October 2017, which is in accordance with the schedule of implementation of this activity in the Action Plan. |
| Next steps | The next step in the implementation of this commitment is execution of 4 (four) trainings for CSO representatives operating at the local level, which will be selected through public calls for each of the trainings, and announced by the Office, in cooperation with Civic Initiatives. A report on the implementation of trainings will be created after their completion, which will be an integral part of the final Report on conducted trainings, which is envisaged as activity No. 3 within this commitment. The report will be published on the website of the Office for Cooperation with the Civil Society. |
| Activity Status | Start Date: | End Date: | Completion Rate |
| 1. Preparation of the Training Programme | Q1 2017 (March 2017) | Q2 2017 (April 2017) | Completed |
| 2. Organisation of training events | Q4 2017 (October 2017) | Q4 2017 (October 2017) | In progress |
| 3. Compiling a Report on Completed Trainings with recommendations for further improvement of the collaboration process | Q4 2017 (1 November 2017) | Q4 2017 (20 November 2017) | November 2017 |
| Contact |
| Lead implementing agency | Office for Cooperation with the Civil Society |
| Name of a responsible person in the implementing agency | Milena Banović |
| Title, Department | Head of Division for Planning and Creating an Enabling Environment for Civil Society Development |
| Email and phone number | milena.banovic@civilnodrustvo.gov.rs , 011/311-38-95 |
| Other actors involved | Administration |  |
|  | Civil sector organisations, private sector, working groups | Civic Initiatives, Civil society organisations |
| Additional information |

| COMMITMENT 4: Improve the system for collecting initiatives from citizens and businesses |
| --- |
| Period – Commitment Start and End Date In progress – Q2 2017 |
| Lead implementing agency | Republic Secretariat for Public Policies |
| Description of Commitment |
| Problem addressed by the commitment | Decision-makers often tend to propose, draft and pass regulations without consulting the stakeholders whose behaviour they seek to codify. In doing so, they miss the opportunity to collect meaningful information on the subject matter they seek to codify, fail to address or do not fully address the practical issues they encounter and sometimes pass inadequate provisions which are not based on a sound analysis of potential effects and available options for addressing those issues. In order to improve the role of citizens and businesses in decision-making, different models should be provided for the participation of citizens and businesses in the decision-making process. |
| Main objective | Implementation of this commitment will improve the role of citizens and businesses in the public policy management system and in the passing of regulations. This commitment will require the installation of appropriate online software and provision of functionalities on the website of the Republic Secretariat for Public Policies (RPPS) through better, faster and easier access of citizens and businesses to the content of RPPS’s website. There are also plans to establish a Forum for Initiatives for Amendment of Inefficient Regulations in the Legislative Process. This system would enable citizens and businesses to submit initiatives to amend any existing regulations or initiatives to pass new regulations. For this system to be able to function properly, it will be necessary to build the capacities of the RPPS staff in charge of these duties. |
| How will this commitment contribute to problem solving? | The implementation of this commitment will contribute to the establishment of an interactive electronic portal for collecting initiatives from citizens and businesses, and to the establishment of a Forum for initiatives for amendment of ineffective regulations and improvement of the legislative procedure, and also development of (internal) procedures for collecting and processing initiatives from citizens and businesses. This will enable the submission of initiatives on the RPPS website for the amendment of poor regulations and for the repeal of unnecessary ones, as well as follow-up on those initiatives, and access to information on submitted initiatives and case progress. |
| Why is this commitment relevant compared to OGP values | This commitment allows for broader civic participation in decision-making and contributed to improved cooperation and more active involvement of citizens in the process of drafting and passing of regulations. |
| Additional information (optional) | Funds for the execution of this commitment are provided in the budget of the Republic of Serbia within available funds. Connection with other related government programs This commitment is seen as a priority in the Regulatory Reform Strategy and improvement of the public policy management system for period 2016-2020 Connection with sustainable development goals |
| Implementation level | Not started | Partially implemented | Significantly implemented | Completed |
|  |  |  |  | Х |
| Description of results | So far, a total of 17 initiatives was received via this portal, and three of them were successfully resolved (https://adminhack.yrpri.org/community/557 ) |
| Next steps | The following period involves working on the continuous improvement of the Forum (by 1 November 2017, it will be possible to access the platform for the submission of initiatives for changes, and simplify administrative procedures; by December 2017, the forum will be set up for a certain number of areas, depending on which reforms have been implemented) |
| Activity Status | Start Date: | End Date: | Completion Rate |
| 1. Establishment of an interactive electronic portal for collecting initiatives from citizens and businesses | Q1 (March 2017) | Q1 (March 2017) | Fully completed |
| 2. Establishment of a Forum for initiatives for amendment of ineffective regulations and improvement of the legislative procedure | Q1 (March 2017) | Q1 2017 is part of the e-portal for collecting initiatives from citizens and businesses | Fully completed |
| 3. Development of (internal) procedures for collecting and processing initiatives from citizens and businesses | Q1 2017 (January 2017) | September 2017 | Fully completed |
| Contact |
| Lead implementing agency | Public Policy Secretariat of the Republic of Serbia |
| Name of a responsible person in the implementing agency | Ninoslav Kekić |
| Title, Department | Acting Director, Sector for the Quality Assurance of Public Policies |
| Email and phone number | ninoslav.kekic@rsjp.gov.rs 3349-818 |
| Other actors involved | Administration | Ministry of Public Administration and Local Self-Government – eGovernment Directorate, Ministry of Economy |
|  | Civil sector organisations, private sector, working groups |  |
| Additional information |

B. ACCESS TO INFORMATION

| COMMITMENT 5: Introducing standards for civic participation in the - |
| --- |
| Period – Commitment Start and End Date In progress – 30 June 2017 |
| Lead implementing agency | Public Policy Secretariat of the Republic of Serbia |
| Description of Commitment |
| Problem addressed by the commitment | One of the key reasons why certain unenforceable public policy documents exist is that mechanisms for participation of stakeholders and target groups affected by those public policies are limited and unevenly applied. Serbia’s legal system does not incorporate arrangements for stakeholder consultation and rules for their implementation in the drafting of public policy documents. Furthermore, the process of passing of public policy documents is often non-transparent, i.e. the public is frequently unaware of the fact that a public policy is being drafted, which is why inputs by institutions and citizens whose expertise (based on previously conducted analyses and studies) could contribute to the quality of public policy documents remain unavailable to state administration bodies. |
| Main objective | The key aspect of this commitment is to provide for consultations, i.e. to impose a duty on state administration bodies to hold consultations when drafting proposals of public policy documents. A legal framework should be put in place to define the consultation process, set out the criteria for determining the appropriate type and scope of consultations, specify the criteria for choosing representative members of the public and the business community who are knowledgeable on the subject matter and could take part in the consultations and provide for a duty to make public calls for participation of stakeholders and target groups. Another important form of civic participation in the decision-making process is public hearing. It is necessary to set out methodological rules for the conduct of public hearings, standardise the public hearing process and ensure appropriate participation of stakeholders and target groups in the process of passing of public policy documents. |
| How will this commitment contribute to problem solving? | This commitment will result in provisions which will impose a duty to hold consultations in the process of drafting proposals of public policy documents and will bind state administration bodies to announce the drafting of any public policy document on the eGovernment portal and on their website. Furthermore, methodological rules for consultations and public hearings in the process of drafting and passing public policy documents would be put in place. |
| Why is the commitment relevant compared to OGP values | This commitment will enable broader civic participation in decision-making and greater transparency of public administration. Enactment of the relevant law and regulation will impose a duty to hold consultations and public hearings in the process of drafting proposals of public policy documents. |
| Additional information (optional) | Funds for the execution of this commitment are provided in the budget of the Republic of Serbia Connection with other government programs The commitment is related to the Action Plan for implementation of the Public Administration Reform Strategy, Action Plan for the implementation of the Public Administration Reform Strategy in the Republic of Serbia for the period 2015-2017 (Special objective 1: Improving organisational and functional public administration sub-systems, measure 1.3. Improving the public policy management system of the Government by establishing the legal and institutional framework for integrated strategic management and adoption of mid-term work plans for state administration bodies by the end of 2017, which are harmonised with strategic priorities of the Government and the program budget) Connection with sustainable development goals |
| Implementation level | Not started | Partially implemented | Significantly implemented | Completed |
|  |  |  |  | X |
| Description of results | The proposal of the Law on the Planning System was drafted at the Government session held on 31 August 2017. |
| Next steps | Adoption of the Law in the National Assembly The Government adopted the Regulation on the methodology for public policy management, analysis of effects of public policies and regulations and content of specific public policy documents within six months of the adoption of the Law |
| Activity Status | Start Date: | End Date: | Completion Rate |
| 1. Drafting of the Law on Planning System in the Republic of Serbia | In progress | Q1 2017 (March 2017) | Fully completed |
| 2. Drafting of the Regulation on the Methodology for Public Policy Management, Analysis of Effects of Public Policies and Regulations and Content of Specific Public Policy Documents | In progress | Q1 2017 (March 2017.) | Fully completed |
| Contact |
| Lead implementing agency | Public Policy Secretariat of the Republic of Serbia |
| Name of a responsible person in the implementing agency | Dragana Aleksić |
| Title, Department | Acting Assistant Director, Sector for Support to Planning, Coordination and Monitoring of the Implementation of Public Policies |
| Email and phone number | dragana.aleksic@rsjp.gov.rs 3349-818 |
| Other actors involved | Administration | Ministry of Finance, Ministry of Public Administration and Local Self-Government, Secretariat General, Legislation Secretariat of the Republic of Serbia |
|  | Civil sector organisations, private sector, working groups |  |
| Additional information |

| COMMITMENT 6: Improving proactive transparency – Information Booklet |
| --- |
| Period – Commitment Start and End Date In progress - upon expiry of fourteen months of the date of when the new Instructions come into force |
| Lead implementing agency | Implementing agency for activity 1,3,4,5,6 : MPALSG MPALSG 2: Commissioner for Information of Public Importance and Personal Data Protection |
| Description of Commitment |
| Problem addressed by the commitment | The Law on Free Access to Information of Public Importance, which came into force in 2004, provides that transparency in the work of public administration bodies can be achieved in two ways: proactively and reactively. Proactive transparency implies timely publishing of documents and availability of understandable information for citizens. Information booklets on the work of public authorities and their content are defined by the by the Law on Free Access to Information of Public Importance and they include information used or generated by public administration bodies in their work. The currently applicable arrangement for publishing the Information Booklets (in Word/PDF formats) and the updating system lead to insufficient data, make any attempt at oversight an arduous task and provide limited possibilities for comparison of information, which reduces citizens’ overall awareness of the issues. The results of a survey carried out by the Belgrade Open School at the local self-government unit level showed that information booklets generally tend to lack the most sensitive information, especially information about the budget, which was observed in 69% of all cases. Only 16% of all municipalities published information about public procurement, while 11% published information about awarded state aid and various forms of financial support to public and other enterprises. About a half of all information booklets of LSGUs in Serbia (47%) do not contain information about e.g. documents and requirements necessary to exercise a social security entitlement or about the issuance of a certificate of registration with the register of births. |
| Main objective | The planned amendments to the Law on Free Access to Information of Public Importance, namely its Article 39 and Article 3 that defines the concept of a public authority body and the concept of a government body within the meaning of this Law, to which category of authorities refers obligation to publish the Information Booklet, as well as amendments to the Instructions on Preparation of Information Booklets, will see the information contained in those Information Booklets reformatted with the aim of opening the data contained therein, improving proactive transparency and expanding the circle of administration bodies subject to the legal requirement of publishing Information Booklets. This will entail: 1) Development of a single IT system to access, process and present the Information Booklet 2) Designing a segment of an online platform that would serve as an Information Booklet, coupled with an obligation for public administration bodies to publish information booklets in PDF format. 3) Training of employees in government bodies for the use of a single IT system 4) Piloting the use of the application 5) Promotion of the application (single IT system) for the public, civil sector, business sector and the media. Effectiveness of the amendments to Article 39 of the Law on Free Access to Information of Public Importance would be delayed until the online platform is designed. |
| How will this commitment contribute to problem solving? | In order to increase civic participation, it will first be necessary to raise citizens’ awareness, both in quantitative and in qualitative terms. In this context, the level of comprehensibility of information made available to citizens by the public administration should also be taken into account. Only if citizens fully comprehend information that is provided to them proactively can it be considered that citizens have been properly informed. Reformatting of the information booklets would entail changes in the data entry and updating arrangements, which in turn would have direct effects on citizens’ awareness and facilitate the work of civil servants and oversight of compliance with the Law. If adopted, this measure would ensure the following: - Public administration bodies would be able to enter data in their Information Booklets in a more efficient and faster manner - The number of freedom of information requests would be reduced - Public administration would be significantly improved because all pieces of information would be available in a single central database, both for other authorities and for citizens - The system used for overseeing compliance with the Law on Free Access to Information of Public Importance would be more efficient if the oversight procedures were more expedient and if the oversight activities were conducted to a higher standard of quality. - Interested parties would have easier and faster access to the required information, which they would be able to download in an open format, compare, cross-check and use for further analysis, research and development of various applications. - Civic participation would improve significantly, as would the watchdog role of the media and citizens’ oversight of the work of public administration bodies. |
| The way in which this commitment is relevant to further advancing OGP values | The proactive transparency principle is fully compliant with the open government principles, which are also proclaimed by the OGP initiative. Timely provision of information in an open format would directly improve data accessibility, which will ensure transparency and accountability in the work of public administration and foster civic participation and influence on the work of public administration. Provision of information in an open data format would enable subsequent processing of information and easier development of services and digital solutions for certain social services or social changes (e.g. development of a web or mobile application which would provide necessary information on required documentation to citizens). |
| Additional information (optional) |  |
| Implementation level | Not started | Partially implemented | Significantly implemented | Completed |
|  |  | Х |  |  |
| Description of results | This commitment is connected to commitment 7 – Amendments to the Law on Free Access to Information of Public Importance. Therefore, the Description of results for activity 1 of this commitment is contained in commitment 7, whereas only activities that are specifically connected to the development of a single IT system for accessing, processing and presentation of the Information Booklet. One of Commissioner’s activities on Project: “Building capacities of the Commissioner for the information of public importance and personal data protection for the effective ad adequate execution of his legal powers and ensuring the exercise of the right to free access to information and data protection right in accordance with European standards“, implemented by the Commissioner for information of public importance and personal data protection, based on Project Implementation Agreement No 337-00-00018/2015-04/1 dated 18 September 2015, concluded between the European Integration Office and the Commissioner, is creating the Model (electronic platform) for the Information Booklet. The application was also presented to the Ministry of Public Administration and Local Self-Government. After adoption of the Law on Amendments to the Law on Free Access to Information of Public Importance, it will be possible to quickly upgrade and arrange the application, and timely implement planned activities. In partnership and with the support of the UNDP, the MPALSG initiated the process of support for several local self-government units (Novi Sad, Niš, Leskovac, Vranje, Novi Pazar, Zrenjanin, Pančevo, Bečej, Šabac, Užice, Loznica) through which these LSGUs would receive support from consultants in the field of information technology, as well as advisory assistance for the implementation of a new electronic application for the input of the Information Booklet, including data preparation and processing. At the same time, interested civil society organisations from selected LSGUs attended the training for work with open data, and for the development of specific applications based on LSGU data, which would contribute to the quality of life of their fellow citizens, more efficient services and easier communication with citizens. An interactive workshop was held in Belgrade, on 5 July 2017, as part of this process, where representatives of selected LSGUs had an opportunity to get acquainted with the OGP initiative, the Action Plan and the new application for the entry of the Information Booklet, as well as with great benefits of open data for local development. The training for the representatives of civil society organisations was organised in the period from 16 to 18 June 2017, in Belgrade. The entry of data in the electronic Information Booklet by selected municipalities is under way. |
| Next steps |  |
| Activity Status | Start Date: | End Date: | Completion Rate |
| 1. Amendments to the Law on Free Access to Information of Public Importance (the “Law”) | In progress | Q4 2017 | Partially implemented |
| 2. Passing of new Instructions on Preparation and Publishing of Information Booklets (the “Instructions”) | On the date when the Law comes into force | Two months of the date when the Law comes into force | In progress |
| 3. Development of a single IT system to access, process and present Information Booklets | On the date when the New Instructions come into force | Upon expiry of one month of the date when the new Instructions come into force | In progress |
| 4. Training of employees at government bodies in the use of a single IT system | Two months of the date when the new Instructions come into force | Upon expiry of fourteen months of the date when the new Instructions come into force | Not started |
| 5. Piloting the use of the application | At the beginning of the fourth month of the date when the new Instructions come into force | Nine months of the date when the new Instructions come into force | Pre-piloting is in progress |
| 6. Promotion of the application (single IT system) for the public, civil sector, business sector and the media | Two months of the date when the new Instructions come into force | Fourteen months of the date when the new Instructions come into force | Not started |
| Contact |
| Lead implementing agency | Implementing agency for activity 1,3,4,5,6 : MPALSG Implementing agency for activities 2: Commissioner for Information of Public Importance and Personal Data Protection |
| Name of a responsible person in the implementing agency | MPALSG: Ivana Antić Commissioner: Slavoljupka Pavlović |
| Title, Department | MPALSG: Acting Assistant Minister Commissioner: Head of the Cabinet, entrusted with tasks of the Assistant Secretary General of the Commissioner’s Office at the Sector for Harmonisation and Cooperation |
| Email and phone number | ivana.antic@mduls.gov.rs, 2645-231 slavoljupka.pavlovic@poverenik.rs , 064 847-9-111 |
| Other actors involved | Administration |  |
|  | Civil sector organisations, private sector, working groups | BOS, CRTA, UNDP |
| Additional information |

| COMMITMENT 7: Amendments to the Law on Free Access to Information of Public Importance |
| --- |
| Period – Commitment Start and End Date Q4 2016 |
| Lead implementing agency | Ministry of Public Administration and Local Self-Government - MPALSG |
| Description of Commitment |
| Problem addressed by the commitment | The Law on Free Access to Information of Public Importance is currently being revised. The current revision aims to address certain deficiencies that have been observed in the implementation of the Law in practice. The Law on Free Access to Information of Public Importance dates back to 2004. The Law has been praised as excellent in terms of its legislative arrangements, but its implementation in practice has revealed certain deficiencies. The Commissioner for Information of Public Importance received a similar number of complaints in 2014 and 2015 – about 4,000 – mostly in cases of the so-called administrative silence. This shows that the legal enforcement mechanisms cannot be fully implemented in practice. In addition, the supervisory authority in charge of the implementation of this Law, the Administrative Inspectorate, has rarely used the option of imposing penalties for violations of the Law. Indeed, in recent years, entities that broke the Law were allowed to go unpunished on several occasions. The last two years saw progress in this regard, with the institution of infringement proceedings against a number of entities. However, taking into account that the Commissioner annually submits to Administrative inspection between 300 and 400 initiatives to initiate infringement proceedings, in cases of drastic violations of the right to free access to information of public interest, when the public authorities do not act according to the decision of the Commissioner, the number of infringement proceedings that are actually instituted remains very low. As the Law is currently being revised, these and other shortcomings might be eliminated in order to raise awareness of entities subject to the Law on Free Access to Information of Public Importance, as a constitutional category. Furthermore, the Action Plan on Development of e-Government also envisages the establishment of a legislative framework for open data and reuse of public sector information (to transpose the European Directive on Reuse of Public Sector Information) in the coming years. |
| Main objective | The Law on Free Access to Information should be amended in order to ensure exercising the right to access to information, as well as compliance with legally set deadlines. At the same time, it is necessary to determine an obligation of proactive publication of information. The future Law on Free Access to Information of Public Importance must include the following provisions: 1. To ensure efficient oversight of lawfulness of operations of public administration bodies and other entities subject to administrative oversight and inspection for violations of the right of access to information of public importance, in compliance with the principle of independence of oversight authorities and the principles of good governance 2. To introduce the obligation to obtain an opinion of the Commissioner for Information of Public Importance and Personal Data Protection in the process of passing regulations, to the extent that those regulations fall within the remit of this authority 3. To improve the situation regarding enforcement of decisions passed by the Commissioner for Information of Public Importance and Personal Data Protection 4. To bring the amount of fines in compliance with the Law on Misdemeanours and to establish a protective mechanism to ensure the achieved level of freedom of information cannot be reduced by other regulations 5. To impose a duty on the authorities subject to this Law to proactively publish information of public importance. |
| How will this commitment contribute to problem solving? | Amendments to the Law on Free Access to Information of Public Importance would address the issues which arose in the implementation of this Law in practice. Proper oversight of implementation of the Law and of the institute of enforcement of the Commissioner’s decisions would improve the exercise of the right of access to information and would raise awareness of the importance of this right among the entities subject to this Law. In addition, amendments to the Law which would vest the Commissioner with the power to give opinions in the process of enactment of laws would ensure that the existing level of protection of rights is not reduced by other laws and regulations. Amendments to the Law regarding proactive publishing of information would help reduce the number of appeals filed to the Commissioner due to violations of the right to free access to information of public interest, and improve respect for the right of access to information, which is also enshrined in the Constitution. |
| The way in which this commitment is relevant to further advancing OGP values | Adoption of amendments to this Law through improved procedure and transparency will enable easier and faster access to information provided by state administration authorities, all in the service of efficient, transparent and responsible work of the state administration. |
| Additional information (optional) |  |
| Implementation level | Not started | Partially implemented | Significantly implemented | Completed |
|  |  | Х |  |  |
| Description of results | A special working group for the preparation of the text of the Draft Law on Amendments to the Law on Free Access to Information of Public Importance was established on 3 November 2016. Members of the working group are representatives of the Ministry of State Administration and Local Self-Government, Administrative Inspectorate, Ministry of Justice, Legislation Secretariat of the Republic of Serbia, Public Policy Secretariat of the Republic of Serbia, National Assembly, Ministry of Finance. The Special working group for the preparation of the text of the Draft Law established cooperation with members of the Working Group for Open Data in the field of harmonisation of this regulation with the EU Directive on re-use of public sector information, as well as with members of the Working Group for the Action Plan for the implementation of the Open Government Partnership initiative in the Republic of Serbia for 2016 and 2017. Meetings of the Special group for the preparation of the text of the Draft Law on Amendments to the Law on Free Access to Information of Public Importance were held, and schedule of work was determined as well as the framework of amendments. The MPALSG held meetings with SIGMA representatives on 22 and 23 March 2017, as well as with members of the Special Group. SIGMA presented conclusions of its analysis, and agreed on next steps in order to improve the reform process. The working group made the first working draft of the Draft Law, and SIGMA commented on it on July 2017. The following period envisages consultations with the representatives of the Working Group for Open Data and Working Group for the Action Plan for the Implementation of the Open Government Partnership in the Republic of Serbia for 2016 and 2017. This is followed by consultations with the Commissioner for the Information of Public Importance and Personal Data Protection and civil society organisations. SIGMA submitted comments in July 2017, which was followed by a meeting of the Special Group on 6 September 2017, where they were analysed and discussed about. The most important amendments to the Law were presented on different meetings with CSOs during the preparation of the text of the Draft Law. Intensive consultations regarding the entry of provisions relating to open data and re-use of data in the Draft Law are in progress |
| Next steps | Finalising drafting of the text of draft amendments to the Law on Free Access to the Information of Public Importance Publishing the text of the draft law Conducting public debate Gathering opinions of competent authorities Adoption of the law in the Government |
| Activity Status | Start Date: | End Date: | Completion Rate |
| 1. Consultations between civil society organisations the Working Group on preparation of amendments to the Law on Free Access to Information of Public Importance | Q4 2016 | Q4 2017 | Partially implemented |
| 2. Preparation of draft amendments to the Law on Free Access to Information of Public Importance | In progress | Q4 2017 | Partially implemented |
| 3. Public debate programme established and published | Q4 2016 | Q4 2017 | Not started |
| 4. Public debate | Q4 2016 | Q4 2017 | Not started |
| 5. Submission of the Draft Law to the Government for review and adoption of the Bill | Q4 2016 | Q4 2017 | Not started |
| Contact |
| Lead implementing agency | Ministry of Public Administration and Local Self-Government - MPALSG |
| Name of a responsible person in the implementing agency | Ivana Antić |
| Title, Department | Acting Assistant Minister |
| E-mail and phone number | ivana.antic@mduls.gov.rs |
| Other actors involved | Administration | Ministry of Justice, RPPS, Ministry of Finance Working Group for Open Data |
|  | Civil sector organisations, private sector, working groups | Special Working Group on preparation of the Draft Law Amending the Law on Free Access to Information of Public Importance, Working Group for Open Data. |
| Additional information |

C. OPEN DATA

| COMMITMENT 8: Development of an Open Data Portal |
| --- |
| Period – Commitment Start and End Date 1 September 2016 – 31 October 2017 |
| Lead implementing agency | Office for Information Technologies and E-Government (former E-Government Directorate) |
| Description of Commitment |
| Problem addressed by the commitment | To date, Serbia has completed a feasibility study for open data, held a hackathon based on the first open data sets and commissioned a website containing open data and previously unavailable documents. Further coordinated efforts to open data will require a recognisable, unified state-of-the-art software solution to be published for an Open Data Portal. |
| Main objective | The aim is to publish an Open Data Portal where all institutions would open their data sets and which would provide a recognisable setting for open data users. |
| How will this commitment contribute to problem solving? | An Open Data Portal would enable public administration to publish data about its work and would thus increase transparency and citizen awareness, while also providing opportunities for developing applications which could potentially, in addition to providing improved services to citizens, also contribute to economic development and development of small and medium-sized enterprises. Accessible and comprehensible open data enable civic participation in the work of public administration and provide opportunities for technological innovation and development of highly useful applications and services. Open data portals bring budget savings because the administration has no need to spend budget resources to develop services and applications for open data sets, which increases the efficiency of its work. |
| The way in which this commitment is relevant to further advancing OGP values | The commitment refers to the publication of more information, improvement of the quality of published information, improvement of information access, and provision of the right to information. This means that the commitment is relevant in terms of transparency. The commitment also refers to the strengthening of public integrity. |
| Additional information (optional) | This measure follows one of government’s strategic goals referring to the opening of public administration data. |
| Implementation level | Not started | Partially implemented | Significantly implemented | Completed |
|  |  |  | Х |  |
| Description of results | The portal of open data was published at https://data.gov.rs/sr/data.gov.rs and currently there are 29 sets of open data. To prepare for the development of the Portal, we will conduct a needs analysis, examine positive experiences with existing Portals and develop technical specifications for the software. Based on the results of this exercise, a software solution will be developed in line with good global practice in terms of technology, which will be upgradeable and will ensure active participation of the open data user community. The next step would be to publish all existing data sets that have been opened to date on the Portal and to train users to ensure sound and comprehensive disclosure of available data. The Portal would also include open data metaregistries. |
| Next steps | Improvement of the Open Data Portal, localisation and design improvement Organising trainings for all categories of open data users Promotion of the Portal and training of open data set users Increase the number of data sets The Portal will provide links to other open data portals published by individual authorities The Portal will also include open data metaregisters. |
| Activity Status | Start Date: | End Date: | Completion Rate |
| 1. Development of the Portal | Q3 2016 | Q4 2016 | Completed |
| 2. Testing and pre-production runs | Q4 2016 | Q4 2016 | Completed |
| 3. User training | Q4 2017 | Q2 2018 | Not started |
| 4. Promotion and training of users of open data sets | Q4 2017 | Q2 2018 | Not started |
| Contact |
| Lead implementing agency | Office for Information Technologies and E-Government |
| Name of a responsible person in the implementing agency | Mihailo Jovanović |
| Title, Department | Director |
| E-mail and phone number | mihailo.jovanovic@gov.rs |
| Other actors involved | Ministry of Public Administration and Local Self-Government, E-Government Directorate, Ministry of Economy | Ministry of Interior, Medicines and Medical Devices Agency, Serbian Environmental Protection Agency, Ministry of Education, Science and Technological Development, Commissioner for Information of Public Importance |
|  | Civil sector organisations, private sector, working groups | Working Group for Open Data, NGOs, academic community |
| Additional information |
| COMMITMENT 9: Draft a bylaw based on the Guidelines for Evaluation of Websites |
| Period – Commitment Start and End Date 1 September 2016 – 31 October 2017 |
| Lead implementing agency | MPALSG, Office for Information Technologies and E-Government (former eGovernment Directorate) |
| Description of Commitment |
| Problem addressed by the commitment | The former eGovernment Directorate has been evaluating the websites of state administration bodies for more than ten years. This evaluation exercise covers also the websites of the bodies of the Autonomous Province of Vojvodina and local self-governments. The evaluation is done using a methodology defined in the Guidelines for website development, which the Government adopted as a standard for quality equalization and which are followed by Evaluation Criteria. While the open data initiative has been gaining momentum in the Republic of Serbia, the concept of open data, and its beneficial effects are still not sufficiently recognised by state institutions. Certain progress has already been achieved (a feasibility study for open data in the Republic of Serbia, an open data portal published at data.gov.rs), a Working Group on Open Data has been formed and an initiative has been launched to draft a legislative framework for open data and reuse of public-sector information. The Guidelines have been recognised as a mechanism for promoting the open data initiative. In this context, constant efforts are underway to further improve the Guidelines. In parallel with this, drafting of a Law on eGovernment is underway, and one of the bylaws would be the Rulebook for Development of Websites and Publishing of Electronic Services, which would be based on the Guidelines. |
| Main objective | This Commitment will involve modification of the Guidelines and Criteria for Evaluation as they pertain to publishing of information of public importance, in an open format. It will also include arrangements for entering information of public importance using a platform for automated data entry and generation of information booklets, as well as publishing of the content of those information booklets in several human-readable formats, as well as in an open machine-readable format. This measure will also define other aspects of websites, including the structure of websites of state authorities, and establishment of a metaregistry of data kept in official records and metaregistries of open data. Furthermore, provisions will be made for publishing of all parts of websites which contain information of public importance in an open format. |
| How will this commitment contribute to problem solving? | Establishment of legal regulations will ensure continuous improvement of the websites of all public administration authorities and the publication of electronic services and opening of data for the purpose of transparency and user orientation of the public administration of the Republic of Serbia. |
| The way in which this commitment is relevant to further advancing OGP values | By becoming a piece of secondary legislation, the Guidelines for Evaluation of Websites, which apply to state administration, autonomous province and local self-government bodies, could be used as a tool for improving the quality and scope of publishing of information of public importance and electronic services and could support the opening of new data sets. One of the steps involved in this measure will be to modify the Guidelines and, on their basis, develop and adopt the bylaw pursuant to the Law on eGovernment. It is expected that the Draft Law will be completed in December 2017. These efforts would highlight the added value the Republic of Serbia has derived from the Open Government Partnership. |
| Additional information (optional) |  |
| Implementation level | Not started | Partially implemented | Significantly implemented | Completed |
|  |  | Х |  |  |
| Description of results | A precondition for the fulfilment of this obligation is the adoption of the Law on E-Government, which will be followed by a by-law that precisely defines the publication of the content and services on the authority’s website, as well as the obligation to publish the service on the central e-Government Portal. The drafting of the Law on E-Government was completed, and the Draft Law has been submitted for a public debate. |
| Next steps | Adoption of the Law on E-Government Adoption of the by-law based on the Guidelines |
| Activity Status | Start Date: | End Date: | Completion Rate |
| 1. Preparation of a Draft Law on eGovernment | Q1 2017 | Q4 2017 | In progress |
| 2. Improvement and modification of the Guidelines to include publishing of open data, automated entry of Information Booklets using an application and publishing of a standardised version of the Information Booklet on the home page of each website, as well as publishing of all open data and metadata sets |  | Q4 2017 | Not started |
| 3. Preparation of a Draft Rulebook on the Content of Websites and Publishing of e-Services of State Administration Bodies |  | Q1 2018 | Not started |
| 4. Adoption of the Rulebook |  | Q1 2018 | Not started |
| Contact |
| Lead implementing agency | MPALSG, Office for Information Technologies and E-Government |
| Name of a responsible person in the implementing agency | Dražen Maravić Mihailo Jovanović |
| Title, Department | Assistant Minister Director |
| E-mail and phone number | drazen.maravic@mduls.gov.rs mihailo.jovanovic@gov.rs |
| Other actors involved | Administration | Commissioner for information of public importance, Working Group for the drafting of the Guidelines (members come from state administration bodies) |
|  | Civil sector organisations, private sector, working groups | Working Group for Open Data, CRTA, SHARE, (NGOs), academic community |
| Additional information |

D. GOVERNMENT INTEGRITY

| COMMITMENT 10: Improvement of the institute of public hearing in the drafting of laws |
| --- |
| Period – Commitment Start and End Date Q4 2016 |
| Lead implementing agency | Lead implementing agency for activities 1 and 2: MPALSG Lead implementing agency for activities 3 and 4: Government’s General Secretariat/National Legislation Secretariat |
| Description of Commitment |
| Problem addressed by the commitment | It is not uncommon for the Government to submit bills for parliamentary debate without first holding a public hearing. Since the criteria for determining when a public hearing has to be held in the legislative process, as set out in the Law on Public Administration and the Government’s Rules of Procedure, are not sufficiently clear and are subject to different interpretations in practice, this issue should be addressed in detail through amendments to those regulations. Moreover, even when public hearings are held, stakeholders’ comments and suggestions are sometimes not taken into account and Ministries sometimes fail to explain in the reports of public hearings how they reviewed such suggestions and proposals, whether they accepted such suggestions and proposals and, if so, to what extent. Lack of public hearings and enactment of laws in an expedited procedure are detrimental to civic participation and transparency; furthermore, laws enacted in this way are as a rule deficient in some way and entail a certain level of corruption risks. |
| Main objective | To create legal assumptions for public hearings and ensure that texts of draft laws submitted for public hearing are subsequently modified primarily as a result of acceptance of comments and suggestions made in the public hearing. This should apply to all laws, except in cases where certain precisely defined requirements and criteria are met that require immediate action; where the laws are passed to ratify international agreements or where the so-called “technical” amendments are made to laws, i.e. amendments which do not affect the existing conditions and the manner in which natural persons and legal entities exercise their rights and responsibilities etc. Cases when laws are enacted without a public hearing should be kept at an absolute minimum and this should be done only when strictly necessary, in urgent situations where postponement is not possible, in accordance with precisely defined criteria. Furthermore, a duty should be imposed on public authorities when drafting laws to post on their website all received proposals and comments, as well as reasons for accepting or rejecting those proposals, before providing a detailed report of the public hearing. Interactive relations should be established with stakeholders to ensure that any proposals and suggestions made during a public hearing are clearly conceived, consistent and as specific as possible. |
| How will this commitment contribute to problem solving? | Public hearings are held in the process of enactment of all laws, except in cases where certain precisely defined criteria are met that require immediate action, where the laws are passed to ratify international agreements or where the so-called “technical” amendments are made to laws, i.e. amendments which do not affect the existing conditions and the manner in which natural persons and legal entities exercise their rights and responsibilities etc. Furthermore, when drafting laws, public authorities post on their website all received proposals and comments, as well as reasons for accepting or rejecting those proposals. This contributes to greater transparency in the legislative process, encourages civic participation in the legislative process and improves the quality of enacted laws. |
| The way in which this commitment is relevant to further advancing OGP values | This commitment will clearly contribute to the attainment of all proclaimed principles of the Open Government Partnership – transparency and civic participation. Namely, amendments to these regulations should ensure that public hearings are held on a regular basis and that draft laws submitted for public hearing can subsequently be modified primarily as a result of acceptance of comments and suggestions made during public hearings; the amendments should also provide for publishing of all received proposals and comments, as well as reasons for accepting or rejecting such proposals. |
| Additional information (optional) |  |
| Implementation level | Not started | Partially implemented | Significantly implemented | Completed |
|  |  | Х |  |  |
| Description of results | In the reporting period, the competent authorities (MPALSG, the Government’s General Secretariat and the National Legislation Secretariat) agreed in direct cooperation that planned amendments to laws (the Draft Law amending the Law on Public Administration and the Draft Law on the Planning System of the Republic of Serbia) should be focused on regulation of the consultation procedure, as a form public participation in passing of regulations and public policy documents. The reasons for this include: first, consultations as a form public participation in passing of regulations and public policy documents are not regulated by legislation and their regulation would ensure participation of the interested public in passing of certain instruments from the beginning of their preparation, which would provide a much wider scope for a review of positions, suggestions and comments received from the interested public in the consultation procedure and/or during the preparation of instruments subject to consultations. In addition, consultation as a form of public participation in passing of certain instruments also ensures the participation of the expert community in the development of regulations and public policy documents, thus providing an opportunity for state administration bodies to improve the quality of proposed instruments by using the capacity of the expert community throughout the drafting process. Relevant arrangements in the Draft Law amending the Law on Public Administration and the Bill on the Planning System of the Republic of Serbia, which also include the power to pass implementing regulations which would specify in detail the procedure and methods of consultation, are drafted in that regard. The original version of the Draft Law also included amendments to the Government’s Rules of Procedure, but these amendments were subsequently withdrawn during the public debate and subsequent harmonisation of the text of the Draft Law with other authorities, because a better arrangement was found which ensured better public participation in the legislative process. According to this arrangement, the final version of the Draft Law provides for preparation of a bylaw which would regulate the guidelines for achieving participation of the public in the preparation of draft laws, other instruments and regulations. Focusing on the consultation procedure as a form of public participation in drafting of regulations and making of public policies will significantly contribute to improved quality of regulations and public policy instruments and participation of the public in these processes will be more efficient, which is the objective of this commitment. The proposed amendment to Article 77 under the Draft Law amending the Law on Public Administration, which has been prepared and submitted to the Government, provides for public participation in the preparation of draft laws and other instruments and implies the following main forms: A general duty to include the public in the preparation of draft instruments within the purview of ministries and special organisations; A general duty to issue notice of initiated drafting of legislation; Issuing of Baseline Paper were appropriate; A general duty to hold consultations with the interested public in the working stage of drafting, in accordance with their subject matter and effects; the same duty also applies to secondary legislation in certain cases; A duty to hold public debates on amendments to laws which significantly change the legal arrangements in a specific field or which govern issues of particular interest to the public (regulated in detail by the Government’s Rules of Procedure); 6) Analogous application of these public participation arrangements in the drafting of public policy documents. |
| Next steps | Enactment of the Law amending the Law on Public Administration Enactment of the Law on the Planning System of the Republic of Serbia Preparation and passing of implementing regulations which will provide in detail for guidelines for organisation of consultations in drafting of regulations, after adoption of the Draft Law amending the Law on Public Administration Preparation and adoption of the Government’s regulation providing for the procedure of organisation of consultations and public debates on public policy documents, after adoption of the Bill on the Planning System of the Republic of Serbia which has been submitted to the parliamentary procedure Preparation and adoption of the Government’s regulation providing for the procedure of organisation of consultations in drafting of regulations, after adoption of the Bill on the Planning System of the Republic of Serbia which has been submitted to the parliamentary procedure |
| Activity status | Start Date: | End Date: | Completion rate |
| 1. Preparation of a Draft Law amending the Law on Public Administration |  | Q3 2017 | Completed |
| 2. Submission of the Draft Law to the Government for review and endorsement of a Bill. |  | Q3 2017 | Completed |
| 3. Preparation of amendments to the Government’s Rules of Procedure |  | REVISED |  |
| 4. Submission of a Proposal of Rules of Procedure to the Government for review and adoption |  | REVISED |  |
| Contact |
| Lead implementing agency | Lead implementing agency for activities 1 and 2: MPALSG Lead implementing agency for activities 3 and 4: Government’s General Secretariat/National Legislation Secretariat |
| Name of a responsible person in the implementing agency | 1. MPALSG: Dražen Maravić 2. Government’s General Secretariat: Suzana Otašević and Ljubinka Knežević 3. NLS: Darko Radojičić |
| Title, Department | 1. Assistant Minister, Department for Development of Good Governance 2. Suzana Otašević, Head of the Group, Department of Planning, Supervision, Policy Coordination and Tasks related to the EU Integration Process Ljubinka Knežević, Independent Advisor 3. Assistant Director, Department for Drafting of Regulations |
| Email and phone number | drazen.maravic@mduls.gov.rs suzana.otasevic@gov.rs, ljubinka.knezevic@gov.rs darko.radojicic@gov.rs 011-3345-532 011-3620-099 011-363-3527 |
| Other actors involved | Administration | Anti-Corruption Agency Republic Secretariat for Public Policies |
|  | Civil sector organisations, private sector, working groups | Civil society organisations |
| Additional information |

E. FISCAL TRANSPARENCY

| COMMITMENT 11: Development of a uniform methodology for planning, monitoring and performance evaluation of programmes and projects implemented by civil society organisations and monitoring the spending of allocated funds |
| --- |
| Period – Commitment Start and End Date Q1 2017 – Q2 2017 (January-June 2017.) |
| Lead implementing agency | Office for Cooperation with Civil Society |
| Description of Commitment |
| Problem addressed by the commitment | The data obtained through the Annual Aggregate Report on spending of budget funds allocated and disbursed to associations and other civil society organisations from the national budget of the Republic of Serbia as support to programme activities show that cross-checking methods are not sufficiently used in the monitoring of execution of supported projects and programmes. These data also show that the main method of monitoring the execution of programmes and projects is review of final and narrative reports, while monitoring visits to associations account for the lowest share. This shows there is a need to harmonise the practices of monitoring supported CSO programmes and projects, using multiple different monitoring and evaluation methods. |
| Main objective | The aim of improving the process of monitoring and evaluation of supported programmes and projects is to ensure sounder follow-up to ensure their better implementation. In addition, this will give public administration bodies and citizens a much better image of the value for money of their investment, which will provide the basis for improved planning and more effective spending of budget funds, in accordance with the objectives set out in public policy documents. |
| How will this commitment contribute to problem solving? | Adoption of methodological instructions on the development of a plan of monitoring and evaluation of approved programmes and projects will impose a duty on public administration bodies to adopt a uniform approach to planning, monitoring and evaluation of approved CSO programmes and projects. This uniform approach to evaluation of the results of supported projects and programmes will provide a basis for evaluation and publishing of achieved results. This measure is in line with Commitment 12 of this Action Plan, which envisages amendments to the Regulation on Funds to Support Programmes or Missing Amount of Funds for Programmes of Public Interest implemented by Associations, as it imposes a duty to report on achieved results of the supported CSO programmes and projects and defines the content and form of the Tender Cycle Evaluation Report. This will ensure better public availability of information about the value for money of implemented projects and greater accountability of public administration bodies and CSOs for the public money they spend. |
| The way in which this commitment is relevant to further advancing OGP values | Strengthening the system of fiscal accountability and provision of information to the general public about CSO projects and programmes financed from the national budget of the Republic of Serbia will promote and develop integrity and accountability in the work of state institutions and build citizens’ trust in state institutions and civil society organisations. |
| Additional information (optional) |  |
| Implementation level | Not started | Partially implemented | Significantly implemented | Completed |
|  |  |  | Х |  |
| Description of results | The Methodology of Planning, Monitoring and Evaluation of Implemented Programmes and Projects of Civil Society Organisations and Tracking Spending of Allocated Funds (hereinafter referred to as the “Methodology”) has been prepared. Taking into account the importance of the issues regulated by the Methodology, the implementation of key provisions of this Methodology in the text of the Regulation on Funds to Support Programmes or Missing Amount of Funds for Programmes of Public Interest implemented by Associations has been proposed to the Working Group on amending the Regulation. Once the proposed provisions of the Methodology are incorporated in the Regulation which governs the procedure and manner of allocation of funds to CSOs, the provisions of the Methodology pertaining to monitoring and evaluation of success of supported programmes and projects will become binding on public administration bodies. |
| Next steps | The Office is working on a Guide on Methodology Implementation, which will provide public administration with instructions and support to ensure effective application of monitoring and evaluation methods to the supported programmes and projects. The Office has provided for public administration capacity building trainings on transparent funding of civil society organisations from public funds, which will cover topics relating to successful implementation of programme and project monitoring and evaluation methods in accordance with the Methodology. Amendments have been made to the Regulation on Funds to Support Programmes or Missing Amount of Funds for Programmes of Public Interest implemented by Associations to incorporate specific provisions of the Methodology. |
| Activity status | Start Date: | End Date: | Completion rate |
| 1. Development of a single Methodology of Planning, Monitoring and Evaluation of Implemented Programmes and Projects of Civil Society Organisations and Tracking Spending of Allocated Funds and instructions for its implementation | Q1 2017 (March 2017) | Q3 2017 (September 2017) | Completed |
| 2. Organisation of trainings in transparent financing of civil society organisations from public funds, which should include topics relating to successful application of the method for monitoring and evaluation of programmes and projects, as set out in the Methodology. | Q4 2017 (November 2017) | Q4 2017 (November 2017) | Ongoing |
| 3. Adoption of amendments to the Regulation on Funds to Support Programmes or Missing Amount of Funds for Programmes of Public Interest implemented by Associations which includes provisions of the Methodology |  | Q4 2017 | Ongoing |
| Contact |
| Lead implementing agency | Office for Cooperation with Civil Society |
| Name of a responsible person in the implementing agency | Milena Banović |
| Title, Department | Head of the Division for Planning and Creating an Enabling Environment for Civil Society Development |
| Email and phone number | milena.banovic@civilnodrustvo.gov.rs +381 11 311 3895 |
| Other actors involved | Administration | Ministry of Public Administration and Local Self-Government |
|  | Civil sector organisations, private sector, working groups | Civil society organisations |
| Additional information |

| COMMITMENT 12: Amendments to the Regulation on Funds to Support Programmes or Missing Amount of Funds for Programmes of Public Interest implemented by Associations |
| --- |
| Period – Commitment Start and End Date 1 March 2017 – 31 October 2017 |
| Lead implementing agency | MPALSG Office for Cooperation with Civil Society |
| Description of Commitment |
| Problem addressed by the commitment | The existing legal order in the Republic of Serbia does not impose a duty to publish reports on the achieved results of programmes and projects supported from the national budget of the Republic of Serbia. |
| Main objective | Amendments to the Regulation on Funds to Support Programmes or Missing Amount of Funds for Programmes of Public Interest implemented by Associations will introduce a duty to publish a report on the results achieved by supported CSO programmes and projects and will define the content and form of the Tender Cycle Evaluation Report. |
| How will this commitment contribute to problem solving? | This measure would impose a duty to publish the results achieved by the CSO programmes and projects supported from the national budget, which would give the public detailed access to information about the purpose of budget spending and the results achieved through such spending, which in turn would contribute to promotion of the core OGP values (fiscal transparency, openness and accountability of public administration). |
| The way in which this commitment is relevant to further advancing OGP values | Provision of information to the general public about the projects and programmes of civil society organisations financed from the national budget of the Republic of Serbia and the results they achieved will promote and develop integrity and accountability in the work of state institutions and build citizens’ trust in state institutions and civil society organisations. |
| Additional information (Optional) |  |
| Implementation level | Not started | Partially implemented | Significantly implemented | Completed |
|  |  |  | Х |  |
| Description of results | On 14 March 2017, the MPALSG formed a special Working Group, which has held five meetings and prepared a Draft Regulation amending the existing Regulation. The consultative process has begun in collaboration with the Office. The Draft Regulation was available on the official websites of the MPALSG and the Office for Cooperation with the Civil Society from 1 to 15 September 2017 to enable online public consultation. The Draft Regulation was also made available to all local self-government units for consultation through the Network of SCTM Commissioners. Their comments have been received and duly noted. The next step will involve setting up focus groups, both with representatives of local self-government units and with civil society organisations, to ensure transparency of the process of amending the Regulation and also to ensure the amendments meet the required quality standard. |
| Next steps | MPALSG, in cooperation with the Office for Cooperation with Civil Society, will organise a consultation process with CSOs and the Anti-Corruption Agency. The prepared Draft Regulation will be submitted to the Government of the republic of Serbia for adoption. |
| Activity status | Start Date: | End Date: | Completion rate |
| 1. Preparation of an Initiative to amend the Regulation on Funds to Support Programmes or Missing Amount of Funds for Programmes of Public Interest implemented by Associations | Q4 2016 (December 2016) | Q1 2017 (January 2017) | Completed |
| 2. Submitting the Initiative to the Ministry of Public Administration and Local Self-Government, by the Office for Cooperation with Civil Society | Q1 2017 (January 2017) | Q2 2017 (March 2017) | Completed |
| 3. The consultation process with CSOs in cooperation with the Office and the Anti-Corruption Agency | Q2 2017 (July 2017) | Q3 2017 (September 2017) | Ongoing |
| 4. Adoption of amendments to the Regulation on Funds to Support Programmes or Missing Amount of Funds for Programmes of Public Interest implemented by Associations | Q3 2017 (September 2017) | Q4 2017 (October 2017) |  |
| Contact |
| Lead implementing agency | MPALSG |
| Name of a responsible person in the implementing agency | Ivana Antić |
| Title, Department | Acting Assistant Minister, Department of Human and Minority Rights and Freedoms |
| Email and phone number | ivana.antic@mduls.gov.rs 011/2641-495 |
| Other actors involved | Administration |  |
|  | Civil sector organisations, private sector, working groups | Civil society organisations |
| Additional information |
| In accordance with the duties assumed under the Action Plan on Implementation of the Open Government Partnership Initiative, a consultation process will be implemented with civil society organisations and the Anti-Corruption Agency. |

F. PUBLIC SERVICES

| COMMITMENT 13: Enactment of the Law on Electronic Documents, Electronic Identification and Trusted Services in Electronic Business |
| --- |
| Period – Commitment Start and End Date 1 September 2016 – 31 October 2017 |
| Lead implementing agency | Ministry of Trade, Tourism and Telecommunications |
| Description of Commitment |
| Problem addressed by the commitment | Trust in online services is a crucial element for building trust in the work of public administration, as well as for social development. The existing regulations (Law on Electronic Signature and Law on electronic Document) do not cover certain segments of use of electronic data, means of electronic communication and electronic processing of data in the transactions of natural persons and legal entities, including public administration bodies (e-business), which feeds into the fear that e-services make it impossible to verify the identity of a legal entity or natural persons, enable electronic identification and guarantee for the authenticity of specific data, all of which affects the openness of public administration. The Draft Law on Electronic Documents, Electronic Identification and Trusted Services in Electronic Business was prepared and public debate was conducted from 7 to 30 September 2016. |
| Main objective | The main objective of regulating these issues by the law is to ensure and promote faster and more efficient business operations and reduction of operating costs, to develop of the trusted services market, to modernize and thus make more efficient the work of public authorities and economic operators, to ensure easier and safer access to services provided by public authorities and other entities for citizens and access to more such services, as well as reliable keeping of electronic documents, which will contribute to reduction of costs of document keeping. The specific objectives of regulating these issues by the law include using legal regulation of this subject matter to provide the scope for intensified e-business, to ensure trust of the general public in the use and exchange of electronic documents and the use of trusted services in e-business and to ensure competitiveness in international markets. |
| How will this commitment contribute to problem solving? | The new Law will improve Serbia’s legal framework and harmonise it with the most recent EU regulations in this field by introducing provisions pertaining to electronic documents, electronic identification and trusted services in e-business. The Law will introduce registers of electronic identification service providers, trusted service providers and qualified devices for certificate generation, regulate long-term storage of information and legal validity of electronic signatures and stamps and provide for their validation regardless of future technological changes. |
| The way in which this commitment is relevant to further advancing OGP values | The new Law and bylaws will enable easier and faster access to information and services provided by state administration bodies, with the aim of ensuring efficient, transparent and accountable work of state administration and providing better public services, suited to the needs of citizens and businesses. The Law will contribute to the attainment of core OGP values: technology and innovation as tools for achieving transparency and accountability. It will create conditions for fostering greater trust in electronic transactions and e-business, which in turn will lead to greater transparency and accountability of public administration and civic participation in the drafting of regulations and decision-making. The Law will facilitate access to information and civic participation. |
| Additional information (Optional) |  |
| Implementation level | Not started | Partially implemented | Significantly implemented | Completed |
|  |  |  | Х |  |
| Description of results | The Ministry of Trade, Tourism and Telecommunications prepared the Draft Law on Electronic Documents, Electronic Identification and Trusted Services in Electronic Transactions in 2016. A public debate was held in September 2016, in which the Ministry received numerous constructive proposals and suggestions. After the public debate, the Draft Law was sent for an opinion to the European Commission, which had no objections, and to state authorities. Once the harmonisation process was completed, on 17 August 2017 the Government adopted the Bill. The National Assembly has completed the general and specific hearings on the Bill and it is expected to be passed into law on Tuesday, 17 October 2017. |
| Next steps | Drafting of implementing regulations |
| Activity status | Start Date: | End Date: | Completion rate |
| 1. Obtaining and harmonizing opinions with the text of the Draft Law | 1 November 2016 | 16 August 2017 | Completed |
| 2. Adoption of the Draft Law by the Government | 17 August 2017 | 17 August 2017 | Completed |
| 3. Submission of the Bill to the parliamentary procedure and adoption of the Law | 29 August 2017 | 17 October 2017 | Ongoing |
| 4. Drafting of implementing regulations to be implemented by associations | 26 October 2017 | 26 April 2019 | Will be implemented after adoption of the Law. |
| Contact |
| Lead implementing agency | Ministry of Trade, Tourism and Telecommunications |
| Name of a responsible person in the implementing agency | Sava Savić |
| Title, Department | Assistant Minister, Department of Information Society |
| Email and phone number | sava.savic@mtt.gov.rs 011/20-20-272 |
| Other actors involved | Administration |  |
|  | Civil sector organisations, private sector, working groups | Civil society organisations |
| Additional information |

| COMMITMENT 14: Establishing of a single public register of administrative procedures and other conditions for pursuing a business activity |
| --- |
| Period – Commitment Start and End Date Ongoing – Q4 2018 |
| Lead implementing agency | Republic Secretariat for Public Policies |
| Description of Commitment |
| Problem addressed by the commitment | The existing public administration system does not have an integrated database of applicable administrative requirements (procedures). Citizens are therefore often confused, not knowing where to ask for advice or seek information about the procedures and costs of services provided by state administration bodies. This often creates unnecessary additional expenses and waste of time for public service seekers. A comprehensive and updated electronic database of administrative requirements would facilitate access to the required information for citizens and businesses, thus avoiding any additional expenses. |
| Main objective | A single public register of administrative procedures and other conditions for pursuing a business activity will enable citizens and businesses to access in one place all administrative requirements and procedures that have to be met and completed in order to obtain a certain service, including any costs in the form of fees, charges etc. Simplification of procedures and scrapping of unnecessary levies will create assumptions for greater predictability of operations and lower costs for citizens and businesses associated with the exercise of their guaranteed rights and compliance with their statutory duties. It is of particular importance to provide citizens and businesses with information about integrated procedures, i.e. procedures within the purview of multiple public administration bodies, in order to clearly identify all activities that need to be undertaken to complete a procedure as soon as possible. |
| How will this commitment contribute to problem solving? | Implementation of this commitment will result in free online availability of a single updated database of administrative procedures and other conditions for pursuing business activities. In this way, citizens and businesses will have ready access to the information they need without incurring any unnecessary additional expenses; this will save time for public service seekers and increase the efficiency of public service providers. |
| The way in which this commitment is relevant to further advancing OGP values | Introduction of the register will contribute to greater transparency in the work of public administration and facilitate day-to-day operations of businesses and daily life of citizens. Citizens and businesses will have at their disposal a “one-stop shop” where they will be provided with details of all procedures and costs for the parties involved and information on the relevant bodies in charge of those procedures. |
| Additional information (optional) | Funds for implementation of this commitment will be provided from donor funds (GGF – 291,000 £; GIZ; IPA 2013) Link with other Government’s programmes: Introduction of the Register has been recognised as one of the priority activities in the following strategic documents: Strategy of Regulatory Reform and Improvement of the System of Managing Public Policies for the period 2016-2020, Strategy for Support to Development of Small and Medium-Sized Enterprises, Entrepreneurship and Competitiveness for the period from 2015 to 2020, National Programme to Combat Grey Economy, Economic Reform Programme (ERP) for the period 2016-2018, Plan of Priority Activities to reduce the Administrative Burden in the Republic of Serbia 2016–2018. (“Stop Bureaucracy”). |
| Implementation level | Not started | Partially implemented | Significantly implemented | Completed |
|  |  |  | Х |  |
| Description of results | An overall plan of activities to establish a single register of administrative conditions has been prepared. The Government passed a resolution which put in place a mechanism for communication and coordination between 79 bodies, organisations, agencies and public enterprises in order to inventory all administrative procedures applicable to businesses. The Public Policy Secretariat established a functional portal for the purpose of inventorying administrative procedures. In total, 35 one-day training events were held for 479 civil servants from 107 bodies and organisations. The inventory of administrative procedures involves 79 bodies and organisations in total (16 ministries, 6 special organisations, 7 other state bodies, 48 subordinated bodies and organisations, public enterprises and other organisations overseen by ministries and the Chamber of Commerce and Industry of Serbia). All relevant institutions have designated their respective coordinators and team members, who are actively involved in the inventorying of administrative procedures and other business conditions. The inventory process involves 75 coordinators from those institutions and 439 civil servants The inventory began on 5 June and is still underway, although it should have been finished in September 2017. The inventory portal includes entries of 2470 administrative procedures and the inventory has entered its final stage, which involves data verification. A Working Group has been formed to prepare a Draft Law on the Single Public Register of Administrative Procedures and Other Business Conditions. The first version of the Draft Law has been prepared to date. |
| Next steps | Completion of the inventory of administrative procedures Development of a methodology to simplify and optimise administrative procedures Analysis and optimisation of administrative procedures Preparation of an inventory of administrative requirements Analysis of administrative requirements Creating proposals to modify inefficient procedures Development of an Action Plan to modify the legal framework in order to simplify or optimise administrative procedures and other business conditions Development of a Draft Law that would provide for the establishment and functioning of a Single Public Register of Administrative Procedures and Other Business Conditions, with draft secondary legislation Establishment of the Single Public Register |
| Activity status | Start Date: | End Date: | Completion rate |
| 1. Preparation and adoption of an operating action plan on the establishment of a single public register of administrative procedures and other conditions for business activities | Q2 2016 (May 2016) | Q4 2016 (December 2016) | Completed |
| 2. Designing forms and conducting trainings for inventorying administrative procedures | Q2 2016 (June 2016) | Q1 2017 (March 2017) | Completed |
| 3. Inventory of administrative procedures | Q2 2017 (5 June 2017) | Ongoing (completion is expected in October 2017) | Ongoing (significantly implemented) |
| 4. Inventory of business procedures | Q2 2017 (April 2017) | Q4 2017 (December 2017) | Not started (initiation is expected in Q4 2017, continually until establishing of the register, i.e. until Q2 2019) |
| 5. Development of a methodology for optimising the inventoried administrative requirements | Q3 2017 (August 2017) | Q3 2017 (October 2017) | Ongoing (adoption of the methodology and supporting documents for calculation of administrative costs is expected soon) |
| 6. Development of software for the e-portal of the integrated public register of administrative procedures | Q1 2018 (March 2018) | Q4 2018 (December 2018) | Not started |
| Contact |
| Lead implementing agency | Republic Secretariat for Public Policies |
| Name of a responsible person in the implementing agency | Ninoslav Kekić |
| Title, Department | Acting Assistant Director, Department for Quality Assurance of Public Policies |
| Email and phone number | ninoslav.kekic@rsjp.gov.rs 3349-818 |
| Other actors involved | Administration | Ministry of Economy, Ministry of Finance, Ministry of Trade, Tourism and Telecommunications, Ministry of Public Administration and Local Self-Government, Human Resource Management Service-activity 2 (as it pertains to training) |
|  | Civil sector organisations, private sector, working groups | Chamber of Commerce and Industry of Serbia |
| Additional information |

# Footnotes

http://www.mduls.gov.rs/partnerstvo-za-otvorenu-upravu.php

https://ogp.rs/

https://ogp.rs/kontakt/

Decision No. 06-00-377/2015-04 dated 20 January 2016, http://ogp.rs/wp-content/uploads/2016/02/Resenje-o-osnivanju-RG-final.pdf

https://www.youtube.com/watch?v=XsdIHmM1ek4

https://www.youtube.com/watch?v=9aV9YXFaORI

https://www.youtube.com/watch?v=0bxaQPr_nsY

http://civilnodrustvo.gov.rs/vest/partnerstvo-za-otvorenu-upravu:-kandidatura-za-%C4%8Dlana-radne-grupe.37.html?newsId=689

http://civilnodrustvo.gov.rs/vest/partnerstvo-za-otvorenu-upravu:-doneta-odluka--o-o-izboru-%C4%8Dlanova-i-zamenika-%C4%8Dlanova.37.html?newsId=699

http://civilnodrustvo.gov.rs/upload/documents/Kancelarija/Dokumenta_Kancelarije/Konacna%20Odluka%20Komisije%20RG%20OGP.pdf

http://www.mduls.gov.rs/latinica/partnerstvo-otv-upravu-2017.php

http://www.civilnodrustvo.gov.rs/%D0%B2%D0%B5%D1%81%D1%82/%D0%BF%D0%B0%D1%80%D1%82%D0%BD%D0%B5%D1%80%D1%81%D1%82%D0%B2%D0%BE-%D0%B7%D0%B0-%D0%BE%D1%82%D0%B2%D0%BE%D1%80%D0%B5%D0%BD%D1%83-%D1%83%D0%BF%D1%80%D0%B0%D0%B2%D1%83:-%D0%BA%D0%BE%D0%BD%D1%81%D1%83%D0%BB%D1%82%D0%B0%D1%86%D0%B8%D1%98%D0%B5-%D1%81%D0%B0-%D1%86%D0%B8%D0%B2%D0%B8%D0%BB%D0%BD%D0%B8%D0%BC-%D0%B4%D1%80%D1%83%D1%88%D1%82%D0%B2%D0%BE%D0%BC.74.html?newsId=705

http://www.mduls.gov.rs/latinica/partnerstvo-otv-upravu-2017.php

http://www.mduls.gov.rs/latinica/partnerstvo-otv-upravu-2017.php

http://ogp.rs/akcioni-plan-2016-2017/#dokumenta

http://www.mduls.gov.rs/latinica/partnerstvo-za-otvorenu-upravu.php

http://civilnodrustvo.gov.rs/%D0%B2%D0%B5%D1%81%D1%82/%D1%98%D0%B0%D0%B2%D0%BD%D0%B8-%D0%BF%D0%BE%D0%B7%D0%B8%D0%B2-%D0%B7%D0%B0-%D1%83%D1%87%D0%B5%D1%88%D1%9B%D0%B5-%D1%83-%D1%98%D0%B0%D0%B2%D0%BD%D0%B8%D0%BC-%D0%BA%D0%BE%D0%BD%D1%81%D1%83%D0%BB%D1%82%D0%B0%D1%86%D0%B8%D1%98%D0%B0%D0%BC%D0%B0-%D0%BE-%D0%B0%D0%BA%D1%86%D0%B8%D0%BE%D0%BD%D0%BE%D0%BC-%D0%BF%D0%BB%D0%B0%D0%BD%D1%83-%D0%BF%D0%B0%D1%80%D1%82%D0%BD%D0%B5%D1%80%D1%81%D1%82%D0%B2%D0%B0-%D0%B7%D0%B0-%D0%BE%D1%82%D0%B2%D0%BE%D1%80%D0%B5%D0%BD%D1%83-%D1%83%D0%BF%D1%80%D0%B0%D0%B2%D1%83-20162017.74.html?newsId=743

http://ogp.rs/vesti/javni-poziv-za-ucesce-u-javnim-konsultacijama-o-akcionom-planu-za-sprovodenje-pou-inicijative/

http://www.mduls.gov.rs/partnerstvo-za-otvorenu-upravu.php

https://goo.gl/AwW91X

http://ogp.rs/vesti/izvestaj-o-sprovedenim-javnim-konsultacijama/

http://www.mduls.gov.rs/partnerstvo-otv-upravu-2017.php

http://civilnodrustvo.gov.rs/%D0%B2%D0%B5%D1%81%D1%82/%D0%BE%D0%B4%D1%80%D0%B6%D0%B0%D0%BD-%D1%81%D0%B0%D1%81%D1%82%D0%B0%D0%BD%D0%B0%D0%BA-%D1%81%D0%B0-%D0%BE%D1%80%D0%B3%D0%B0%D0%BD%D0%B8%D0%B7%D0%B0%D1%86%D0%B8%D1%98%D0%B0%D0%BC%D0%B0-%D1%86%D0%B8%D0%B2%D0%B8%D0%BB%D0%BD%D0%BE%D0%B3-%D0%B4%D1%80%D1%83%D1%88%D1%82%D0%B2%D0%B0-%E2%80%93-%D0%BF%D1%80%D0%B0%D1%9B%D0%B5%D1%9A%D0%B5-%D0%B0%D0%BF-%D0%B7%D0%B0-%D1%81%D0%BF%D1%80%D0%BE%D0%B2%D0%BE%D1%92%D0%B5%D1%9A%D0%B5-%D0%B8%D0%BD%D0%B8%D1%86%D0%B8%D1%98%D0%B0%D1%82%D0%B8%D0%B2%D0%B5-%D0%BF%D0%B0%D1%80%D1%82%D0%BD%D0%B5%D1%80%D1%81%D1%82%D0%B2%D0%BE-%D0%B7%D0%B0-%D0%BE%D1%82%D0%B2%D0%BE%D1%80%D0%B5%D0%BD%D1%83-%D1%83%D0%BF%D1%80%D0%B0%D0%B2%D1%83.74.html?newsId=824

http://ogp.rs/vesti/poziv-za-ucesce-na-sastanku-u-okviru-pracenja-procesa-sprovodenja

Date of completion of this activity is specified in the Action Plan for Chapter 23. This activity will be monitored through that Action Plan.

The date of completion of this activity is defined under the Action Plan for Chapter 23. This activity will be monitored through this Action Plan.