**Open Government Partnership (OGP)**

**Criteria & Standards Subcommittee Meeting Minutes**

Open Government Hub, Washington, D.C, USA

February 23-24, 2016

**1. Welcome**

The Government of Brazil, as chair of the Criteria and Standards subcommittee, welcomed participants to the meeting. Members agreed on the agenda for the next two days.

**2. Discussion on Countries Under Review**

The subcommittee discussed the countries under review for acting contrary to OGP process for two consecutive action plan cycles. The Support Unit reminded the subcommittee that a country can be considered to have acted against the OGP process in the following situations:

1. The country does not publish a National Action Plan within 4 months of the due date;
2. The National Action Plan was developed with neither online or offline engagements with citizens and civil society;
3. The Self-Assessment Report is not submitted within 4 months of the due date;
4. The country refuses to engage with the IRM researcher in charge of the country’s Mid-term progress report and End-of-Term reports;
5. The IRM Report establishes that there was no progress made on implementing any of the commitments under the country’s national action plan;

There are currently five participating countries under review: Australia, Kenya, Malawi, Montenegro, and Turkey. In all cases, the review process would be finalized once a new Action Plan is submitted.

**Australia.** The Government of Australia has not delivered a National Action Plan since they sent their letter of intent in May 2013. On November 24, 2015, the Support Unit received a letter from Prime Minister Malcolm Turnbull, that established that they would formalize Australia’s participation in OGP by developing an Action Plan to be delivered by July 1st, 2016. An OGP point of contact was appointed and the government is now working on an Action Plan with national civil society organizations. The Support Unit is planning to visit Australia to assist with the development of the new Action Plan in the next 2-3 months.

**Kenya.** Kenya sent its letter of intent to join OGP in August 2011 and submitted their first National Action Plan in February 2012. However, the government failed to submit its second Action Plan in 2014 and 2015. Since then, the office of the Deputy President has taken over ownership of OGP in Kenya and is leading the preparation of the new action plan. In a letter dated February 23, 2016, the Kenyan government confirmed it will complete the development of a new Action Plan by the revised deadline of June 30, 2016. In addition, the government of South Africa has committed to provide support and outreach.

**Malawi.** Malawi sent its letter of intent to join in July 2013, yet was unable to submit an Action Plan in 2014 and 2015. The Government of Malawi joined the meeting by teleconference as part of their review process. The Government of Malawi point of contact provided a brief description about the latest developments regarding their action plan development process and the commitments that will be included. They expect to send the Action Plan to the Support Unit within the next two months. The plan will include commitments in the areas of access to information, anti-corruption, national integrity and service delivery. The subcommittee also recommended scheduling a conversation between its members, the government of Malawi and multilateral partners in the margins of the Africa regional meeting in May. This would focus on support for the implementation of the new commitments.

**Montenegro.** Montenegro sent its letter of intent to join OGP in September 2011 and submitted their first National Action Plan in 2012. However, the government failed to submit its second Action Plan in 2014 and 2015. The Government of Montenegro joined the meeting by teleconference as part of their review process. The Government of Montenegro points of contact explained the process to develop their Action Plan and the challenges they have faced. They assured the subcommittee members that during the past several weeks they have held weekly meetings to ensure buy-in from all parties involved in every commitment to be included in their Action Plan. They expect to send the approved action plan by late March or early April. Their plan will cover themes like Open Data, Access to Information, and proactive transparency.

**Turkey.** Turkey’s participation has been under review by the OGP Criteria and Standards since 2015, after they were found acting contrary to the OGP process for two consecutive action plan cycles. First, the IRM Report established that there was no progress made on implementing any of the commitments on Turkey’s first Action Plan in 2014. Secondly, the government failed to produce a new National Action Plan in 2014 and 2015.

The subcommittee discussed Turkey, where there is not currently an assigned lead ministry or official point of contact. The subcommittee agreed to ask the co-chairs, and other Steering Committee members to invest political and diplomatic capacity to make a final outreach to Turkey to reengage in OGP prior to the Ministerial level Steering Committee meeting in South Africa on May 3-4th, 2016. If no response is received before the Steering Committee meeting, Criteria and Standards decided that it will then make a recommendation to the full Steering Committee that Turkey be considered inactive.

**3. Country discussion: Azerbaijan**

Azerbaijan is currently being reviewed under the OGP Response Policy. The subcommittee thoroughly discussed the case and the recommendations emerging from stage one of the review. They agreed on a resolution (Annex 1) to recommend to the full Steering Committee to move to stage two actions. This item will be tabled for Steering Committee discussion and decision at the Ministerial level meeting on May 3-4th, 2016.

**4. Country discussion: Hungary**

Hungary is currently being reviewed under the OGP Response Policy. The subcommittee discussed the draft report that evaluates the relevance and credibility of the concerns received, and makes recommendations for next steps. The subcommittee agreed to provide final edits to the report in writing following the meeting. The Support Unit will revise the report for approval by the subcommittee before it is sent to the filers and the government of Hungary in mid March.

**5. Session with lead co-chairs**

The subcommittee held a discussion with the OGP lead co-chairs to update them on the issues currently under consideration. At the beginning of the discussion, Joseph Powell, acting director of the OGP Support Unit, reminded everyone that the session was not to be considered an official meeting between the Governance and Leadership and the Criteria and Standards Subcommittees given the support co-chairs were not present; but should be an informal discussion to promote closer collaboration between the different subcommittees of the Steering Committee.

During the meeting, the lead co-chairs briefed CS on several topics. They shared their plans to celebrate the 5-year anniversary of OGP in September, around the UN General Assembly; summarized their discussion on how to strengthen peer learning and support; and talked about addressing other potential cross-cutting issues using the OGP platform, such as Legislative Openness and Climate Change.

During the session, the CS Chair and other subcommittee members informed the OGP chairs Deputy Minister Ayanda Dlodlo and Alejandro Gonzalez about the progress of different countries currently under response policy review and of those found acting contrary to OGP process for two consecutive cycles. The group discussed the recommendation that will be tabled for decision by the full Steering Committee in May, as well as other potential recommendations that might be tabled for the next meeting.

**6. IRM session**

The subcommittee met the Independent Reporting Mechanism team and a representative of the International Experts Panel for a discussion about recent activities. They informed the subcommittee about plans to publish and launch upcoming IRM reports in different countries. They talked about how reports were being received and what communication there was around them. The IEP updated the subcommittee on policy changes, including the amendment to the criteria for starred commitments and a new assessment in the end of term reports about whether commitments measurably opened government (i.e. is there more information available in a commitment area, are there more mechanisms for citizens to participate, are there the means to hold governments accountable). The subcommittee also discussed alternatives to reduce the workload and streamline the two self-assessment reports that all OGP participating countries have to deliver.

**7. Review of response policy**

During the October 2015 Steering Committee meeting, the subcommittee presented a draft one-year report on the implementation of the Response Policy with some recommendations and lessons learned. Based on the learnings from the two current Response Policy cases, the subcommittee members discussed further recommendations on the timeline, procedures and resources required to ensure successful, accurate and reliable practices. The subcommittee agreed to provide input for a draft document to be discussed at the subcommittee meeting in May, which would be presented to the full Steering Committee in September.

**8. Legislative action plans**

The IRM presented information they currently have about legislative action plans that are being drafted or implemented. The subcommittee focused their discussion on the issue of stand alone legislative action plans (i.e. those that are not integrated with the national action plans regularly submitted to the Support Unit). The subcommittee had previously discussed this issue at their July 2015 meeting and decided that OGP would not formally accept legislative action plans that were separate to national action plans. The subcommittee highlighted that currently participating countries can include legislative commitments in their national action plans, as various participating countries have done in their action plans, but it would not be possible for OGP to consider separate plans, from a different entity/branch of government, as this would contradict the rule of OGP regarding one National Action Plan per participating country. The subcommittee upheld the 2015 decision. The OGP co-chairs have agreed this issue will be discussed at the Steering Committee meeting in May 2016.

**9. Subnational IRM**

The IRM team presented a proposal on the scope of IRM assessments for the leaders track of the subnational pilot program, that will see subnational governments submitting short Action Plans to OGP. Subcommittee members presented suggestions on possible models the IRM could experiment with in the subnational pilot program, including the use of a peer review process. The IEP was asked to make a final recommendation about how the IRM will assess these subnational action plans based on the need for independent assessment of a maximum of five commitments per plan.

**10. Consultation guidelines**

The directors of the Civil Society Engagement team, within the Support Unit, and the IRM presented a series of broad recommendations on how civil society participation requirements could be updated. This would include changes to the rules that encourage high-quality dialogues with robust, open and inclusive participation, and providing feedback and seriously considering inclusion of proposals from civil society organizations. The subcommittee decided that there should be a review of the existing consultation guidelines – and a decision taken by the Steering Committee on updating them - in time to inform the development of action plans in 2017.

It was agreed that the Support Unit and IRM will prepare a draft set of consultation recommendations for discussion by the subcommittee at their next in-person meeting in May. This proposal will seek to simplify requirements, assess the quality of the consultation and provide guidance on the ongoing dialogue between government and civil society in all three phases of OGP Action Plan Cycle: NAP development, implementation and monitoring. The subcommittee will then work on a policy update recommendation to be presented to the Steering Committee for discussion and decision in September 2016.

# **Participant List**

*Governments*

Brazil

Roberta Solis Ribeiro Office of the Comptroller General of Brazil

Otavio Moreira de Castro Neves Office of the Comptroller General of Brazil

Felipe Bandeira de Mello Embassy of Brazil

Chile

Francisco Sánchez Ministry General Secretariat of the Presidency (videoconference)

Croatia

Katarina Andric Directorate-General for Multilateral Affairs and Global Issues (videoconference)

United States

Camille Eiss Department of State

Corinna Zarek White House, Office of Science Technology Policy

*Civil Society*

Mukelani Dimba Open Democracy Advice Centre (ODAC)

Nathaniel Heller Results for Development Institute (R4D)

Warren Krafchik International Budget Partnership (IBP)

*Support Unit*

Joe Powell Acting Executive Director

Paul Maassen Civil Society Engagement Director

Alonso Cerdan Program Manager

Abhinav Bahl Program Manager

Kitty von Bertele Special Assistant

*Independent Reporting Mechanism*

Hazel Feigenblatt International Experts Panel

Joseph Foti Program Director

Denisse Miranda Research Manager

Tinatin Ninua Research Manager

**Annex 1:**

**Criteria and Standards Subcommittee Resolution on the Policy on Upholding the Values and Principles of the Open Government Partnership for the case of Azerbaijan**

On September 2014, the Open Government Partnership (OGP) Steering Committee (SC) adopted the Policy on Upholding the Values and Principles of the OGP (otherwise known as the “Response Policy”) in order to achieve two objectives: a) assist the country in question to overcome difficulties and to help re-establish an environment for government and civil society collaboration, and b) safeguard the Open Government Declaration and mitigate reputational risks to OGP.

The response policy considers two stages of action. Stage one is led by the Criteria and Standards Subcommittee (CS) and seeks to validate the complaint through a review process. Once the review process has established the relevance of the concern, the Criteria and Standards subcommittee develops a set of recommendations to address the original issues of concern including technical assistance, diplomatic outreach, and regular check-ins and a timeline for key actions to demonstrate progress. If the stage one actions do not meaningfully address the issues of concern validated in the report, “the Criteria and Standards subcommittee is to recommend to the full OGP Steering Committee that one or both of the following stage two actions take place:

1. Recommend that the OGP co-chairs invite the government principal to attend a special session of the Steering Committee to discuss the situation and consequences for the country’s participation in OGP.
2. Recommend the OGP co-chairs author a letter to the country informing them they are to be temporarily listed as inactive in OGP until the concern is resolved.”[[1]](#footnote-1)

This document summarizes the ongoing Azerbaijan Response Policy process. The stage one deadlines have expired without satisfactory resolution, and thus the Criteria and Standards subcommittee has prepared this document to support its recommendation to the full Steering Committee to move to stage two actions. The subcommittee resolution, outlined in section 4, recommends to the full OGP Steering Committee that Azerbaijan be listed as inactive in OGP until such a time that the areas of concern have been adequately addressed.

The areas of concern are discussed in detail in sections 1 and 3 below. In recommending that the Steering Committee move to stage two actions, the CS is particularly troubled by the constraints in the operating environment for NGOs and the absence of efforts to address these constraints through the draft National Action Plan. Such constraints are evident in the laws on grants, non-governmental organizations, and registration of legal entities and state registry, and the Code on Administrative Offenses; the freezing of bank accounts of some NGOs promoting open government; and the incarceration of NGO activists and journalists promoting open government. The resulting environment has made it difficult if not impossible for a number of NGOs to operate. These developments are inconsistent with the OGP’s core commitments and principles and pose a challenge to the institutional integrity of the OGP. CS continues to hope that the government will expeditiously address these concerns.

***1. Complaint Letter and Initial Review Process***

On March 2, 2015, the Response Policy was used for the first time.[[2]](#footnote-2) The OGP Steering Committee received a letter of complaint from CIVICUS, Publish What You Pay, and Article 19 regarding the threats they perceived civil society to face in Azerbaijan, and the way those alleged threats affected civil society’s ability to engage effectively in the OGP process. The letter raised concerns about five issues: government control over registration and operations of NGOs; government control over NGO finances; harassment of civil society; initiation of criminal and tax cases; and consultation failures.[[3]](#footnote-3) The Government of Azerbaijan was informed about the raised concern and on April 15, 2015, the OGP Support Unit received a letter of response, which was considered during the review process.[[4]](#footnote-4)

After a thorough review of the claims made in the original letter, the Criteria and Standards subcommittee generated a report informed by credible third-party analysis of the situation in the country. Based on this research and analysis, the CS deemed the concern relevant, true, accurate, and an immediate and real threat to OGP’s credibility. The CS report also assessed that an OGP response could potentially “help establish a positive environment for government and civil society collaboration.”[[5]](#footnote-5)

In order to address the situation described by the filers, CS developed a set of five specific recommendations that the government of Azerbaijan would need to address to meaningfully address the concerns raised and validated. The CS shared these recommendations in a letter to the Government of Azerbaijan July 6.[[6]](#footnote-6) These items were:

1. **Timeline for the next National Action Plan**. In its July 6 letter, the CS requested that the government of Azerbaijan submit its new plan by December 30th 2015, to begin implementation on January 1st 2016. The recommendation called for an action plan that is 18 months in length, ending in June 2017. CS also requested that the Government of Azerbaijan produce a timeline for the consultation period of the new National Action Plan in time for a check-in call in August 2015.
2. **Consultation with civil society**. The Government of Azerbaijan was asked to meaningfully consult with civil society organizations and citizens in the creation of its new action plan according to OGP requirements. The CS subcommittee offered to prepare recommendations on how to conduct an open and representative consultation process. CS recommendations also called for an independent assessment of the consultation process to be reported back to the CS following the conclusion of the National Action Plan consultation process.
3. **Peer exchange and technical support.** CS members offered to share lessons learned from their respective NGO cooperation work.
4. **Commitments to improve the operating environment for civil society**. CS requested that the government of Azerbaijan consider including commitments in the new action plan that specifically address the functioning of the Law on Grants, Law on Non-governmental Organizations, Law on Registration of Legal Entities and State Registry, and the Code on Administrative Offenses. CS, in collaboration with NGO legal experts, deemed these commitments as best positioned to meaningfully address the barriers that NGOs currently face in registering and processing contracts and receiving funding, and worked together to develop recommendations on how implementation of these laws could help improve the operating environment for civil society organizations in Azerbaijan. CS invited the Government of Azerbaijan to submit evidence on progress toward these reforms at the three and six-month points of implementation following release of the new action plan in 2016. Those reports would be evaluated as part of the progress towards resolving the original response policy concerns, with the reports being sent to the full Steering Committee.
5. **Working with the OGP Steering Committee**. CS invited the Government of Azerbaijan to participate in a teleconference in August 2015 to discuss the consultation process and be available for on-going support throughout the new action plan development process.[[7]](#footnote-7)

***2. Action Plan Development Process***

In their response to the CS recommendations, on August 28, 2015 the Government of Azerbaijan committed to conduct an open, participatory and wide consultation on a new action plan; use the resources and assistance of OGP and international partners; and to “meet with members of the Criteria and Standards Subcommittee and discuss the specific issues on commitments during the OGP summit in Mexico.”[[8]](#footnote-8) The response noted that the drafting of the new Action Plan would begin “mid-October” and would be adopted either at the end of December 2015 or the beginning of January 2016.

During the Mexico City Summit, the Government of Azerbaijan did not send a representative from Baku. The CS members therefore met with officials from the Embassy of Azerbaijan in Mexico. This meeting was scheduled to provide updates on Azerbaijan’s commitments considered for its new action plan, including those under consideration to address the functioning of the NGO laws in the country, an issue at the heart of the original letter of concern.

In that meeting, the Subcommittee requested a public letter from the government of Azerbaijan that addressed the following issues:

1. The precise timeline to be followed during the National Action Plan drafting process.
2. The detailed steps and methodology to be followed in the National Action Plan drafting process.
3. The initial list of civil society organizations that would be involved in and consulted with during the National Action Plan drafting process.

On November 12, 2015, the CS received notice from the Government of Azerbaijan that, “the Working Group on ‘Improvement of legislation’ (including government and civil society participation) had started drafting the new Action Plan, stating that *“there is no strict deadline …, the timing of [the] drafting process could easily be increased for a month or even more.”[[9]](#footnote-9)*

In their next communication, dated December 02, 2015, the CS requested further information on the participating organizations, the themes to be included in the new action plan, and outlined that any extension of the previous action plan deadlines would depend “upon strengthening the consultation process by including other organizations and actors in the process and allowing them to suggest new commitments.”[[10]](#footnote-10)

In their last communication to CS in 2015, dated December 4, the Government of Azerbaijan relayed that the first public discussion had taken place on November 27, 2015 with “members of civil society institutions and other stakeholders,” that no proposals to address the operating environment had been presented by civil society, and that the organizations participating in the process had requested *“not to focus on January deadline and prolong the consultation period depending on the way [the] process develops with the aim to engage all stakeholders and provide enough time for well developed document” [sic].[[11]](#footnote-11)*

In light of this communication, the CS granted an extension for delivering the new National Action Plan to January 30 2016, noting that no further extensions would be granted. CS also requested again that the government of Azerbaijan provide a list of organizations participating in the action plan drafting process; the date, time and place of all public hearings at least 7 days in advance; and the minutes of all public hearings. These requests were communicated to the country on two separate occasions, via email on December 21, 2015 and in a formal letter on January 25, 2015.[[12]](#footnote-12) The letter, signed by Joseph Powell, the acting OGP executive director, also stated that: *“If no National Action Plan, which clearly addresses the issues raised during the review process, is received by January 30, 2016, the Criteria and Standards Subcommittee will begin deliberations on whether to make a recommendation to the Steering Committee on stage 2 actions, in accordance with the OGP Response Policy.”*

On Saturday January 30, 2016, the Government of Azerbaijan submitted the list of organizations that had participated in the action plan drafting process to date, stated that during the initial hearings no minutes were taken, and that at the moment they could not “*ensure that draft Action Plan will be ready for the end of January 2016*.”[[13]](#footnote-13)

Since the passing of the January 30, 2016 deadline, the Government of Azerbaijan has submitted three emails to the OGP Support Unit. On February 4 they stated that the next public hearing would be held on February 11, noting the call for participation was posted in both Azerbaijani and English languages on the commission website[[14]](#footnote-14) On February 5 they informed the OGP Support Unit that they had published a draft of the Action Plan on the Anticorruption Commission website, including recommendations from non-governmental organizations.[[15]](#footnote-15) Finally, on February 12 the Government of Azerbaijan sent photographs and the list of persons that participated in the February 11 public hearing.[[16]](#footnote-16)

***3. Assessment of Current Activities***

The following table compares the recommendations made to the Government of Azerbaijan as part of this Response Policy review process with the evidence available to this Subcommittee when the January 30 2016 deadline expired.

|  |  |
| --- | --- |
| CS Recommendation | Documented Activities |
| **1. Timeline for the next National Action Plan**. | **Not completed.**  On July 6, 2015, CS requested that the new Azerbaijan Action Plan be submitted by December 30, 2015. A one-month extension was granted and the Action Plan was due on January 30. No new extensions were granted and the Plan was not delivered.  On July 6, 2015, CS also requested a timeline to develop the National Action Plan in time for the August check in call; CS has yet to receive it despite several requests. Timeline availability is the first of the requirements traditionally evaluated by OGP regarding the consultation process. |
| **2. Consultation with civil society**. | **Not completed**  As part of the National Action Plan development process, the Government of Azerbaijan formed a Working Group that met once before the deadline and a second time after it.  The CS had recommended the government of Azerbaijan “consult with civil society organizations and citizens according to the OGP requirements.” This includes the following steps:   1. Availability of timeline. [Not delivered.] 2. Adequate notice 3. Awareness raising 4. Multiple channels 5. Breadth of consultation 6. Documentation and feedback 7. Consultation during implementation   The consultation is not yet complete, so the independent assessment regarding the consultation process could not take place. |
| **3. Peer exchange and technical support.** | **Not completed.**  The Government of Azerbaijan was not responsive once their public hearing began, which limited the chances to take advantage of peer exchange. |
| **4. Commitments to improve the operating environment for civil society**. | **Not completed**.  None of the commitments included in the available draft action plan address the particular laws identified by CS in its July recommendations (Law on Grants, Law on Non-governmental Organizations, Law on Registration of Legal Entities and State Registry, and the Code on Administrative Offenses), the recommendations made by third-party experts, or the barriers that NGOs currently face in registering and processing contracts and grants. The government has not taken steps to address any of these areas. |
| **5. Working with the OGP Steering Committee** | **Partially completed.**  The Government of Azerbaijan was mostly responsive to the OGP Support Unit channeling of CS requests. |

***4. Criteria and Standards Resolution***

The final communication to the Government of Azerbaijan outlined that “if no National Action Plan, which clearly addresses the issues raised during the review process, is received by January 30, 2016, the Criteria and Standards Subcommittee will begin deliberations on whether to make a recommendation to the Steering Committee on stage 2 actions.”

The evidence gathered shows that the Government of Azerbaijan has not effectively addressed the recommendations established by the Criteria and Standards Subcommittee or meaningfully addressed the issues raised in the original complaint and validated in the review process under the timeline established for stage 1 actions. The OGP Criteria and Standards Subcommittee therefore resolves to:

1. Consider that this issue now exceeds the mandate of the subcommittee;
2. Recommend that the OGP Steering Committee move to stage two actions;
3. In light of the information collected and actions taken so far, recommend that the OGP Steering Committee consider that the appropriate stage 2 action is for the country to be listed as inactive in OGP.

The Criteria and Standards subcommittee recalls that, under the OGP Response Policy, the inactive status of an OGP participating country, -- if designated as such by the full Steering Committee -- lasts until the concerns raised in the original complaint letter are resolved. To ascertain that steps were taken to remedy the situation that triggered the Response Policy, the government of Azerbaijan would have to undergo a new Criteria and Standards subcommittee review process, which may or may not recommend to the Steering Committee that the country be reengaged in OGP as an active participant. Specifically, the four areas highlighted in the original set of Criteria and Standards subcommittee recommendations would need to be adequately addressed for the group to recommend to the Steering Committee that Azerbaijan’s active status be restored. The Criteria and Standards subcommittee continues to hope that these steps will be taken in the near term and that Azerbaijan can reengage in OGP as an active participating government.

***Annex: Overview of Communications***

|  |  |  |  |
| --- | --- | --- | --- |
| **Document** | **Author** | **Date** | **Description** |
| Letter of concern | · **Dr Danny Sriskandarajah**, Secretary General, CIVICUS  · **Marinke van Riet**, International Director, PWYP  · **Thomas Hughes**, Executive Director, Article 19 | March 2, 2015 | Letter of concern submitted to the Steering Committee. |
| Government of Azerbaijan response | · **Dr. Azay Guliyev**, Member of Parliament Chairman of the Council of State Support to NGOs under the Auspices of the President Republic of Azerbaijan  · **Vusal Huseynov,** National point of Contact, Executive Secretary Anti-Corruption Commission of the Republic of Azerbaijan | April 15, 2015 | Response to the Letter of concern by the Government of Azerbaijan. |
| Summary of review team findings | · Review Team named by the Criteria and Standards Subcommittee | May 18, 2015 | Report by the review team that deems the Letter of complaint relevant and true. |
| OGP Criteria and Standard Subcommittee Briefing: Proposal for dialogue with Government of Azerbaijan | · Criteria and Standards Subcommittee | July 6, 2015 | Summary of proposed actions that the government of Azerbaijan should follow as part of the Stage one actions. |
| OGP Criteria and Standard Subcommittee Briefing: Proposal for dialogue with Government of Azerbaijan Annexes | · Support Unit | July 6, 2015 | Annexes to the Proposal for dialogue with Government of Azerbaijan: National Action Plan Guidance note, Consultation Guidance note, Guidance for Second National OGP Dialogue in Azerbaijan. |
| Response from Azerbaijan to Criteria and Standards Recommendations | · **Vusal Huseynov**, National point of Contact, Executive Secretary Anti-Corruption Commission of the Republic of Azerbaijan | August 28, 2016 | Response from the government of Azerbaijan to Criteria and Standards Recommendations. |
| Update on consultation from the government of Azerbaijan | · **Vusal Huseynov,** National point of Contact, Republic of Azerbaijan | November 12, 2015 | Update on development of the Azeri National Action Plan post-Summit and annex with list of Organizations participating in the consultation. |
| Request for further information by Support Unit (email) | · **Alonso Cerdan**, Program Manager, Support Unit | December 2, 2015 | Based on a request by the Criteria and Standards Subcommittee the Support Unit requested further information. |
| Response by Azerbaijan for further information | · **Vusal Huseynov,** National point of Contact, Republic of Azerbaijan | December 4, 2015 | Response by the government of Azerbaijan on the request for further information. |
| Letter from Joseph Powell | · **Joseph Powell**, Acting Director, Support Unit | January 25, 2016 | Letter form Joseph Powell to inform requests and decisions made by the Criteria and Standards Subcommittee |
| Update on consultation from Azerbaijan (email) | · **Kamal Jafarov**  Senior advisor of Secretariat Anti‐Corruption Commission of the Republic of Azerbaijan | January 30, 2016 | Email from Kamal Jafarov responding to information requests made by CS and informing that they will not meet the January 30 deadline. |
| Update on consultation from Azerbaijan (email) | · **Kamal Jafarov**  Senior advisor of Secretariat Anti‐Corruption Commission of the Republic of Azerbaijan | January 30, 2016 | Annex to Kamal’s email, list of organizations participating. |
| **Deadline established by Criteria and Standards Subcomittee** | | | |
| Update on consultation from Azerbaijan (email) | · **Kamal Jafarov**  Senior advisor of Secretariat Anti‐Corruption Commission of the Republic of Azerbaijan | February 4, 2016 | Email from Kamal Jafarov to inform that the next consultation meeting would take place on February 11. |
| Update on consultation from Azerbaijan (email) | · **Kamal Jafarov**  Senior advisor of Secretariat Anti‐Corruption Commission of the Republic of Azerbaijan | February 5, 2016 | Email from Kamal Jafarov to inform that the draft National Action Plan is available on the Anticorruption Commission website. |
| Update on consultation from Azerbaijan (email) | · **Kamal Jafarov**  Senior advisor of Secretariat Anti‐Corruption Commission of the Republic of Azerbaijan | February 12, 2016 | Email from Kamal Jafarov to give a brief update on the consultation meeting held on February 11. |
| Draft National Action Plan | · Government of Azerbaijan | February 5, 2016 | Translation of the draft National Action Plan presented in the Anticorruption Commission Website. |

1. Open Government Partnership. Policy on Upholding the Values and Principles of the OGP. OGP Articles of Governance. Addendum F. [↑](#footnote-ref-1)
2. The Response Policy is triggered when the SC, the chair of the CS, or the OGP Support Unit receives a letter of concern regarding a situation of relevance to OGP in a participating country from: 1) a fellow SC member –either government or civil society--; 2) a multilateral partner or Working Group co-anchor; 3) or a civil society, not-for-profit organization, or media organization involved in OGP at the national or international level. [↑](#footnote-ref-2)
3. Danny Sriskandarajah, Marinke van Riet, and Thomas Hughes. Letter of concern. March 2, 2015. Letter. [↑](#footnote-ref-3)
4. Azay, Guliyev and Vusal Huseynov, Response to the Letter of concern by the Government of Azerbaijan, April 15, 2015, letter. [↑](#footnote-ref-4)
5. Criteria and Standards Subcommittee. Summary of Review Team Findings. [↑](#footnote-ref-5)
6. OGP Criteria and Standard Subcommittee Briefing: Proposal for dialogue with Government of Azerbaijan, July 6, 2015. [↑](#footnote-ref-6)
7. OGP Criteria and Standard Subcommittee Briefing: Proposal for dialogue with Government of Azerbaijan, July 6, 2015. [↑](#footnote-ref-7)
8. Huseynov, Vusal. Response from Azerbaijan to Criteria and Standards Recommendations. August 28, 2015. Letter. [↑](#footnote-ref-8)
9. Huseynov, Vusal. Update on consultation from the government of Azerbaijan. November 12, 2015. Email. [↑](#footnote-ref-9)
10. Cerdan, Alonso- Request for further information by Support Unit. December 2, 2015. Email. [↑](#footnote-ref-10)
11. Huseynov, Vusal. Response by Azerbaijan for further information. December 4, 2015. Email. [↑](#footnote-ref-11)
12. Powell, Joseph. Letter from Joseph Powell, Acting Director, Support Unit. January 25, 2016. Letter. [↑](#footnote-ref-12)
13. Jafarov, Kamal. Update on consultation from Azerbaijan. January 30, 2016. Email. [↑](#footnote-ref-13)
14. Jafarov, Kamal. Update on consultation from Azerbaijan. February 4, 2016. Email. [↑](#footnote-ref-14)
15. Jafarov, Kamal. Update on consultation from Azerbaijan. February 5, 2016. Email. Draft Action Plan available at: <http://we.tl/O3atFu26AQ> [↑](#footnote-ref-15)
16. Jafarov, Kamal. Update on consultation from Azerbaijan. February 12, 2016. Email. [↑](#footnote-ref-16)