GOVERNMENT OF HUNGARY

to be published in: the Hungarian Gazette

Decision of the

G O V E R N M E N T

-------------------

on Hungary’s Second Action Plan on the commitments for the years 2015-2017 made under the Open Government Partnership initiative

- The Government concurs with the Action Plan of Hungary on the Commitments for the years 2015-2017 made under the Open Government Partnership initiative (hereinafter: OGP) and calls upon the Minister of Interior to have the Action Plan published on the Government portal and to forward it to the Steering Committee of the OGP.

Person in charge: 		Minister of Interior

Deadline: 			Immediately

- The Government hereby adopts the measures necessary to implement the objectives of the Action Plan.

- A methodological guideline shall be developed to ensure the publicity of local decision-making and to enhance the efficiency of related publication practices, the wide-scale application of which shall be promoted at the national level by organizing at least seven workshops for local governments.

Persons in charge: 	Minister of Interior

Minister heading the Prime Minister’s Office

Deadline: 			31 December, 2016

- The comprehensibility of central budget data accessible online shall be enhanced by raising the quality of the graphic presentation and taking further measures to ensure up-to-date access to the data.

Persons in charge: 	Minister for National Economy

Minister of Interior

Deadline: 			31 May, 2017

- A guideline shall be published in order to support compliance with the rules of contact with third parties representing private interests.

Persons in charge: 	Minister of Interior

Minister of Justice

Deadline: 			30 June, 2016

6.	An e-learning training on freedom of information providing clear guidance also on the self-reliant and proactive publication of data of public interest shall be developed and provided as part of the further training programs of public administration and local government organs.

Persons in charge: 	Minister of Interior

Minister heading the Prime Minister’s Office

Deadline: 			30 June, 2016

7.	With the National University of Public Services involved, a training package promoting corruption prevention and integrity shall be developed

- for local governments, ensuring awareness raising by organizing at least seven pilot training sessions at the national level;

- for citizens, helping awareness raising in civil society by the opportunity of free further use of the training package.

Persons in charge: 	Minister of Interior

Minister heading the Prime Minister’s Office

Deadline: 			31 December, 2016

8. 	A user-friendly electronic interface shall be developed for public consultation on legal acts and strategic planning documents, enabling the monitoring of the whole consultation process.

Persons in charge: 	Minister heading the Prime Minister’s Office

Minister of Justice

Minister of Interior

Deadline: 			30 June, 2016

9. 	Within the framework of a pilot project it shall be examined in what ways the searchability and processability of local government decrees and the records of municipal council sessions can be improved by introducing an internationally proven open standard.

Persons in charge: 	Minister of Interior

Minister heading the Prime Minister’s Office

Deadline: 			31 May, 2017

10. 	A free mobile phone application facilitating access to police organs and better communication between police and citizens shall be developed and made accessible.

Person in charge: 		Minister of Interior

Deadline: 			31 May, 2017

11. 	The Government hereby repeals Government Decision 1080/2013 (25 February) on the approval of the Action Plan on Hungary’s Commitments to be made in the framework of the Open Government Partnership international initiative.

12. 	This Decision shall enter into force on the day following its publication.

Budapest,    June, 2015

Viktor Orbán

Prime Minister

(signed manu propria)