# List of Abbreviations

| AG | Attorney General |
| --- | --- |
| CAG | Controller and Auditor General |
| CSOs CS DRAM | Civil Society Organisations Cabinet Secretariat Dynamic Random Access Memory |
| eGA | e-Government Agency |
| TEITI | Tanzania Extractive Industries Transparency Initiative |
| EWURA | Energy and Water Utilities Regulatory Authority |
| GIS | Geographical Information System |
| IMTC | Inter ministerial Technical Committee |
| LAAC | Local Authorities Accounts Committee |
| LGA’s | Local Government Authorities |
| MDA | Mining Development Agreements |
| MEM | Ministry of Energy and Minerals |
| MOF | Ministry of Finance |
| MOW | Ministry of Water |
| NBS | National Bureau of Statistics |
| OGP | Open Government Partnership |
| PAC | Public Accounts Committee |
| PMORALG | Prime Minister’s Office, Regional Administration and Local Government |
| PO PSM PSAs | President’s Office, Public Service Management Production Sharing Agreements |
| PSCs | Profit Sharing Agreements |
| RS | Regional Secretariats |
| TIC | Tanzania Investment Centre |
| TRA | Tanzania Revenue Authority |
| URT | The United Republic of Tanzania |

# ANNUAL PROGRESS REPORT ON OGP ACTION PLAN – PHASE II

# FOR THE YEAR 2014/2015

- Area: Access to Information.

Commitment: Enactment of Access to Information legislation by December 2014.

Lead Institution: Ministry of Constitutional and Legal Affairs

| S/n | Annual Planned Activities | Key Collaborators | Indicator | Time Frame | Actual Progress | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Get Government Approval through CS, IMTC, Cabinet and Preparation of Bill | AG, CSOs, Private Sector | Bill tabled in Parliament | December, 2014 | The Bill was tabled before Parliament for the First and Second reading in May, 2015 | Due to the formation of new Parliament, the process of tabling the Bill has to be re-established. The bill will be discussed in the Constitutional and Parliamentary Affairs committee and thereafter the Parliament processes will follow. |

- Area: Open Data.

Commitment: To establish a strong Open Data system by December 2016.

Lead Institution: Ministry of Finance

Implementing Institutions: Ministries of Education, Health, Water, eGA, NBS, National Archives, POPSM & PMOLARG.

| S/n | Annual Planned Activities | Key Collaborators | Indicator | Time Frame | Actual Progress | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Prepare guidelines on data management | PMO-RALG, Education, Health, Water, eGA, NBS CSOs and Private Sector | Guidelines in place | October, 2014 | Open data guidelines have been drafted and approved in January 2015 Data sets were identified, vetted and uploaded on the portal | The Open data guidelines are operational |
| 2 | Review existing data disclosure Policy, Act and Regulations. | PMO-RALG CSOs, Private Sector | Reviewed data disclosure Policy, Act and Regulations. | March, 2015 | Open Data Working Group comprised of members from NBS, eGA& DRAM was established to review the existing data disclosure Policy, Act and Regulations. | The review work will start in February, 2016. |
| 3 | Formulate Open Data Policy | PMO-RALG, Education, Health, Water, eGA, NBS, CSOs and Private Sector | Draft Policy in place | June, 2016 | Open data Policy Framework has been formulated Open Data Policy drafting is in progress | More funds are needed to accomplish the open data policy drafting process. |
| 4 | Establishment of Open Data Portal. | PMO-RALG, Education, Health, Water, eGA, NBS CSOs and Private Sector | Open Data Portal in place | June, 2015 | Open data portal www.opendata.go.tz was developed and is operational The Comprehensive Knowledge Archive Net Work (CKAN) technical training was provided Data visualizations have been developed to support the understanding of the datasets uploaded | More funds are needed to maintain the portal, develop more visualisation and mobile apps in order to improve its accessibility to citizens |
| 5 | Publish first set of Open Data (Education, Health and Water) on Open Data Portal and other platform. | PMO-RALG, Education, Health, Water, eGA, NBS, CSOs and Private Sector | Data published and accessible through Open Data Portal and respective Ministry websites | June, 2015 | The approved 16 data sets have been uploaded on the Government Portal www.opendata.go.tz as follows: Education: 5 data sets Health: 6 data sets Water: 3 data sets NBS: 2 data sets Water points data published on MoW website (www.maji.go.tz) and (https://wpm.maji.go.tz) showing functional and non-functional water points in all Local Government Authorities in Tanzania Mainland. EWURA published information on service performance and tariffs of the urban water supply authorities | More funds are needed to clean, upload and update data sets |
| 6 | Publish second set of Open Data (more on service delivery, surveys) on Open Data Portal and other platform. | PMO-RALG, Education, Health, Water, eGA, NBS, CSOs and Private Sector | Data published and accessible through open data portal and other platforms | December, 2015 | A total of 81 approved data sets were uploaded on the Government Open Data Portal www.opendata.go.tz as follows: Education: 48 data sets Health: 09 data sets Water: 10 data sets NBS: 14 data sets | More funds are needed to clean, upload and update more data sets |

- Area: Open Budgets.

Commitment 1: To make budget data (eight key budget reports) publicly available.

Lead Institution: Ministry of Finance

| S/n | Annual Planned Activities | Key Collaborators | Indicator | Time Frame | Actual Progress | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Publish eight key budget reports (pre-budget statement; budget proposal; enacted budget; citizens’ budget; in-year reports; mid-year review; year-end report; audit reports) online in real time. | PMO-RALG, CAG, CSOs, Private Sector | Number of budget reports published online. Number of District Council and facility with publishing on the notice board the basic budget information | December 2014 and Each Year | Seven key budgets reports have been finalised, published and uploaded on the MoF website. These are:- The 2015/16 Plan and Budget Guidelines. The 2015/16 Enacted Budget Books. The 2014/15 Citizens’ Budget. Expenditure Reports as of September, 2015 |  |
|  |  |  |  |  | Mid year Expenditure Flash Report. Monthly budget data posted on MDAs, RS and LGAs online and on notice boards. The 2015/16 Government Budget Speech is uploaded on the Ministry of Finance website. | Compilation of the year-end expenditure flash report is being finalized. More follow up needs to be made to ensure the expenditure be published in LGAs. |

Commitment 2: To publish reports of Oversight Committees.

| S/n | Annual Planned Activities | Key Collaborators | Indicator | Time Frame | Actual Progress | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Publish reports and recommendations of the PAC and LAAC within one month of report release. | Parliament of URT CSOs, Private Sector | Timely publication of Parliamentary reports | December 2014 and on-going | The PAC and LAAC reports of the year 2013/2014 were tabled and discussed in the 18th Parliamentary session in April, 2015. The reports are available on the Parliament website. Recommendations given by the Parliament are being worked upon by a Task Force which is under the Prime Minister’s Office. |  |

Commitment 3: To Publish Tax Exemptions.

| S/n | Annual Planned Activities | Key Collaborators | Indicator | Time Frame | Actual Progress | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Publish type, amount and entity for all tax exemptions on a monthly or quarterly basis | TRA | Timely publication of tax exemptions | December 2014 and on-going quarterly | The report for granted tax exemptions from April –June.2015 is being compiled. The report as of September, 2015 has been uploaded on the MoF website. |  |

- Area:  Land Transparency

Commitment: Make land use plan, ownership and demarcated areas for large-scale land deals accessible online for public use

Lead Institution: Ministry of Lands, Housing and Human Settlement Development.

Implementing Institutions: Prime Minister’s Office, Regional Administration and Local Government

| S/n | Annual Planned Activities | Key Collaborators | Indicator | Time Frame | Actual Progress | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Publish demarcated areas for large scale agricultural investment (farming and livestock keeping) | PMO-RALG CSOs, Private Sector TIC | Number of all registered large scale agricultural investments published online | December 2015 | Ground work and documentary process of establishment of Integrated Land Management Information System (ILMIS) to accommodate all land issues (Planning, Surveying, Land Use Plan, Allocation and Registration) to public needs finalized. List of 348 Demarcated areas for large scale agricultural investments in the Eastern Zone Identified and Verified ready to be filled to the System | Waiting to Award the winner Consultant of ILMIS Tender to start implementation. All demarcated areas country wide need to be identified. However, due to budgetary constraints to work has began in the Eastern Zone. List of 348 large scale agricultural investments has been uploaded on the Ministry website www.ardhi.go.tz |
| 2 | Publish Land Use Plans and make them accessible at both national and local levels | PMO-RALG | National Land Use Plans published online Number of Districts with land use plans published | December 2015 | Land use plans of villages having large scale farms have been prepared in Morogoro (9), Kilosa (5) and Mvomero (5), awaiting approval for publication | List of large scale farms has been uploaded on the Ministry website www.ardhi.go.tz |
| 3 | Make land ownership database online | PMO-RALG, CSOs and Private Sector | Database available online | December 2015 | List of 348 Ownership for large scale agricultural investments Eastern Zone Identified and Verified ready to be uploaded The list will be online via Ministry website in January, 2016 through www.ardhi.go.tz | Ownership country wide for large scale agricultural investments need to identified. However, due to budgetary constraint work has began in the Eastern Zone. |

- Area:  Extractive Industries Transparency.

Commitment: Government to fulfil its EITI Commitments.

Lead Institution: Ministry of Energy and Minerals.

| S/n | Annual Planned Activities | Key Collaborators | Indicator | Time Frame | Actual Progress | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Publish signed Mining Development Agreement (MDA), Profit sharing contracts (PSCs) from 2014 onwards | AG, TEIT | Number of Mining Development Agreement (MDA) and Profit Sharing Contracts (PSCs) signed. | By December, 2015 | The Tanzania Extractive Industries (Transparency and Accountability) Act of 2015 was enacted and came into force after being gazetted. The Act will enable the publication of signed Mining Development Agreements and Profit Sharing Contracts. | Regulations will be finalized by April 2016. Hence, Deadline for implementation of December 2015 is revised and will now be finalized by December 2016. |
| 2 | Document government’s policy on actual practice for disclosure of contracts signed before 2014. |  | Policy on actual practice for disclosure of contracts available. | By December 2015 | The TEITA Act (s.27) 2015 has made improvement as it provides mandatory disclosure of all MDAs and PSAs signed prior to the operation of this Act (i.e. before January 2014) except for information deemed to be confidential, as may be determined by TEITA Committee. | Regulations will be finalized by April 2016. Hence, Deadline for implementation of December 2015 is revised and will now be finalized by December 2016. |
| 3 | Publish demarcated areas for mining |  | Number of all registered large scale mines online | By December 2014 | 217 out of the total 423 large scale mines have been demarcated and uploaded on the MEM website. | 50% of Large scale mines are registered. |