## Sheet1
OGP ACTION PLAN ROADMAP - ELBASAN 2024-2025
Activities | Responsible | Necessary Resources | September | October | November | December | January | February | March | April | May | June
Onboarding
Signing of the Municipality-NDI-SHAV Memorandum of Understanding on Transparent Co-Governance Processes | Municipality of Elbasan-NDI-SHAV | N/A | 2024-09-26
The City Council approved the presented agreement. | Municipality of Elbasan | N/A |  | 2024-10-24
Build a team and select a forum
The municipality announced an open call for civil society organizations, media and activists, inviting them to contribute to the OGP process through its official platform. | Municipality of Elbasan | N/A | 2024-09-18
Establishment of a working group, composed of 9 members from the municipality, including: the Deputy Mayor, the Performance and Statistics Coordinator, the Right to Information Coordinator, specialists from various fields, with the aim of overseeing and implementing the provisions of the agreement. | Municipality of Elbasan | N/A |  | 2024-10-16
The Chairperson of the Municipality Council granted authorization to add three members from the Urban Development Commission in the Working Group established by the Mayor. | Municipality of Elbasan | N/A |  | 2024-10-17
The Mayor invited civil society representatives ( civil society organisations - ‘Tjeter Vizion”, “Women’s Forum Elbasan, Youth Roma and Egyptian Movement, and the Women Center for Development and Culture Albania- ; local media - Skampa TV and ATSH -, and two professors from Elbasan University, ) that responded to the open call and expressed interest to participate in the Municipality's working group on open government. | Municipality of Elbasan | N/A |  |  | 2024-11-07
Identify opportunity areas
NDI organized a two-day workshop in Tirana to identify the main challenges and priorities of the Municipality, including the development of the General Urban Plan and enhancing citizen participation n decision-making. The workshop participants engaged in strategic discussions and capacity building of the muncipality employees, civil society and academia representatives for the implementation of the OGP principles. | NDI | NDI supported event | 2024-09-30 | 2024-10-01
The Municipality of Elbasan held a follow-up meeting with participants from the Working Group, media, the Municipality Council, and NDI representatives, to discuss the priorities ad next steps from the two-day workshop in Tirana, where the Deputy Mayor, as Chair of the Technical Committee for the Local Development Plan, provided an update on the current progress of the plan and opened the discussion. The Municipality of Elbasan developed a questionnaire with all members of the working group, to identify opportunity and priority areas (identification of the priority of PPV and citizen engagement). | Municipality of Elbasan & working group | Municipality premisses |  | 2024-10-18
In November, NDI facilitated a Zoom meeting between Elbasan municipality and representatives from Banska Bistrika (a small Slovak municipality chapmioning OGP local) to exchange experiences on the OGP action plan, where valuable advice was provided on best practices in implementing OGP principles. | NDI - Municipality of Elbasan | Zoom |  |  | 2024-11-15
Prioritize opportunity areas
The Municipality of Elbasan will convene a consultation meeting with the working group to redefine priority areas as part of its engagement with the local Open Government Partnership (OGP). The obejtive of the meeting will be the achievement in a consensus on the key priority areas to which the municipality will be committed til the completion of its term. | The Working Group (Municipality of Elbasan and Civil Society) | Questionaire form |  |  |  | 2024-12-18
Identify solutions
The engagement of municipal staff in actively seeking and identifying solutions for each of the selcted commitments | Projects and Donors Sector Directorate of Coordination and Monitoring Human Resources Sector Coordinator for the Right to Information Media and Press Communication Sector Budget and Finance Directorate Projects and Urban Planning Directorate Directorate of Protection and Social Inclusion
The active engagement of civil society in addressing and contributing to solutions for community challenges, fostering collaboration, and promoting inclusive decision-making processes. | Representitive from Roma and Egyptian Community, Elbasan Women's Forum, Aleksander Xhuvani University, Tjeter Vizion, etc.
Build a commitment support network
Based on the selected commitment/priority area, invitations will be sent, and efforts will be made to engage other relevant stakeholders who can provide valuable input through comments and suggestions. This collaborative approach aims to support the development of a strategic vision and an actionable plan, ensuring that diverse perspectives are incorporated into the process. | The Working Group (Municipality of Elbasan and Civil Society)
Draft a strategic vision and commitments
The working group will collaborate to develop an initial draft of the action plan and strategic vision. This process will involve identifying key objectives, outlining proposed strategies, and setting a framework for achieving the selected commitments. The draft will serve as a foundation for further refinement through stakeholder input and consultation, ensuring it reflects diverse perspectives and addresses the community's needs effectively. | The Working Group (Municipality of Elbasan and Civil Society)
The working group will hold brainstorming sessions to collaboratively develop the strategic vision and action plan, ensuring alignment and shared ownership of the outcomes. | The Working Group (Municipality of Elbasan and Civil Society)
Validate action plan
A workshop will be organized to validate the action plan, providing a platform for stakeholders to review, assess, and offer feedback on the proposed strategies and activities. The goal is to ensure that the plan is realistic, relevant, and aligned with the community's needs and priorities. | Municipality of Elbasan
Gathering feedback from key stakeholders on the action plan through targeted meetings with specific groups. | The Working Group (Municipality of Elbasan and Civil Society)
Submit and share the action plan
Submit and share the Final action plan with relevant stakeholders for review and final approval, ensuring transparency and engagement in the process.
Prepare the inception assessment
Prepare the inception assessment and establishing monitoring mechanisms to track progress and ensure alignment with goals.